## Slide 1
Introduction
Andy Penev
Construction Management
CityCenterDC | Parcel 1
Washington, D.C.

## Slide 2
Project Overview
Analysis #1: SIPS
Background Information
New Phasing & SIPS
Impact
Analysis #2: Electrical Redesign
Background Information
Redesign
Impact
Analysis #3: Footbridge Installation
Background Information
Research
Application
Results
Final Recommendations
Acknowledgements
Project Overview
Andy Penev
Construction Management
CityCenterDC | Parcel 1
Washington, D.C.
Size: 257,500 SF
Location: Washington, D.C.
Project Cost: $48 million
Contract Type: (4) GMP
Delivery Method: Design-Bid-Build
Schedule: 4/11 – 1/14
Developer: Hines|Archstone
General Contractor: Clark/Smoot (JV)
Arch. of Record: Shalom Baranes Associates
Design Architect: Foster + Partners

## Slide 3
Project Overview
Analysis #1: SIPS
Background Information
New Phasing & SIPS
Impact
Analysis #2: Electrical Redesign
Background Information
Redesign
Impact
Analysis #3: Footbridge Installation
Background Information
Research
Application
Results
Final Recommendations
Acknowledgements
Andy Penev
Construction Management
CityCenterDC | Parcel 1
Washington, D.C.
Analysis #1: SIPS
Create a new phasing and sequencing plan for typical floor and implement through a Short Interval Production Schedule.
Analysis #2: Construction Analysis of Electrical Redesign
Propose an alternative electrical distribution system design and analyze its construction impacts.
Analysis #3: Alternative Footbridge Installation
Provide an alternative footbridge installation method to reduce cost and constructability issues.

## Slide 4
Project Overview
Analysis #1: SIPS
Background Information
New Phasing & SIPS
Impact
Analysis #2: Electrical Redesign
Background Information
Redesign
Impact
Analysis #3: Footbridge Installation
Background Information
Research
Application
Results
Final Recommendations
Acknowledgements
Analysis #1
Short Interval Production Schedule (SIPS)
Andy Penev
Construction Management
CityCenterDC | Parcel 1
Washington, D.C.

## Slide 5
Project Overview
Analysis #1: SIPS
Background Information
New Phasing & SIPS
Impact
Analysis #2: Electrical Redesign
Background Information
Redesign
Impact
Analysis #3: Footbridge Installation
Background Information
Research
Application
Results
Final Recommendations
Acknowledgements
Background Information
CityCenterDC | Parcel 1
Washington, D.C.
Analysis #1: SIPS
Framing & Plumbing Rough In
Risers
Mechanical Duct
AHU

## Slide 6
Project Overview
Analysis #1: SIPS
Background Information
New Phasing & SIPS
Impact
Analysis #2: Electrical Redesign
Background Information
Redesign
Impact
Analysis #3: Footbridge Installation
Background Information
Research
Application
Results
Final Recommendations
Acknowledgements
Background Information
CityCenterDC | Parcel 1
Washington, D.C.
Analysis #1: SIPS
Framing & Plumbing Rough In
Risers
Mechanical Duct
AHU

## Slide 7
Project Overview
Analysis #1: SIPS
Background Information
New Phasing & SIPS
Impact
Analysis #2: Electrical Redesign
Background Information
Redesign
Impact
Analysis #3: Footbridge Installation
Background Information
Research
Application
Results
Final Recommendations
Acknowledgements
New Phasing
CityCenterDC | Parcel 1
Washington, D.C.
Analysis #1: SIPS
Identify Duct Mains
Identify VAV Boxes

## Slide 8
Project Overview
Analysis #1: SIPS
Background Information
New Phasing & SIPS
Impact
Analysis #2: Electrical Redesign
Background Information
Redesign
Impact
Analysis #3: Footbridge Installation
Background Information
Research
Application
Results
Final Recommendations
Acknowledgements
New Phasing
CityCenterDC | Parcel 1
Washington, D.C.
Analysis #1: SIPS
Identify Duct Mains
Identify VAV Boxes

## Slide 9
Project Overview
Analysis #1: SIPS
Background Information
New Phasing & SIPS
Impact
Analysis #2: Electrical Redesign
Background Information
Redesign
Impact
Analysis #3: Footbridge Installation
Background Information
Research
Application
Results
Final Recommendations
Acknowledgements
New Phasing
CityCenterDC | Parcel 1
Washington, D.C.
Analysis #1: SIPS
Identify Duct Mains
Identify VAV Boxes

## Slide 10
Project Overview
Analysis #1: SIPS
Background Information
New Phasing & SIPS
Impact
Analysis #2: Electrical Redesign
Background Information
Redesign
Impact
Analysis #3: Footbridge Installation
Background Information
Research
Application
Results
Final Recommendations
Acknowledgements
New Phasing
CityCenterDC | Parcel 1
Washington, D.C.
Analysis #1: SIPS
Create zones on each floor
Crew stays in zone for given amount of time
Creates efficient use of space
Entire floor space is used
Important:
Clean up
Timely completion
Material management

## Slide 11
Project Overview
Analysis #1: SIPS
Background Information
New Phasing & SIPS
Impact
Analysis #2: Electrical Redesign
Background Information
Redesign
Impact
Analysis #3: Footbridge Installation
Background Information
Research
Application
Results
Final Recommendations
Acknowledgements
SIPS
CityCenterDC | Parcel 1
Washington, D.C.
Analysis #1: SIPS
Short Interval Production Schedule
Same crew
Same duration
Reorganization
Overlapping activities
Float on second half of activities

## Slide 12
Project Overview
Analysis #1: SIPS
Background Information
New Phasing & SIPS
Impact
Analysis #2: Electrical Redesign
Background Information
Redesign
Impact
Analysis #3: Footbridge Installation
Background Information
Research
Application
Results
Final Recommendations
Acknowledgements
Results
CityCenterDC | Parcel 1
Washington, D.C.
Analysis #1: SIPS
Cost
General Conditions
Total Savings = $20,524
Chart: 
| Project Management | Field Supervision | Equipment/Supplies
 | 10450 | 6700 | 3374.4
Constructability
Organization
Collaboration
Delays
Material Management
Deliveries
Schedule
Decreased by 13 days

## Slide 13
Project Overview
Analysis #1: SIPS
Background Information
New Phasing & SIPS
Impact
Analysis #2: Electrical Redesign
Background Information
Redesign
Impact
Analysis #3: Footbridge Installation
Background Information
Research
Application
Results
Final Recommendations
Acknowledgements
Analysis #2
Construction Analysis of Electrical Redesign
Andy Penev
Construction Management
CityCenterDC | Parcel 1
Washington, D.C.

## Slide 14
Project Overview
Analysis #1: SIPS
Background Information
New Phasing & SIPS
Impact
Analysis #2: Electrical Redesign
Background Information
Redesign
Impact
Analysis #3: Footbridge Installation
Background Information
Research
Application
Results
Final Recommendations
Acknowledgements
Background Information
CityCenterDC | Parcel 1
Washington, D.C.
Analysis #2: Electrical Redesign
2 Switchboards (4000A & 3000A)
Total kVA = 5,248
  20.4 W/SF
Separate retail feed
Lighting + Receptacle load = 2,092 kVA
  7.7 W/SF
4000A SWBD busway to electrical closets
  Took most of lighting and receptacle loads (1,902 kVA)

## Slide 15
Project Overview
Analysis #1: SIPS
Background Information
New Phasing & SIPS
Impact
Analysis #2: Electrical Redesign
Background Information
Redesign
Impact
Analysis #3: Footbridge Installation
Background Information
Research
Application
Results
Final Recommendations
Acknowledgements
Redesign
CityCenterDC | Parcel 1
Washington, D.C.
Analysis #2: Electrical Redesign
Chart: Ltg. + Receptacle Power Density
| Original | New
 | 7.7 | 4.1
ASHRAE Maximum Lighting Power Density = 0.9 W/SF
Receptacle Load = 2.4 W/SF
Total= 3.3 W/SF
 | kVA Load | FLA | Voltage | Phase | SWBD Size
Initial SWBD | 3173 | 3982 | 480 | 3 | 4000A
Revised SWBD | 2373 | 2978 | 480 | 3 | 3000A

## Slide 16
Project Overview
Analysis #1: SIPS
Background Information
New Phasing & SIPS
Impact
Analysis #2: Electrical Redesign
Background Information
Redesign
Impact
Analysis #3: Footbridge Installation
Background Information
Research
Application
Results
Final Recommendations
Acknowledgements
Redesign
CityCenterDC | Parcel 1
Washington, D.C.
Analysis #2: Electrical Redesign
Eliminate XFMR on floors 4,6, & 8
  Feed low voltage panels from floor above
Floors 5,7, & 9 XFMR step up to 150kVa
Feeders, plugs, breakers
Coordination of cores
  Fireproofing

## Slide 17
Project Overview
Analysis #1: SIPS
Background Information
New Phasing & SIPS
Impact
Analysis #2: Electrical Redesign
Background Information
Redesign
Impact
Analysis #3: Footbridge Installation
Background Information
Research
Application
Results
Final Recommendations
Acknowledgements
Redesign
CityCenterDC | Parcel 1
Washington, D.C.
Analysis #2: Electrical Redesign
Consolidation of HVAC panels
Smaller XFMR from reduced loads on 3rd floor
Feeders
Eliminate XFMR on floors 4,6, & 8
  Feed low voltage panels from floor above
Floors 5,7, & 9 XFMR step up to 150kVa
Feeders, plugs, breakers
Coordination of cores
  Fireproofing

## Slide 18
Project Overview
Analysis #1: SIPS
Background Information
New Phasing & SIPS
Impact
Analysis #2: Electrical Redesign
Background Information
Redesign
Impact
Analysis #3: Footbridge Installation
Background Information
Research
Application
Results
Final Recommendations
Acknowledgements
Results
CityCenterDC | Parcel 1
Washington, D.C.
Analysis #2: Electrical Redesign
ELECTRICAL RISER ROUGH IN | Hours per Floor | Crew Size
Original Design (5 day duration) | 76 | 2
Redesign Floor w/ XFMR | 79.75 | 2
Redesign Floor w/o XFMR | 31.42 | 1*
Total labor hours saved: 182
Dependency
Resource allocation
ELECTRICAL ROUGH IN | Hours per Floor | Crew Size
Original Design | 149 | 4
Redesign Floor w/ XFMR | 142.33 | 4
Redesign Floor w/o XFMR | 148.33 | 4
Schedule

## Slide 19
Project Overview
Analysis #1: SIPS
Background Information
New Phasing & SIPS
Impact
Analysis #2: Electrical Redesign
Background Information
Redesign
Impact
Analysis #3: Footbridge Installation
Background Information
Research
Application
Results
Final Recommendations
Acknowledgements
Results
CityCenterDC | Parcel 1
Washington, D.C.
Analysis #2: Electrical Redesign
ELECTRICAL RISER ROUGH IN | Hours per Floor | Crew Size
Original Design (5 day duration) | 76 | 2
Redesign Floor w/ XFMR | 79.75 | 2
Redesign Floor w/o XFMR | 31.42 | 1*
Total labor hours saved: 182
Dependency
Resource allocation
ELECTRICAL ROUGH IN | Hours per Floor | Crew Size
Original Design | 149 | 4
Redesign Floor w/ XFMR | 142.33 | 4
Redesign Floor w/o XFMR | 148.33 | 4
Schedule
Cost
Chart: 
| Material | Labor
 | 112761 | 8179
Chart: Cost Comparison
Material | 417299 | 304538
Labor | 90517 | 82338
Savings = $120,940
Original
Redesign

## Slide 20
Project Overview
Analysis #1: SIPS
Background Information
New Phasing & SIPS
Impact
Analysis #2: Electrical Redesign
Background Information
Redesign
Impact
Analysis #3: Footbridge Installation
Background Information
Research
Application
Results
Final Recommendations
Acknowledgements
Results
CityCenterDC | Parcel 1
Washington, D.C.
Analysis #2: Electrical Redesign
ELECTRICAL RISER ROUGH IN | Hours per Floor | Crew Size
Original Design (5 day duration) | 76 | 2
Redesign Floor w/ XFMR | 79.75 | 2
Redesign Floor w/o XFMR | 31.42 | 1*
Total labor hours saved: 182
Dependency
Resource allocation
ELECTRICAL ROUGH IN | Hours per Floor | Crew Size
Original Design | 149 | 4
Redesign Floor w/ XFMR | 142.33 | 4
Redesign Floor w/o XFMR | 148.33 | 4
Schedule
Cost
Constructability
Chart: 
| Material | Labor
 | 112761 | 8179
Item | Labor Hours
4000A Busway (59.4 lb/ft) | 719.9
3000A Busway (42.7 lb/ft) | 626
Labor Savings | 93.9
Horizontal bus runs quicker with lighter material
Less panels
Less XFMRs
Less cluttered electrical closet
Coring coordination
Fireproofing
Chart: Cost Comparison
Material | 417299 | 304538
Labor | 90517 | 82338
Original
Redesign
Savings = $120,940

## Slide 21
Project Overview
Analysis #1: SIPS
Background Information
New Phasing & SIPS
Impact
Analysis #2: Electrical Redesign
Background Information
Redesign
Impact
Analysis #3: Footbridge Installation
Background Information
Research
Application
Results
Final Recommendations
Acknowledgements
Analysis #3
Alternative Footbridge Installation
Andy Penev
Construction Management
CityCenterDC | Parcel 1
Washington, D.C.

## Slide 22
Project Overview
Analysis #1: SIPS
Background Information
New Phasing & SIPS
Impact
Analysis #2: Electrical Redesign
Background Information
Redesign
Impact
Analysis #3: Footbridge Installation
Background Information
Research
Application
Results
Final Recommendations
Acknowledgements
Background Information
CityCenterDC | Parcel 1
Washington, D.C.
Analysis #3: Footbridges
5 footbridges in between office buildings
Steel
Curtain wall
On floors 3,5,7,9, & 11

## Slide 23
Project Overview
Analysis #1: SIPS
Background Information
New Phasing & SIPS
Impact
Analysis #2: Electrical Redesign
Background Information
Redesign
Impact
Analysis #3: Footbridge Installation
Background Information
Research
Application
Results
Final Recommendations
Acknowledgements
Background Information
CityCenterDC | Parcel 1
Washington, D.C.
Analysis #3: Footbridges
Bridges
Prefabrication
  Including curtain wall
  Too much risk building in place
20’ long/each
36,666 lbs./each
Crane
500 ton mobile
220,500 lbs counterweight
138’ jib length
51,717 lifting capacity
Shoring underneath

## Slide 24
Project Overview
Analysis #1: SIPS
Background Information
New Phasing & SIPS
Impact
Analysis #2: Electrical Redesign
Background Information
Redesign
Impact
Analysis #3: Footbridge Installation
Background Information
Research
Application
Results
Final Recommendations
Acknowledgements
Research
CityCenterDC | Parcel 1
Washington, D.C.
Analysis #3: Footbridges
VSL Heavy Lifting
Hydraulic jacks
  Piston
  Tensile member
Gauges and control systems
  Synchronized movement
20 m/hr
Up to 10,000 tons
“For projects where notable weight, dimensions, or space limitations exclude the use of cranes or other conventional handling.” (VSL)

## Slide 25
Project Overview
Analysis #1: SIPS
Background Information
New Phasing & SIPS
Impact
Analysis #2: Electrical Redesign
Background Information
Redesign
Impact
Analysis #3: Footbridge Installation
Background Information
Research
Application
Results
Final Recommendations
Acknowledgements
Research
CityCenterDC | Parcel 1
Washington, D.C.
Analysis #3: Footbridges
VSL Heavy Lifting
Hydraulic jacks
  Piston
  Tensile member
Gauges and control systems
  Synchronized movement
20 m/hr
Up to 10,000 tons
“For projects where notable weight, dimensions, or space limitations exclude the use of cranes or other conventional handling.” (VSL)

## Slide 26
Project Overview
Analysis #1: SIPS
Background Information
New Phasing & SIPS
Impact
Analysis #2: Electrical Redesign
Background Information
Redesign
Impact
Analysis #3: Footbridge Installation
Background Information
Research
Application
Results
Final Recommendations
Acknowledgements
Research
CityCenterDC | Parcel 1
Washington, D.C.
Analysis #3: Footbridges
VSL Heavy Lifting
Hydraulic jacks
  Piston
  Tensile member
Gauges and control systems
  Synchronized movement
20 m/hr
Up to 10,000 tons
“For projects where notable weight, dimensions, or space limitations exclude the use of cranes or other conventional handling.” (VSL)
Petronas Towers
Damas Tower Footbridge

## Slide 27
Project Overview
Analysis #1: SIPS
Background Information
New Phasing & SIPS
Impact
Analysis #2: Electrical Redesign
Background Information
Redesign
Impact
Analysis #3: Footbridge Installation
Background Information
Research
Application
Results
Final Recommendations
Acknowledgements
Application
CityCenterDC | Parcel 1
Washington, D.C.
Analysis #3: Footbridges
4 jacks
Temporary beams span between atriums
Structural Considerations
  Steel strands
    Max. force: 12.6 kips
  Temporary beams
    Moment: 25.2 ft k
  Column buckling
    F.S. = 3.4

## Slide 28
Project Overview
Analysis #1: SIPS
Background Information
New Phasing & SIPS
Impact
Analysis #2: Electrical Redesign
Background Information
Redesign
Impact
Analysis #3: Footbridge Installation
Background Information
Research
Application
Results
Final Recommendations
Acknowledgements
Results
CityCenterDC | Parcel 1
Washington, D.C.
Analysis #3: Footbridges
Schedule

## Slide 29
Project Overview
Analysis #1: SIPS
Background Information
New Phasing & SIPS
Impact
Analysis #2: Electrical Redesign
Background Information
Redesign
Impact
Analysis #3: Footbridge Installation
Background Information
Research
Application
Results
Final Recommendations
Acknowledgements
Results
CityCenterDC | Parcel 1
Washington, D.C.
Analysis #3: Footbridges
Schedule
Cost
Constructability
Chart: 
Shop Drawings/Engineering | 200000 | 200000
Materials | 750000 | 750000
Shop Fabrication | 125000 | 125000
Equipment | 500000 | 150000
Guide cables
Prefabricate bridges onsite
17 days/bridge
  On portable platform

## Slide 30
Project Overview
Analysis #1: SIPS
Background Information
New Phasing & SIPS
Impact
Analysis #2: Electrical Redesign
Background Information
Redesign
Impact
Analysis #3: Footbridge Installation
Background Information
Research
Application
Results
Final Recommendations
Acknowledgements
Conclusion
CityCenterDC | Parcel 1
Washington, D.C.
Analysis #1: SIPS
Decrease schedule by 13 days
General conditions savings
Efficient use of floor space
Analysis #2: Construction Analysis of Electrical Redesign
Material & labor savings
Easier system to install
Reduction of crew size
Analysis #3: Alternative Footbridge Construction
Major equipment cost savings
Fewer constructability concerns
No schedule impact
Total Cost Savings: $491,464
Schedule Savings
Reduction of Constructability Concerns
Tenant Fit-Out
Efficiency

## Slide 31
Project Overview
Analysis #1: SIPS
Background Information
New Phasing & SIPS
Impact
Analysis #2: Electrical Redesign
Background Information
Redesign
Impact
Analysis #3: Footbridge Installation
Background Information
Research
Application
Results
Final Recommendations
Acknowledgements
Acknowledgements
CityCenterDC | Parcel 1
Washington, D.C.
Academic
Dr. John Messner
Dr. Robert Leicht
Dr. Richard Mistrick
Bob Holland
Ronald Dodson
Kevin Parfitt
Special Thanks
Family & Friends
CityCenterDC Project Team
PACE Industry Members
Al Hedin
Jared Oldroyd
Matt Orosz
Mike Current
Industry
Clark Construction
Truland
Hines
TSI
VSL
Thank You!

## Slide 32
Project Overview
Analysis #1: SIPS
Background Information
New Phasing & SIPS
Impact
Analysis #2: Electrical Redesign
Background Information
Redesign
Impact
Analysis #3: Footbridge Installation
Background Information
Research
Application
Results
Final Recommendations
Acknowledgements
CityCenterDC | Parcel 1
Washington, D.C.

## Slide 33
Appendix
CityCenterDC | Parcel 1
Washington, D.C.

## Slide 34
Appendix
CityCenterDC | Parcel 1
Washington, D.C.

## Slide 35
Appendix
CityCenterDC | Parcel 1
Washington, D.C.

## Slide 36
Appendix
CityCenterDC | Parcel 1
Washington, D.C.

## Slide 37
Appendix
CityCenterDC | Parcel 1
Washington, D.C.

## Slide 38
Appendix
CityCenterDC | Parcel 1
Washington, D.C.

## Slide 39
Appendix
CityCenterDC | Parcel 1
Washington, D.C.