## Sheet1
THESIS PROGRESS SCHEDULE 1/15/08 |  | Alex Wyczalkowski
McKinstry Oregon Headquarters |  | Mechanical Option
Portland Oregon |  | Dr. Jelena Srebric
Week | Activities
2009-01-12 | Update Proposal and Breadth Proposal
Meet with Professor Srebric
Progress Schedule
2009-01-19 | DOAS /Panel Research
Size Radiant Panels
Milestone: Jan 26 | Preliminary Research Done
2009-01-26 | Test Panels for Condensation
2009-02-02 | Lighting Breadth
Milestone: Feb 9 | Lighting Breadth complete
Radiant Panels Sized
2009-02-09 | Resize AHU for reduced airflow
2009-02-16 | Resize/Rearrange Ductwork
Milestone: Feb 23 | Redesign Complete
2009-02-23 | Energy Model
2009-03-02 | Acoustics Breadth
2009-03-09 | SPRING BREAK
Milestone: March 16 | Substantial Completion of Research
2009-03-16 | Begin Report
Check Calculations
Optional Research on Combined Heat and Power
2009-03-23 | Begin Presentation Design
Optional Research on Combined Heat and Power
2009-03-30 | Work On Report
Work On Presentation
Optional Research on Combined Heat and Power
2009-04-06 | Finish Report
Finish Presentation
2009-04-13 | Presentation Week
2009-04-20 | ABET Evaluation
CPEP Update