## Slide 1
AE Senior Thesis 2009
April 14th, 2009
50 Connell Drive
Berkeley Heights, NJ

## Slide 2: About Myself
Program
5th year Penn State AE
Hometown
Poughkeepsie, NY
Professional Experience:
Whiting-Turner 2007
  Loyola Dormitory
Turner Construction 2008
  WTC Tower 2
Jason Salyer
Construction Management

## Slide 3: Topics to be Presented
Analysis 1 – Panelized Façade System
Analysis 2 - High Performance Glazing
Analysis 3 - Prefabrication
Industry Issue - Reducing Operating Costs
Berkeley Heights, NJ
50 Connell Drive

## Slide 4
Background Info
Major Players:
Owner: Connell Real Estate & Development
CM: Turner Construction for Core & Shell
Architect: HLW International
General Data:
4 Story High End Office Building with Cafeteria
185,000 Total Square Feet
$38.9 Million Construction Cost
Dates of Construction (core & shell):
July 2007 to January 2009
Berkeley Heights, NJ
50 Connell Drive

## Slide 5
Background Info
Location:
20 miles west of NYC & adjacent to I-78
Berkeley Heights, NJ
50 Connell Drive

## Slide 6
Background Info
Structural:
Concrete Footings
Grade Beams
Structural Steel Frame
Composite Floor Slabs
Vertical Steel Cross Bracing
Berkeley Heights, NJ
50 Connell Drive

## Slide 7: Background Info
Mechanical Systems:
Concealed Mechanical Penthouse
2 Air Cooled Condensing Units (ACCU’s) per floor
2 pipe direct return air/water system
2 AHU’s supply 100% OA to the ACCU’s
Mechanical Penthouse
Berkeley Heights, NJ
50 Connell Drive

## Slide 8: Panelized Facade System
1
2
3
4
Berkeley Heights, NJ
50 Connell Drive

## Slide 9: Panelized Facade System
The Problem
The vertical joints between the window panels & stone panels were out of alignment
Each contractor blamed the other
Correct Alignment
Misalignment Joints
Berkeley Heights, NJ
50 Connell Drive
20% of windows had to be removed

## Slide 10: Panelized Facade System
Problem Statement:
Could using a single contractor for the façade prevented the alignment problems?
Berkeley Heights, NJ
50 Connell Drive

## Slide 11: Integrated Contractor
Panelized Facade System
Advantages | Disadvantages
Less Coordination | Finding Qualified Bidders
Strong Incentive for Quality Work | Chance of Subcontracting a Work Package
Eliminates “Finger Pointing” | CM has less Control Over the Process
Subs Claim it is More Cost Effective | Unqualified Subcontractor May get Hired
Subcontractor would be More Likely to Work Through a Problem on Their Own | Subcontracting Defeats the Goal of Using An Integrated Contractor
Potential Solution:
Berkeley Heights, NJ
50 Connell Drive

## Slide 12: Panelized Facade System
Dedicated Quality Control Staff:
Probably would have caught problem sooner
$8,000 more per month
Regular field personnel could be just as effective
Another Option:
Berkeley Heights, NJ
50 Connell Drive
Conclusion: Using an integrated contractor is not feasible since the disadvantages have major implications
Shop drawing coordination is the key to success
The experience was a lesson learned for everyone involved

## Slide 13: High Performance Glazing
Problem Statement
Can replacing the vision glass with a more
energy efficient glass result in long run energy
& equipment savings for the owner?
Methodology
Research and select a new type of glass
Perform energy modeling simulation
Compare costs
Berkeley Heights, NJ
50 Connell Drive

## Slide 14
High Performance Glazing
Current Glass - YCW 750 Spline Tech
Proposed Glass -Solarban® 70XL
Product Description: SolarBan is a revolutionary new Solar Control, Low-E glass manufactured by PPG that has been recognized as one of the most energy efficient on the market
Glass | U-Value
SplineTech 750 | 0.45
SolarBan70XL | 0.26
Berkeley Heights, NJ
50 Connell Drive
SolarBan has a lower rate of heat transfer

## Slide 15
Glazing Type | Square Foot Cost | Size of Panels (sf) | Cost per Unit | Number of Glass Units | Total Material Cost
Spline Tech | $10.45 | 35 | $365.75 | 589 | $215,427
SolarBan70XL | $9.25 | 35 | $323.75 | 589 | $190,689
High Performance Glazing
Material Cost Comparison:
Upfront Savings = $25,000
Berkeley Heights, NJ
50 Connell Drive

## Slide 16
Glazing Type | Estimated Operating Expenses | Annual Operating Savings | Estimated Total Capital Cooling HVAC Costs | Initial Capital Cost Savings | 1st Year Savings
Spline Tech | $1.56/sf | N/A | $7.63/sf | N/A | N/A
SolarBan70XL | $1.41/sf | $25,500* | $6.34/sf | $1.29/sf | $244,800*
*Based on 170,000 sf of office space |  |  |  |  | 
High Performance Glazing
The DOE’s 2.2 Building Energy Analysis Simulation Tool was
Used for this estimate
Simulation Results
Berkeley Heights, NJ
50 Connell Drive
SolarBan was used
on this university building
Over $200,000 saved in initial equipment cost
$25,500 saved per year in utility bills

## Slide 17
Summary of Findings |  |  |  |  |  |  | 
Glazing Type | U- Value | Square Foot Cost | Cost per Unit | Total Glass Material Cost | Glass Material Cost Savings | Estimated Energy Reduction | Estimated Equipment Cost Reduction
Spline Tech | 0.45 | $10.45 | $365.75 | $215,427 | N/A | N/A | N/A
SolarBan70XL | 0.26 | $9.25 | $323.75 | $190,689 | $24,738 | 9% | 16%
High Performance Glazing
Conclusion:
SolarBan70XL provides significant cost savings
9% Energy Reduction
16% Equipment Cost Reduction
SolarBan70XL should be used in place of SplineTech750
Berkeley Heights, NJ
50 Connell Drive

## Slide 18: Prefabrication
Problem Statement:
Would replacing the mechanical equipment with a modular central plant
be beneficial for the project?
Berkeley Heights, NJ
50 Connell Drive

## Slide 19
Prefabrication
What is it?
Modular Plants Combine
Chiller
Pumps
Cooling Tower
Interconnecting Pipes
All in one pre-assembled module
Berkeley Heights, NJ
50 Connell Drive

## Slide 20
Prefabrication
Modular Central Plant vs. Site Built Plant | 
Advantages | Disadvantages
Reduced owner & contractor risk | Long lead time
Single source supplier | Heavy loads
Fast site assembly time | Structural coordination
Reduced trade coordination | Rigging & crane requirements
Less field labor required | Vibration isolation
Easily expandable | May need to locate on grade
Berkeley Heights, NJ
50 Connell Drive

## Slide 21
Prefabrication
Rigging Requirements
66 Ton Equipment Weight
Must balance load
Multiple Spreader Bars & Shackles
1” Cables, 1” Shackles Minimum
Experienced Rigging Crew Essential
Berkeley Heights, NJ
50 Connell Drive

## Slide 22
Prefabrication
Key Assumption: 7 days to connect wiring & piping hookups
Modular vs. Site Built Plants
Begin Start up and Testing
37 Days
Berkeley Heights, NJ
50 Connell Drive

## Slide 23
Prefabrication
Elevation of MCP Located on Grade
2 Options
Increase size of structural members = $$$
Locate on grade = Eyesore
Berkeley Heights, NJ
50 Connell Drive
STAAD Analysis: Supporting W18x35 will deflect at least 2” = not acceptable

## Slide 24
Design Concern #1
High Volume of Air Required compared to the 8 ACCU’s
What does this mean?
MCP would require 185,000 CFM (total supply & return)
This requires 2 vertical shafts (supply & return) each measuring 6’ x 7’
Why is this Bad?
Too much floor space used – Lack of vertical shaft space
Large ductwork heavier & more expensive to construct & support
Supply & return fan would be required
Very high horsepower motors required for fans
Prefabrication
Berkeley Heights, NJ
50 Connell Drive

## Slide 25
Design Concern #2
Service failure = no AC for entire building
Why is this bad?
The building is unoccupiable until the unit is fixed.
What about the current design?
2 units per floor provide cooling
If one unit fails the other unit can still cool the floor while the other is being repaired
All units are required only for peak design load
Prefabrication
Berkeley Heights, NJ
50 Connell Drive

## Slide 26
Design Concern #3
Replacement parts are large must be special ordered
What does this mean?
Must keep parts in stock or wait until they arrive for service
Why is this bad?
Long lead time
The building may be without cooling capabilities for an extended period of time
Prefabrication
Example:
Replacement motors for the fans are very large
and may require a crane.
The parts for the actual equipment are smaller and easily attainable.
Berkeley Heights, NJ
50 Connell Drive

## Slide 27
Prefabrication
Conclusion
A modular plant is not a good option for this building
Why?
Even though it has a faster installation time the disadvantages create bigger problems.
Berkeley Heights, NJ
50 Connell Drive

## Slide 28
Reducing Operating Costs
Critical Industry Issue
Energy Costs are expected to rise dramatically in the next decade
Energy modeling prior to construction
Use of efficient equipment & water efficient fixtures
Take advantage of state rebates for efficient equipment
Energy monitory
Optimizing operating set points
Continuous commissioning
Techniques to Reduce Costs
Berkeley Heights, NJ
50 Connell Drive

## Slide 29
The End
Questions or Comments?
Berkeley Heights, NJ
50 Connell Drive