## Slide 1
Outline
Additional Information
Holiday Inn Express
Thesis by: Josh Raphael
Architectural Engineering
Construction Management
Introduction
  Personal and Building Intro
Building Background
  Building Size, Location, and Type
  Current Budget and Schedule
  Areas for Improvement/Client Influence
Analysis 1: Solyndra Solar Panel Implementation
  Installation location
  Sizing the Panel Layout
  Schedule and Labor Analysis
  Cost Analysis
  Energy Savings Analysis/Payback
Analysis 2: SIP Panel Implementation
  SIP Application
  SIP vs. Stick Built
    Material Cost
    Schedule and Labor Analysis
    Energy Savings Analysis/Payback
Analysis 3: BAS Systems
  BAS System Application
    Bathroom Nightlight motion Sensor
    Hallway Motion Sensor
    Motion Sensor PTAC
Conclusion
  Final Schedule and Budget
  Final Decisions (What and What Not to Proceed With)
  Q/A

## Slide 2
Outline
Additional Information
Holiday Inn Express
Building Background
Location - 655 White Horse Pike, Absecon, NJ
Mixed Separate Use Group – R-1 Residential/ A-3 Assembly
Construction Type – V-B
Addition Area
    First Floor (A-3): 4,912 ft2
    First Floor (R-1): 6,475 ft2
    Second Floor (R-1): 7,984 ft2
    Third Floor (R-1): 7,984 ft2
Total initial Cost - $4 Million
Date of Construction – March 2009 – April 2010
Owner – Renuka Hospitality, LLC
General Contractor – DRK Associates
Architect – Harry S. Harper Architects
Introduction
  Personal and Building Intro
Building Background
  Building Size, Location, and Type
  Current Budget and Schedule
  Areas for Improvement/Client Influence
Analysis 1: Solyndra Solar Panel Implementation
  Installation location
  Sizing the Panel Layout
  Schedule and Labor Analysis
  Cost Analysis
  Energy Savings Analysis/Payback
Analysis 2: SIP Panel Implementation
  SIP Application
  SIP vs. Stick Built
    Material Cost
    Schedule and Labor Analysis
    Energy Savings Analysis/Payback
Analysis 3: BAS Systems
  BAS System Application
    Bathroom Nightlight motion Sensor
    Hallway Motion Sensor
    Motion Sensor PTAC
Conclusion
  Final Schedule and Budget
  Final Decisions (What and What Not to Proceed With)
  Q/A

## Slide 3
Outline
Additional Information
Holiday Inn Express
Introduction
  Personal and Building Intro
Building Background
  Building Size, Location, and Type
  Current Budget and Schedule
  Areas for Improvement/Client Influence
Analysis 1: Solyndra Solar Panel Implementation
  Installation location
  Sizing the Panel Layout
  Schedule and Labor Analysis
  Cost Analysis
  Energy Savings Analysis/Payback
Analysis 2: SIP Panel Implementation
  SIP Application
  SIP vs. Stick Built
    Material Cost
    Schedule and Labor Analysis
    Energy Savings Analysis/Payback
Analysis 3: BAS Systems
  BAS System Application
    Bathroom Nightlight motion Sensor
    Hallway Motion Sensor
    Motion Sensor PTAC
Conclusion
  Final Schedule and Budget
  Final Decisions (What and What Not to Proceed With)
  Q/A
Current Budget & Schedule
Schedule Summary
  Project Duration – 13 Months
  Milestones
    Substructure Complete
    MEP Installation Complete
    Building Structure Complete
Cost Summary
  Approximate Project Cost – $4 Million (Owner Estimate)
  Approximate Project Cost - $4.7 Million (Square Ft Estimate)

## Slide 4
Outline
Additional Information
Holiday Inn Express
Introduction
  Personal and Building Intro
Building Background
  Building Size, Location, and Type
  Current Budget and Schedule
  Areas for Improvement/Client Influence
Analysis 1: Solyndra Solar Panel Implementation
  Installation location
  Sizing the Panel Layout
  Schedule and Labor Analysis
  Cost Analysis
  Energy Savings Analysis/Payback
Analysis 2: SIP Panel Implementation
  SIP Application
  SIP vs. Stick Built
    Material Cost
    Schedule and Labor Analysis
    Energy Savings Analysis/Payback
Analysis 3: BAS Systems
  BAS System Application
    Bathroom Nightlight motion Sensor
    Hallway Motion Sensor
    Motion Sensor PTAC
Conclusion
  Final Schedule and Budget
  Final Decisions (What and What Not to Proceed With)
  Q/A
Areas for Improvement/Client Influence
Issues
  Guest Waste Energy
    Bathroom Night lighting
    Lighting, Heating, & Cooling During Vacancy
  Heating & Cooling Loss from Stud Wall Construction
  Lack of Energy Efficiency Efforts
Solutions
  Solyndra Solar Panel Installation
  SIP Panel Implementation
  BAS Systems

## Slide 5
Outline
Additional Information
Holiday Inn Express
Introduction
  Personal and Building Intro
Building Background
  Building Size, Location, and Type
  Current Budget and Schedule
  Areas for Improvement/Client Influence
Analysis 1: Solyndra Solar Panel Implementation
  Installation location
  Sizing the Panel Layout
  Schedule and Labor Analysis
  Cost Analysis
  Energy Savings Analysis/Payback
Analysis 2: SIP Panel Implementation
  SIP Application
  SIP vs. Stick Built
    Material Cost
    Schedule and Labor Analysis
    Energy Savings Analysis/Payback
Analysis 3: BAS Systems
  BAS System Application
    Bathroom Nightlight motion Sensor
    Hallway Motion Sensor
    Motion Sensor PTAC
Conclusion
  Final Schedule and Budget
  Final Decisions (What and What Not to Proceed With)
  Q/A
Analysis 1:
Solyndra Solar Panels

## Slide 6
Outline
Additional Information
Holiday Inn Express
Introduction
  Personal and Building Intro
Building Background
  Building Size, Location, and Type
  Current Budget and Schedule
  Areas for Improvement/Client Influence
Analysis 1: Solyndra Solar Panel Implementation
  Installation location
  Sizing the Panel Layout
  Schedule and Labor Analysis
  Cost Analysis
  Energy Savings Analysis/Payback
Analysis 2: SIP Panel Implementation
  SIP Application
  SIP vs. Stick Built
    Material Cost
    Schedule and Labor Analysis
    Energy Savings Analysis/Payback
Analysis 3: BAS Systems
  BAS System Application
    Bathroom Nightlight motion Sensor
    Hallway Motion Sensor
    Motion Sensor PTAC
Conclusion
  Final Schedule and Budget
  Final Decisions (What and What Not to Proceed With)
  Q/A
About Solyndra Solar Panels
Cylindrical PV Tubes – 360º Absorption (Direct, Diffuse, & Reflected Sunlight)
Most Efficient Solar Technology
Air Flow
  Withstand Wind Up to 130mph (Absecon < 120mph)
  Prevents Panel Overheating
Quick & Easy Installation – No need to mount
Greater Rooftop Coverage

## Slide 7
Outline
Additional Information
Holiday Inn Express
Introduction
  Personal and Building Intro
Building Background
  Building Size, Location, and Type
  Current Budget and Schedule
  Areas for Improvement/Client Influence
Analysis 1: Solyndra Solar Panel Implementation
  Installation location
  Sizing the Panel Layout
  Schedule and Labor Analysis
  Cost Analysis
  Energy Savings Analysis/Payback
Analysis 2: SIP Panel Implementation
  SIP Application
  SIP vs. Stick Built
    Material Cost
    Schedule and Labor Analysis
    Energy Savings Analysis/Payback
Analysis 3: BAS Systems
  BAS System Application
    Bathroom Nightlight motion Sensor
    Hallway Motion Sensor
    Motion Sensor PTAC
Conclusion
  Final Schedule and Budget
  Final Decisions (What and What Not to Proceed With)
  Q/A
Installation Location
Location – South East Facing Roofs of Both the New & Existing Buildings (Green Shading)
Panel Size & Layout
Panel Size – 6’ x 3.5’
Panel Power – 191Wp Standard Test Conditions (Irradiance of 1000 W/m^2, air mass 1.5, and cell temperature of 25˚C)
Availiable Roof Area – 11760 ft2
Panel Count – 500 Panels
System Power – 95.5 kW Power

## Slide 8
Outline
Additional Information
Holiday Inn Express
Introduction
  Personal and Building Intro
Building Background
  Building Size, Location, and Type
  Current Budget and Schedule
  Areas for Improvement/Client Influence
Analysis 1: Solyndra Solar Panel Implementation
  Installation location
  Sizing the Panel Layout
  Schedule and Labor Analysis
  Cost Analysis
  Energy Savings Analysis/Payback
Analysis 2: SIP Panel Implementation
  SIP Application
  SIP vs. Stick Built
    Material Cost
    Schedule and Labor Analysis
    Energy Savings Analysis/Payback
Analysis 3: BAS Systems
  BAS System Application
    Bathroom Nightlight motion Sensor
    Hallway Motion Sensor
    Motion Sensor PTAC
Conclusion
  Final Schedule and Budget
  Final Decisions (What and What Not to Proceed With)
  Q/A
Schedule & labor Analysis
Labor Rate – 10 Panels/Hr, Using a 3 Man Crew
Installation Duration – 6.25 Days
Schedule Adjustment
  Panel Installation Proceeding Roof Installment
  Installation simultaneous with site work
Cost Analysis
Panel Material/Installation Cost – $5.42/W
Rebates
  Federal - Investment Tax Credit(ITC) 30% of the Entire Energy System
  State – Eliminates NJ State Tax of 7%
Final Cost per Watt - $4.13/W
Final System Cost – $394,041

## Slide 9
Outline
Additional Information
Holiday Inn Express
Introduction
  Personal and Building Intro
Building Background
  Building Size, Location, and Type
  Current Budget and Schedule
  Areas for Improvement/Client Influence
Analysis 1: Solyndra Solar Panel Implementation
  Installation location
  Sizing the Panel Layout
  Schedule and Labor Analysis
  Cost Analysis
  Energy Savings Analysis/Payback
Analysis 2: SIP Panel Implementation
  SIP Application
  SIP vs. Stick Built
    Material Cost
    Schedule and Labor Analysis
    Energy Savings Analysis/Payback
Analysis 3: BAS Systems
  BAS System Application
    Bathroom Nightlight motion Sensor
    Hallway Motion Sensor
    Motion Sensor PTAC
Conclusion
  Final Schedule and Budget
  Final Decisions (What and What Not to Proceed With)
  Q/A
Energy Savings Analysis: Electrical Breadth
Average Solar Radiation – 4.67 kWh/m2/day
Absecon Electricity Cost – 13 ¢/kWh
Future Carbon Tax – Increased energy cost $0.1027 – $0.1137 /kWh
Carbon Footprint – Savings of 170,007 lbs of CO2/yr
  Energy Savings – 118,886 kWh
Cost Savings
  No Carbon Tax - $15,455/yr
  With Carbon Tax - $28,533/yr
Payback
Payback Period
  No Carbon Tax – 25.5 years
  With Carbon Tax – 13.8 Years

## Slide 10
Outline
Additional Information
Holiday Inn Express
Introduction
  Personal and Building Intro
Building Background
  Building Size, Location, and Type
  Current Budget and Schedule
  Areas for Improvement/Client Influence
Analysis 1: Solyndra Solar Panel Implementation
  Installation location
  Sizing the Panel Layout
  Schedule and Labor Analysis
  Cost Analysis
  Energy Savings Analysis/Payback
Analysis 2: SIP Panel Implementation
  SIP Application
  SIP vs. Stick Built
    Material Cost
    Schedule and Labor Analysis
    Energy Savings Analysis/Payback
Analysis 3: BAS Systems and Wireless Controls
  BAS System Application
    Bathroom Nightlight motion Sensor
    Hallway Motion Sensor
    Motion Sensor PTAC
Conclusion
  Final Schedule and Budget
  Final Decisions (What and What Not to Proceed With)
  Q/A
Analysis 2:
Structural Insulated Panels

## Slide 11
Outline
Additional Information
Holiday Inn Express
Introduction
  Personal and Building Intro
Building Background
  Building Size, Location, and Type
  Current Budget and Schedule
  Areas for Improvement/Client Influence
Analysis 1: Solyndra Solar Panel Implementation
  Installation location
  Sizing the Panel Layout
  Schedule and Labor Analysis
  Cost Analysis
  Energy Savings Analysis/Payback
Analysis 2: SIP Panel Implementation
  SIP Application
  SIP vs. Stick Built
    Material Cost
    Schedule and Labor Analysis
    Energy Savings Analysis/Payback
Analysis 3: BAS Systems
  BAS System Application
    Bathroom Nightlight motion Sensor
    Hallway Motion Sensor
    Motion Sensor PTAC
Conclusion
  Final Schedule and Budget
  Final Decisions (What and What Not to Proceed With)
  Q/A
About SIP Panels
Structurally Sound – Stronger & Straighter
R – Value – R 24.7 compared to R19
Prefabrication – Lower on Site Labor Cost
Labor – 50-70% Faster
SIP Application
Exterior Wall - 6” SIP Panel vs. 2 x 6” Stud Construction
Location – 1st, 2nd, & 3rd Floor Addition Exterior Walls
Exterior Wall Area – 15,274 ft2

## Slide 12
Outline
Additional Information
Holiday Inn Express
Introduction
  Personal and Building Intro
Building Background
  Building Size, Location, and Type
  Current Budget and Schedule
  Areas for Improvement/Client Influence
Analysis 1: Solyndra Solar Panel Implementation
  Installation location
  Sizing the Panel Layout
  Schedule and Labor Analysis
  Cost Analysis
  Energy Savings Analysis/Payback
Analysis 2: SIP Panel Implementation
  SIP Application
  SIP vs. Stick Built
    Material Cost
    Schedule and Labor Analysis
    Energy Savings Analysis/Payback
Analysis 3: BAS Systems and Wireless Controls
  BAS System Application
    Bathroom Nightlight motion Sensor
    Hallway Motion Sensor
    Motion Sensor PTAC
Conclusion
  Final Schedule and Budget
  Final Decisions (What and What Not to Proceed With)
  Q/A
SIP vs. Stick Built
Material Cost
  Initial Cost of SIP Panels - $60,188
  Budget Increase - $14,690, about 33% more expensive than Stick Built
Schedule & Labor Analysis
  Current Framing Duration – 26 Days (All 3 Floors)
  New Framing Duration – 17 Days ( All 3 Floors)
  Estimated Schedule Reduction – 50%, 4 Days/Floor
  Schedule Reduction – 3 Days/Floor (Learning Curve)
  Total Reduction – 9 Days

## Slide 13
Outline
Additional Information
Holiday Inn Express
Introduction
  Personal and Building Intro
Building Background
  Building Size, Location, and Type
  Current Budget and Schedule
  Areas for Improvement/Client Influence
Analysis 1: Solyndra Solar Panel Implementation
  Installation location
  Sizing the Panel Layout
  Schedule and Labor Analysis
  Cost Analysis
  Energy Savings Analysis/Payback
Analysis 2: SIP Panel Implementation
  SIP Application
  SIP vs. Stick Built
    Material Cost
    Schedule and Labor Analysis
    Energy Savings Analysis/Payback
Analysis 3: BAS Systems
  BAS System Application
    Bathroom Nightlight motion Sensor
    Hallway Motion Sensor
    Motion Sensor PTAC
Conclusion
  Final Schedule and Budget
  Final Decisions (What and What Not to Proceed With)
  Q/A
Energy Efficiency Analysis: Mechanical Breadth
Leakage
  2 x 6” (Poor Leakage) – 857 MBTU, 251,101 kWh
  2 x 6” (Avg. Leakage) – 678 MBTU, 198,654 kWh
  SIP Panel – 297 MBTU, 87,021 kWh
Energy Cost Absecon, NJ
  2 x 6” (Poor Leakage) – $32,643
  2 x 6” (Avg. Leakage) – $25,825
  SIP Panel – $11,313
  Savings (Avg. Leakage)- $14,512/yr
  Payback
  Payback Period – 1-2 years

## Slide 14
Outline
Additional Information
Holiday Inn Express
Introduction
  Personal and Building Intro
Building Background
  Building Size, Location, and Type
  Current Budget and Schedule
  Areas for Improvement/Client Influence
Analysis 1: Solyndra Solar Panel Implementation
  Installation location
  Sizing the Panel Layout
  Schedule and Labor Analysis
  Cost Analysis
  Energy Savings Analysis/Payback
Analysis 2: SIP Panel Implementation
  SIP Application
  SIP vs. Stick Built
    Material Cost
    Schedule and Labor Analysis
    Energy Savings Analysis/Payback
Analysis 3: BAS Systems
  BAS System Application
    Bathroom Nightlight motion Sensor
    Hallway Motion Sensor
    Motion Sensor PTAC
Conclusion
  Final Schedule and Budget
  Final Decisions (What and What Not to Proceed With)
  Q/A
Analysis 3:
Building Automated Systems

## Slide 15
Outline
Additional Information
Holiday Inn Express
Introduction
  Personal and Building Intro
Building Background
  Building Size, Location, and Type
  Current Budget and Schedule
  Areas for Improvement/Client Influence
Analysis 1: Solyndra Solar Panel Implementation
  Installation location
  Sizing the Panel Layout
  Schedule and Labor Analysis
  Cost Analysis
  Energy Savings Analysis/Payback
Analysis 2: SIP Panel Implementation
  SIP Application
  SIP vs. Stick Built
    Material Cost
    Schedule and Labor Analysis
    Energy Savings Analysis/Payback
Analysis 3: BAS Systems
  BAS System Application
    Bathroom Nightlight motion Sensor
    Hallway Motion Sensor
    Motion Sensor PTAC
Conclusion
  Final Schedule and Budget
  Final Decisions (What and What Not to Proceed With)
  Q/A
About BAS Systems
Product Suppliers – Prolighting, Lutron, Watt Stoppers
Use – Eliminate Energy Consumption During Vacancy
BAS System Application
3 Areas for Implementation
  Bathroom Nightlight/Motion Sensor Switch
  2. Hallway Motion Sensors
  3. Motion Sensor PTAC

## Slide 16
Outline
Additional Information
Holiday Inn Express
Introduction
  Personal and Building Intro
Building Background
  Building Size, Location, and Type
  Current Budget and Schedule
  Areas for Improvement/Client Influence
Analysis 1: Solyndra Solar Panel Implementation
  Installation location
  Sizing the Panel Layout
  Schedule and Labor Analysis
  Cost Analysis
  Energy Savings Analysis/Payback
Analysis 2: SIP Panel Implementation
  SIP Application
  SIP vs. Stick Built
    Material Cost
    Schedule and Labor Analysis
    Energy Savings Analysis/Payback
Analysis 3: BAS Systems
  BAS System Application
    Bathroom Nightlight motion Sensor
    Hallway Motion Sensor
    Motion Sensor PTAC
Conclusion
  Final Schedule and Budget
  Final Decisions (What and What Not to Proceed With)
  Q/A
  Bathroom Nightlight/Motion Sensor Switch
About
  The switch shuts off energy when vacant
  The switch acts as a low energy nightlight
Reasons
  40% of Hotel guest use bathroom as nightlight
  75% of fixture energy used when operating for more than 2 Hrs (Usually during guest vacancy)
Initial Cost
  New Switch – $38/each, about $20 more than regular switches
  Cost Increase - $980

## Slide 17
Outline
Additional Information
Holiday Inn Express
Introduction
  Personal and Building Intro
Building Background
  Building Size, Location, and Type
  Current Budget and Schedule
  Areas for Improvement/Client Influence
Analysis 1: Solyndra Solar Panel Implementation
  Installation location
  Sizing the Panel Layout
  Schedule and Labor Analysis
  Cost Analysis
  Energy Savings Analysis/Payback
Analysis 2: SIP Panel Implementation
  SIP Application
  SIP vs. Stick Built
    Material Cost
    Schedule and Labor Analysis
    Energy Savings Analysis/Payback
Analysis 3: BAS Systems
  BAS System Application
    Bathroom Nightlight motion Sensor
    Hallway Motion Sensor
    Motion Sensor PTAC
Conclusion
  Final Schedule and Budget
  Final Decisions (What and What Not to Proceed With)
  Q/A
  Bathroom Nightlight/Motion Sensor Switch
Energy Efficiency Analysis: Electrical Breadth
  Bathroom lighting – 3 (100W) Incandescent
  Typical Energy Usage – 190 min/day
  Energy Usage W/ New Switch – 68 min/day
  Daily Use Reduction –122min/day/unit
  Annual Energy Savings – 16,993 kWh/year
  Annual Cost Savings - $2,210/year
Payback
  Payback Period - .5 years

## Slide 18
Outline
Additional Information
Holiday Inn Express
Introduction
  Personal and Building Intro
Building Background
  Building Size, Location, and Type
  Current Budget and Schedule
  Areas for Improvement/Client Influence
Analysis 1: Solyndra Solar Panel Implementation
  Installation location
  Sizing the Panel Layout
  Schedule and Labor Analysis
  Cost Analysis
  Energy Savings Analysis/Payback
Analysis 2: SIP Panel Implementation
  SIP Application
  SIP vs. Stick Built
    Material Cost
    Schedule and Labor Analysis
    Energy Savings Analysis/Payback
Analysis 3: BAS Systems
  BAS System Application
    Bathroom Nightlight motion Sensor
    Hallway Motion Sensor
    Motion Sensor PTAC
Conclusion
  Final Schedule and Budget
  Final Decisions (What and What Not to Proceed With)
  Q/A
  Hallway Motion Sensor
About
  RAB LOS2400H Smart Hallway Sensors
  The sensors have a max viewing range of 16’ x 80’
  Can control 2400W/sensor of lighting
Reasons/Application
  Hallway vacancy between 11PM-6AM
  Excessive emergency hallway lighting
  Apply to 2nd & 3rd floor hallways
Initial Cost
  Sensor Cost – $139/each, Total of $834
  Labor Cost – 30$/each, Total of $180
  Total Cost - $1,014
Design Layout
  3 Sensors/Floor
    Green - controls 4 lights
    Red - controls 7 lights
    Pink - controls 6 lights
    Blue - 6 continuous emergency lights
    Green & pink sensors are offset 46’ from center sensor
    Clg. Mounted – 8’-8” AFF

## Slide 19
Outline
Additional Information
Holiday Inn Express
Introduction
  Personal and Building Intro
Building Background
  Building Size, Location, and Type
  Current Budget and Schedule
  Areas for Improvement/Client Influence
Analysis 1: Solyndra Solar Panel Implementation
  Installation location
  Sizing the Panel Layout
  Schedule and Labor Analysis
  Cost Analysis
  Energy Savings Analysis/Payback
Analysis 2: SIP Panel Implementation
  SIP Application
  SIP vs. Stick Built
    Material Cost
    Schedule and Labor Analysis
    Energy Savings Analysis/Payback
Analysis 3: BAS Systems
  BAS System Application
    Bathroom Nightlight motion Sensor
    Hallway Motion Sensor
    Motion Sensor PTAC
Conclusion
  Final Schedule and Budget
  Final Decisions (What and What Not to Proceed With)
  Q/A
  Hallway Motion Sensor
Energy Efficiency Analysis: Electrical Breadth
  Hallway lighting – 23 (100W) Incandescent
  Daily Use Reduction –5Hrs/day/floor
  # of Lights on Sensors – 17 Lights
  Energy Consumption
    Before – 40,296 kWh/year
    After – 32,850 kWh/uear
  Annual Energy Savings – 7,446 kWh/year
  Annual Cost Savings - $968/year
Payback
  Payback Period - 1year

## Slide 20
Outline
Additional Information
Holiday Inn Express
Introduction
  Personal and Building Intro
Building Background
  Building Size, Location, and Type
  Current Budget and Schedule
  Areas for Improvement/Client Influence
Analysis 1: Solyndra Solar Panel Implementation
  Installation location
  Sizing the Panel Layout
  Schedule and Labor Analysis
  Cost Analysis
  Energy Savings Analysis/Payback
Analysis 2: SIP Panel Implementation
  SIP Application
  SIP vs. Stick Built
    Material Cost
    Schedule and Labor Analysis
    Energy Savings Analysis/Payback
Analysis 3: BAS Systems
  BAS System Application
    Bathroom Nightlight motion Sensor
    Hallway Motion Sensor
    Motion Sensor PTAC
Conclusion
  Final Schedule and Budget
  Final Decisions (What and What Not to Proceed With)
  Q/A
  Motion Sensor PTAC
About
  Current System – 9000 BTU Amana PTAC unit
  New System - 9000 BTU DigiSmart Amana PTAC unit w/ the DigiSmart Motion Sensor
  Typical savings – 35% on Heating & Cooling
Reasons
  Reduce Heating & Cooling Loads
Initial Cost
  PTAC Upgrade Cost – $169/each, Total of $8,291
  Labor Cost – Negligible
Energy Efficiency Analysis: Mechanical Breadth
  Original PTAC
    Energy Usage – 4,400 kWh/year/unit
    Energy Usage – 215,600 kWh/year
    Energy Cost – $28,028/year
  New PTAC
    Energy Usage– 3,000 kWh/year/unit
    Energy Usage – 147,000 kWh/year
    Energy Cost – $19,110/year
  Annual Energy Savings – 16,993 kWh/year
  Annual Cost Savings - $8,918/year
Payback
  Payback Period - 1year

## Slide 21
Outline
Additional Information
Holiday Inn Express
Introduction
  Personal and Building Intro
Building Background
  Building Size, Location, and Type
  Current Budget and Schedule
  Areas for Improvement/Client Influence
Analysis 1: Solyndra Solar Panel Implementation
  Installation location
  Sizing the Panel Layout
  Schedule and Labor Analysis
  Cost Analysis
  Energy Savings Analysis/Payback
Analysis 2: SIP Panel Implementation
  SIP Application
  SIP vs. Stick Built
    Material Cost
    Schedule and Labor Analysis
    Energy Savings Analysis/Payback
Analysis 3: BAS Systems and Wireless Controls
  BAS System Application
    Bathroom Nightlight motion Sensor
    Hallway Motion Sensor
    Motion Sensor PTAC
Conclusion
  Final Schedule and Budget
  Final Decisions (What and What Not to Proceed With)
  Q/A
Conclusion:
Final Budget/Schedule Analysis

## Slide 22
Outline
Additional Information
Holiday Inn Express
Introduction
  Personal and Building Intro
Building Background
  Building Size, Location, and Type
  Current Budget and Schedule
  Areas for Improvement/Client Influence
Analysis 1: Solyndra Solar Panel Implementation
  Installation location
  Sizing the Panel Layout
  Schedule and Labor Analysis
  Cost Analysis
  Energy Savings Analysis/Payback
Analysis 2: SIP Panel Implementation
  SIP Application
  SIP vs. Stick Built
    Material Cost
    Schedule and Labor Analysis
    Energy Savings Analysis/Payback
Analysis 3: BAS Systems
  BAS System Application
    Bathroom Nightlight motion Sensor
    Hallway Motion Sensor
    Motion Sensor PTAC
Conclusion
  Final Schedule and Budget
  Final Decisions (What and What Not to Proceed With)
  Q/A
Final Schedule
Original Finish Date – April 16,2010
New Finish Date – April 7, 2010
Solar Panels – 6.25 day Installation period, doesn’t affect overall finish date
SIP Panel – 3 day Reduction/floor, 9 day overall schedule reduction
BAS Systems – Negligible

## Slide 23
Outline
Additional Information
Holiday Inn Express
Introduction
  Personal and Building Intro
Building Background
  Building Size, Location, and Type
  Current Budget and Schedule
  Areas for Improvement/Client Influence
Analysis 1: Solyndra Solar Panel Implementation
  Installation location
  Sizing the Panel Layout
  Schedule and Labor Analysis
  Cost Analysis
  Energy Savings Analysis/Payback
Analysis 2: SIP Panel Implementation
  SIP Application
  SIP vs. Stick Built
    Material Cost
    Schedule and Labor Analysis
    Energy Savings Analysis/Payback
Analysis 3: BAS Systems
  BAS System Application
    Bathroom Nightlight motion Sensor
    Hallway Motion Sensor
    Motion Sensor PTAC
Conclusion
  Final Schedule and Budget
  Final Decisions (What and What Not to Proceed With)
  Q/A
Final Budget
Two final budget analysis were made, with/without solar panels
The annual savings is 37% less w/o solar panels
The initial cost is 94% cheaper w/o solar panels
Final Payback
Payback Period (w/ Solar Panels) – 10 years
Payback Period (w/o Solar Panels) – 1 year

## Slide 24
Outline
Additional Information
Holiday Inn Express
Introduction
  Personal and Building Intro
Building Background
  Building Size, Location, and Type
  Current Budget and Schedule
  Areas for Improvement/Client Influence
Analysis 1: Solyndra Solar Panel Implementation
  Installation location
  Sizing the Panel Layout
  Schedule and Labor Analysis
  Cost Analysis
  Energy Savings Analysis/Payback
Analysis 2: SIP Panel Implementation
  SIP Application
  SIP vs. Stick Built
    Material Cost
    Schedule and Labor Analysis
    Energy Savings Analysis/Payback
Analysis 3: BAS Systems
  BAS System Application
    Bathroom Nightlight motion Sensor
    Hallway Motion Sensor
    Motion Sensor PTAC
Conclusion
  Final Schedule and Budget
  Final Decisions (What and What Not to Proceed With)
  Q/A
Final Decisions
Solyndra Solar Panels
  Produces about 22% of Entire Building Energy
  Long Payback Period about 26 years
  Almost 10% Increase in Initial Budget
  More Beneficial for Owner to Wait (Carbon Tax, Solar Panel ↓ Cost, & ↑ Efficiency)
SIP Panels
  Stronger, Quieter, & Straighter
  Easy Installation
  Faster installation, 9 day Schedule Reduction
  55% More energy Efficient Than Stick Built
  Quick Payback, 1 Year
  Plausible for Owner
BAS Systems
  Reasonable Reduction in Vacant Energy Consumption
  Cheap Initial Cost
  About $12,000/year Annual Savings
  Easy Installation
  Quick Payback, 1 year
  Plausible for Owner

## Slide 25
Outline
Additional Information
Holiday Inn Express
Introduction
  Personal and Building Intro
Building Background
  Building Size, Location, and Type
  Current Budget and Schedule
  Areas for Improvement/Client Influence
Analysis 1: Solyndra Solar Panel Implementation
  Installation location
  Sizing the Panel Layout
  Schedule and Labor Analysis
  Cost Analysis
  Energy Savings Analysis/Payback
Analysis 2: SIP Panel Implementation
  SIP Application
  SIP vs. Stick Built
    Material Cost
    Schedule and Labor Analysis
    Energy Savings Analysis/Payback
Analysis 3: BAS Systems and Wireless Controls
  BAS System Application
    Bathroom Nightlight motion Sensor
    Hallway Motion Sensor
    Motion Sensor PTAC
Conclusion
  Final Schedule and Budget
  Final Decisions (What and What Not to Proceed With)
  Q/A
Question?
Thesis by: Josh Raphael
Architectural Engineering
Construction Management