## Slide 1
Reston Station Phase 1 Garage
Reston, Virginia
Penn State Architectural Engineering Senior Thesis
Jon Fisher Construction Option Advisor: Dr. Robert Leicht

## Slide 2
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Location
Reston, Virginia
Size
1.3 Million Square Feet
7 Underground Levels
5 Additional Buildings in Future Phases
Function
2300 Public Parking Spaces
Silver Line Metrorail
Schedule
April 2011 – July 2013
27 Months
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Project Overview

## Slide 3
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Project Overview
Cost
$92 Million
Delivery Method
Guaranteed Maximum Price
CM at Risk – Davis Construction
Owner
Fairfax County and Comstock Partners

## Slide 4
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
To understand the public-private partnership used on the project and determine the implications partnerships have on construction as a whole
Goal of Analysis #1
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Public-Private Partnerships

## Slide 5
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Public-Private Partnerships
Public-Private Partnership: “A government service or private business venture funded and operated through a partnership of government and one or more private sector companies.”
When government and the private sector work together
PPP’s In Construction
Simple Example: Toll Roads
Sharing risk and reward

## Slide 6
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Public-Private Partnerships
PPP At Reston Station
County given development funds from VDOT
Fairfax approached by Comstock for future building rights
Virginia Public-Private Partnership Act
99-year lease
Proffer agreement contains terms
Price tag divided by parking ratio
Advantages of Public Private Partnerships | 
Public Owner | Private Owner
● Reduced Cost | ● Operation in New Markets
● Delivery Method Freedom | ● New Revenue Opportunity
● Possible Increase in Revenue | ● Government Relationship
● Increased Efficiency | 

## Slide 7
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Public-Private Partnerships
Challenges
Decision Making
Limited conflicts in separated areas
Decision making paralysis on shared spaces
Decision making flow chart
Usage of Garage Area
Reston Station Decision Making
Generalized Decision Making

## Slide 8
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Public-Private Partnerships
Conclusion
PPP’s are great in theory but still untested with general building construction
Best to proceed in a PPP with critical awareness
Large variance between different levels and states
Long Beach Courthouse
Not a transportation example
Long Beach Judicial Partners LLC
  Clack Design-Build
  AECOM
  Johnson Controls
$490 Million Design-Build-Operate-Maintain
Performance based service fee
Funding source complications

## Slide 9
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Equipment Staging and Bonded Warehouses
To investigate an alternative option for the storage of construction materials utilizing off-site bonded warehouses
Goal of Analysis #2

## Slide 10
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Aug. 2, 2012
Escalator frames, ventilation fans, and stone façade
Escalators originally to be stored on finished slab
Design delay caused complications
140 fans and 2 escalators stored on slabs for extended period of time
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Equipment Staging and Bonded Warehouses
Aug. 2, 2012
Intended Storage of Escalators
Current Situation

## Slide 11
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Aug. 2, 2012
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Equipment Staging and Bonded Warehouses
Current Situation
Actual Storage of Escalators
Aug. 2, 2012
Dec. 3, 2012
Sept. 17, 2012
Nov. 19, 2012
Escalator frames, ventilation fans, and stone façade
Escalators originally to be stored on finished slab
Design delay caused complications
140 fans and 2 escalators stored on slabs for extended period of time

## Slide 12
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Equipment Staging and Bonded Warehouses
The Traditional Method
How Bonded Warehouses Could Help
Limited Bonded Warehouse Use
Typical Method of Equipment Delivery
Delivered directly to the site
Stored on site
Good for projects site freedom
Using Bonded Warehouses for Short Term
Logistics services company
Month-to-month storage
No long term contract
Sites with some restrictions

## Slide 13
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Equipment Staging and Bonded Warehouses
Difference from Subcontractor “Yard”
Cash Flow
“§9.3.2 Unless otherwise provided in the contract document, payments shall be made on account of materials and equipment delivered and suitably store at the site for subsequent incorporation in the work. If approved in advance by the owner, payment may similarly be made for materials and equipment suitably stored off the site at a location agreed upon in writing.”
-General Conditions of the Contract for Construction
(AIA A201)

## Slide 14
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Equipment Staging and Bonded Warehouses
Total Cost of Off Site Storage of Limited Items | 
Storage Cost | $ 20,600.00
Transportation Cost | $ 7,600.00
Bonding (1% Value of Goods) | $ 8,036.00
TOTAL | $ 36,236.00
Costs
Added stage of transportation
Month-to-Month storage
Insurance of materials
Limited Bonded Warehouse Use
Data from England Logistics & Innerspace

## Slide 15
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Equipment Staging and Bonded Warehouses
Bonded Warehouses as HUBs
Using Bonded Warehouses as a HUB
All deliveries to bonded warehouse
Could be used for multiple projects
Long-term lease
Pentagon Renovation Example

## Slide 16
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Equipment Staging and Bonded Warehouses
Costs
Added staff and equipment
36 month lease
Bonding on warehouse
Total Cost of Off Long Term Off Site Storage | 
Storage Cost | $ 896,019.48
Transportation Cost | $ 162,020.00
Staff | $ 660,000.00
TOTAL | $ 1,718,039.48
Bonded Warehouses as HUBs
Compared to $36,000 for short term use

## Slide 17
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Equipment Staging and Bonded Warehouses
Extensive Bonded Warehouse Use
Comparing Costs
Limited Bonded Warehouse Use
Per Month Comparison of Bonded Warehouse Use |  |  | 
Scenario | Time Span (mo.) | Cost | Cost/Mo
Warehouse Leasing | 36 | $ 1,718,039.48 | $ 47,723.32
Short Term Warehouse Space Usage | 6 | $ 36,236.00 | $ 6,039.33
Short term time span from construction schedule
Warehouse leasing option = 1.5% project budget
Minimized impact if used by several projects

## Slide 18
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Equipment Staging and Bonded Warehouses
Advantages
Reduced Risk
Consolidated Delivery
Early Subcontractor cash flow
Eliminates delays in Production
Value of Goods Being Stored and Transported |  |  |  |  | 
Item | Cost | Quantity | Unit |  | Total
Granite Stone Façade | $ 18.00 | 10200 | SF |  | $ 183,600.00
Garage Supply Air Fans | $ 3,140.00 | 50 | Ea |  | $ 157,000.00
Garage Exhaust Air Fans | $ 2,700.00 | 90 | Ea |  | $ 243,000.00
Escalator Trusses | $ 110,000.00 | 2 | Ea |  | $ 220,000.00
 |  |  |  | TOTAL | $ 803,600.00
$800,000 OF MATERIALS
Comparing Costs
Per Month Comparison of Bonded Warehouse Use |  |  | 
Scenario | Time Span (mo.) | Cost | Cost/Mo
Warehouse Leasing | 36 | $ 1,718,039.48 | $ 47,723.32
Short Term Warehouse Space Usage | 6 | $ 36,236.00 | $ 6,039.33
Short term time span from construction schedule
Warehouse leasing option = 1.5% project budget
Minimized impact if used by several projects

## Slide 19
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Equipment Staging and Bonded Warehouses
Advantages
Reduced Risk
Consolidated Delivery
Early Subcontractor cash flow
Eliminates delays in Production
Conclusion
Value of Goods Being Stored and Transported |  |  |  |  | 
Item | Cost | Quantity | Unit |  | Total
Granite Stone Façade | $ 18.00 | 10200 | SF |  | $ 183,600.00
Garage Supply Air Fans | $ 3,140.00 | 50 | Ea |  | $ 157,000.00
Garage Exhaust Air Fans | $ 2,700.00 | 90 | Ea |  | $ 243,000.00
Escalator Trusses | $ 110,000.00 | 2 | Ea |  | $ 220,000.00
 |  |  |  | TOTAL | $ 803,600.00
Recommendation: Implementation of warehouse as month-to-month storage for escalators, stone, and fans will mitigate risk and help site production at Reston.
Leasing warehouse as HUB space is cost prohibitive
Better suited for when required or serving multiple projects
$800,000 OF MATERIALS

## Slide 20
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Short Interval Production Scheduling
To utilize Short Interval Production Scheduling (SIPS) and matrix scheduling to accelerate and illustrate garage finish sequence
Goal of Analysis #3

## Slide 21
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Short Interval Production Scheduling
Original Finish Sequence
Each level divided by East and West
Original zones = 99,000 SF
Concrete sequence determined finish sequence
Reshore restrictions defined finish schedule
Original Finish Sequence

## Slide 22
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Short Interval Production Scheduling
Adjusted Sequence
Reshore restrictions defined finish schedule
Simplified sequence
Includes co-location of certain trades
Original Finish Sequence

## Slide 23
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Short Interval Production Scheduling
Adjusted Sequence
Simplified sequence
Includes co-location of certain trades
Takes most advantage of concrete sequence
Each Subzone = 8,250 Square Feet
Redefined Zones

## Slide 24
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Short Interval Production Scheduling
Redefined Zones
Takes most advantage of concrete sequence
Each Subzone = 8,250 Square Feet
Productivity Rates and Crew Adjustment
Garage Activity Productivity Rates |  |  |  |  | 
Schedule Indicator | Activity | Baseline Duration (Days) | Productivity (SF/Man/Day) | SIPS Subzone Area | # of Workers (SIPS)
A | Layout | 5 | 9900 | 8250 SF | 2
B | Curbs | 20 | 413 |  | 20
C | CMU Walls | 20 | 620 |  | 14
D | Doors & Hardware | 5 | 9900 |  | 2
 | Railings | 10 | 3300 |  | 3
E | Mech Rough In | 10 | 2475 |  | 4
 | Electrical Rough In | 10 | 1650 |  | 6
F | Plumbing Rough In | 20 | 495 |  | 17
G | Sprikler Rough In | 30 | 825 |  | 10
H | Remove Reshores | 3 | 8250 |  | 4
 | Paint Walls and Ceilings | 15 | 660 |  | 13
I | Traffic Coating | 24 | 1094 |  | 8
J | Light Fixtures | 20 | 825 |  | 10
K | Pavement Markings | 5 | 3300 |  | 6
Crew sizes adjusted to achieve 1 subzone/day
Some crew sizes were “irreducible”

## Slide 25
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Short Interval Production Scheduling
Productivity Rates and Crew Adjustment
168 Zones
Duration: 178 Days
“Perfect” Matrix
Crew sizes adjusted to achieve 1 subzone/day
Some crew sizes were “irreducible”
Garage Activity Productivity Rates |  |  |  |  | 
Schedule Indicator | Activity | Baseline Duration (Days) | Productivity (SF/Man/Day) | SIPS Subzone Area | # of Workers (SIPS)
A | Layout | 5 | 9900 | 8250 SF | 2
B | Curbs | 20 | 413 |  | 20
C | CMU Walls | 20 | 620 |  | 14
D | Doors & Hardware | 5 | 9900 |  | 2
 | Railings | 10 | 3300 |  | 3
E | Mech Rough In | 10 | 2475 |  | 4
 | Electrical Rough In | 10 | 1650 |  | 6
F | Plumbing Rough In | 20 | 495 |  | 17
G | Sprikler Rough In | 30 | 825 |  | 10
H | Remove Reshores | 3 | 8250 |  | 4
 | Paint Walls and Ceilings | 15 | 660 |  | 13
I | Traffic Coating | 24 | 1094 |  | 8
J | Light Fixtures | 20 | 825 |  | 10
K | Pavement Markings | 5 | 3300 |  | 6

## Slide 26
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Short Interval Production Scheduling
168 Zones
Duration: 178 Days
“Perfect” Matrix
Concrete Impact
2 framed + 4 reshored levels required
Painting and traffic coating delayed by reshores
11 Days
18 Days

## Slide 27
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Short Interval Production Scheduling
Structural Breadth
Original 2+4 Requirement
Redesign of slab to achieve 2+2
ACI 318-11
  Deflections
  Punching Shear
ASCE 37
Slab Dead Load (10” slab) = 125 PSF
Formwork = 10 PSF
Reshores = 5 PSF
Construction Live Load = 75 PSF
Combined
Capacity
Combined
Loading
>

## Slide 28
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Short Interval Production Scheduling
Structural Breadth
Original 2+4 Requirement
Redesign of slab to achieve 2+2
ACI 318-11
  Deflections
  Punching Shear
10” Slab with 5.5” Drop Panel Meets Requirements
5.5” drop panel allows for dimensional 2x6 form work
Saves time and labor

## Slide 29
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Short Interval Production Scheduling
Conclusion
SIPS Schedule Results |  |  |  |  |  | 
Finish Scenario | Start | Finish | Duration | Saved Duration | Days Complete Before BL Finish | Cost Increase
Baseline Schedule | 14-Feb-12 | 5-Feb-13 | 256 | - | - | $ -
"Perfect" Matrix | 14-Feb-12 | 18-Oct-12 | 178 | 78 | 78 Days | $ -
SIPS w/ 4+2 Shoring | 14-Feb-12 | 13-Nov-12 | 196 | 60 | 60 Days | $ -
SIPS w/ 2+2 Shoring | 2-Jan-12 | 10-Oct-12 | 203 | 53 | 85 Days | $ 200,000.00
Slab redesign with SIPS = $2,350/saved day
Liquidated Damages = approx. $10,000/day after Substantial Completion
Financially beneficial to owner
SIPS REQUIRES COORDINATION
Concrete progress had big impact on finishes
Early completion means lower general conditions
Crew size adjustments impact cost curve

## Slide 30
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Mechanical Chases and Design Coordination
To assess the impacts of adding mechanical pipe chases to the garage on design coordination and project cost.
Goal of Analysis #4
Architect – Davis, Carter, Scott Structural – Luis Fernandez
MEP – Jordan & Skala
Architect – Murphy/Jahn Structural – Thorton Thomasetti
MEP – GHT Chartered
Architect - Hickok Cole Structural - Structura
MEP - Hoffman Borowski
3 Separate Design Teams
Penetration Coordination difficult with varying stages of design
Design Coordination

## Slide 31
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Mechanical Chases and Design Coordination
Mechanical Breadth
Reston 100 Year Storm = 3”/hour
Flat Roof Slope = ¼” / Ft.
Assumes Consolidation to 1 Pipe
Roof Drains

## Slide 32
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Mechanical Chases and Design Coordination
Mechanical Breadth
Reston 100 Year Storm = 3”/hour
Flat Roof Slope = ¼” / Ft.
Assumes Consolidation to 1 Pipe
Roof Drains
Sanitary Drains
Slope of Drain Pipe = 1/8” / ft
Assumes Consolidation to 1 Pipe
Exception: 2 Pipes in Apartment due to excessive drop

## Slide 33
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Mechanical Chases and Design Coordination
Chase Design
8” CMU Partition Walls
Outward Swinging Doors
Steel Grating
6’ x 8’

## Slide 34
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Mechanical Chases and Design Coordination
The Bad
10 Public and 12 Private Parking Spaces lost
Location For Chases
The Good
Perimeter locations simplify connection to exterior
Could coincide with stairwell or elevator shaft location

## Slide 35
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Mechanical Chases and Design Coordination
Cost of Chases |  |  |  |  |  |  |  | 
Item | Unit | Quantity | Labor (Unit Cost) | Material (Unit Cost) | Equipment | Total Labor | Total Material | Total Equipment
Steel Grating | SF | 1008 | $ 14.85 | $ 4.50 | $ 2.49 | $ 14,968.80 | $ 4,536.00 | $ 2,509.92
Steel Angles | Ea | 56 | $ 56.00 | $ 29.50 | $ - | $ 3,136.00 | $ 1,652.00 | $ -
HM Doors | Ea | 28 | $ 560.00 | $ 39.00 | $ - | $ 15,680.00 | $ 1,092.00 | $ -
HM Frames | Ea | 28 | $ 199.00 | $ 44.00 | $ - | $ 5,572.00 | $ 1,232.00 | $ -
CMU Block | SF | 6688 | $ 2.40 | $ 4.34 | $ - | $ 16,051.20 | $ 29,025.92 | $ -
Concrete Expansion Anchors | Ea | 280 | $ 2.38 | $ 3.07 | $ - | $ 666.40 | $ 859.60 | $ -
 |  |  |  |  | Total | $ 56,074.40 | $ 38,397.52 | $ 2,509.92
 |  |  |  |  | Tax |  | $ 2,303.85 | 
 |  |  |  |  | Total | $ 99,285.69 |  | 
12" Core Drills |  |  |  |  | 
unit | Quantity | Material | Labor | Equipment | Total Cost
Ea | 132 | $ 2.75 | $ 71.02 | $ 12.16 | $ 11,001.54
Chase Cost = $99,000
The Ugly
Core Drill Cost = $11,000
Recommendation
Cost prohibitive
Further investigation needed for achieving better design coordination efforts

## Slide 36
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Conclusions
Final Conclusions
Public-Private Partnerships: Good research, caution needed when working with a PPP
Bonded Warehouses: Shows benefit for month-to-month short term needs but leasing is cost prohibitive for Reston
SIPS Scheduling: Biggest impact on schedule comes from design delays. SIPS could have helped in hindsight.
Mechanical Chases: Cost prohibitive

## Slide 37
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Acknowledgements
Penn State Architectural Engineering Faculty
Friends, Family and God
Industry Members

## Slide 38
Questions?

## Slide 39
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Appendix (Bonded Warehouses)

## Slide 40
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Appendix (Bonded Warehouses)

## Slide 41
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
Appendix
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Appendix (SIPS)
Level | Subzone | 14-Feb | 15-Feb | 16-Feb | 17-Feb | 20-Feb | 21-Feb | 22-Feb | 23-Feb | 24-Feb | 27-Feb | 28-Feb | 29-Feb | 1-Mar | 2-Mar | 5-Mar | 6-Mar | 7-Mar | 8-Mar | 9-Mar | 12-Mar | 13-Mar | 14-Mar | 15-Mar | 16-Mar | 19-Mar | 20-Mar | 21-Mar | 22-Mar | 23-Mar | 26-Mar | 27-Mar | 28-Mar | 29-Mar | 30-Mar
G7 | 1A | A | B | C | D | E | F | G | H | Crew 1 |  |  |  | J | K |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
G7 | 1B |  | A | B | C | D | E | F | G | H | Crew 2 |  |  |  | J | K |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
G7 | 1C |  |  | A | B | C | D | E | F | G | H | Crew 3 |  |  |  | J | K |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
G7 | 1D |  |  |  | A | B | C | D | E | F | G | H | Crew 4 |  |  |  | J | K |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
G7 | 1E |  |  |  |  | A | B | C | D | E | F | G | H | Crew 1 |  |  |  | J | K |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
G7 | 1F |  |  |  |  |  | A | B | C | D | E | F | G | H | I | I | I | I | J | K |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
G7 | 2A |  |  |  |  |  |  | A | B | C | D | E | F | G | H | I | I | I | I | J | K |  |  |  |  |  |  |  |  |  |  |  |  |  | 
G7 | 2B |  |  |  |  |  |  |  | A | B | C | D | E | F | G | H | I | I | I | I | J | K |  |  |  |  |  |  |  |  |  |  |  |  | 
G7 | 2C |  |  |  |  |  |  |  |  | A | B | C | D | E | F | G | H | I | I | I | I | J | K |  |  |  |  |  |  |  |  |  |  |  | 
G7 | 2D |  |  |  |  |  |  |  |  |  | A | B | C | D | E | F | G | H | I | I | I | I | J | K |  |  |  |  |  |  |  |  |  |  | 
G7 | 2E |  |  |  |  |  |  |  |  |  |  | A | B | C | D | E | F | G | H | I | I | I | I | J | K |  |  |  |  |  |  |  |  |  | 
G7 | 2F |  |  |  |  |  |  |  |  |  |  |  | A | B | C | D | E | F | G | H | I | I | I | I | J | K |  |  |  |  |  |  |  |  | 
G6 | 1A |  |  |  |  |  |  |  |  |  |  |  |  | A | B | C | D | E | F | G | H | I | I | I | I | J | K |  |  |  |  |  |  |  | 
G6 | 1B |  |  |  |  |  |  |  |  |  |  |  |  |  | A | B | C | D | E | F | G | H | I | I | I | I | J | K |  |  |  |  |  |  | 
G6 | 1C |  |  |  |  |  |  |  |  |  |  |  |  |  |  | A | B | C | D | E | F | G | H | I | I | I | I | J | K |  |  |  |  |  | 
G6 | 1D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | A | B | C | D | E | F | G | H | I | I | I | I | J | K |  |  |  |  | 
G6 | 1E |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | A | B | C | D | E | F | G | H | I | I | I | I | J | K |  |  |  | 
G6 | 1F |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | A | B | C | D | E | F | G | H | I | I | I | I | J | K |  |  | 
G6 | 2A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | A | B | C | D | E | F | G | H | I | I | I | I | J | K |  | 
G6 | 2B |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | A | B | C | D | E | F | G | H | I | I | I | I | J | K | 
G6 | 2C |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | A | B | C | D | E | F | G | H | I | I | I | I | J | K
G6 | 2D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | A | B | C | D | E | F | G | H | I | I | I | I | J
G6 | 2E |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | A | B | C | D | E | F | G | H | I | I | I | I
G6 | 2F |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | A | B | C | D | E | F | G | H | I | I | I

## Slide 42
Project Overview
Analysis #1: Public-Private Partnerships
Analysis #2: Bonded Warehouses
Analysis #3: SIPS Scheduling
Analysis #4: Mechanical Chases
Summary and Conclusions
Acknowledgements
Appendix
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Appendix (SIPS)

## Slide 43
OUTLINE
Reston Station Phase 1 Garage
Reston, Virginia
Jon Fisher | Construction Management
Appendix (Mechanical Chases)