## Slide 1: Geisinger Gray’s Woods AMbulatory Care Campus - Phase II
**Rendering of front view supplied by Alexander Building Construction with Owner Permission
Penn State AE
Senior Capstone Project
George M. Andonie
Construction Option
Advisor: Rob Leicht
April 16th, 2014

## Slide 2
`
George M. Andonie │ Construction Option
Geisinger Grays Woods
Ambulatory Care Campus – Phase II
April 16, 2014
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
IV. Analysis #2: Façade Prefabrication
V. Analysis #3: Revaluating Comp. Slab
VI. Final Recommendations
VII. Acknowledgements
Introduction
Analysis 3 │Re-valuating Composite Slab
Project Overview
Analysis 1 │ Virtual Mockup Implementation
Analysis 2 │ Brick Façade Prefabrication

## Slide 3
George M. Andonie │ Construction Option
Geisinger Grays Woods
Ambulatory Care Campus – Phase II
April 16, 2014
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
  Project Background
III. Analysis #1: Virtual Mockups
IV. Analysis #2: Façade Prefabrication
V. Analysis #3: Revaluating Comp. Slab
VI. Final Recommendations
VII. Acknowledgements
Project Background
General Building Information | 
Building Name | Grays Woods Ambulatory Care Campus
Location | Port Matilda, PA
Function | Outpatient Surgery Center
Size | 77,560 GSF
Height | 2 Stories (48' Total Height)
Cost | $26.3 Million GMP
Construction | July '12 - February '14
Delivery | Design-Bid-Build
LEED | LEED Certified
Building Functions:
  Outpatient Surgery Center
  Houses 70 Exam Rooms, 4 Operating Rooms, 4 Endoscopy Suites & 2 Main Therapy Rooms
  Phase 1: 2007-2008
  Phase 2 :2012-2014
Phase II
Phase I
Project Team:
Structural: EwingCole
MEP: EwingCole
Civil:
Sweetland Engineering
GMP
Cost + Fee
Lump Sum
Architect: EwingCole
Other Owner Contracts:
Commissioning Agent: Flood & Sterling, Inc.
HVAC Controls: Johnson Controls, Inc.
Geotechnical: CMT Laboratories, Inc.
Security: Hillman Technologies
Legend:
Cost + Fee Contract
Guaranteed Maximum Price (GMP)
Lump Sum
CM @ Risk: Alexander Building Construction
Subcontractors:
Sitework, HVAC, Plumbing, Electrical, Concrete, Masonry, Steel, Roofing, Flooring, Windows, Doors, Drywall Fire Protection…
Other Contracts
Communication
Owner: Geisinger Health Systems

## Slide 4
George M. Andonie │ Construction Option
Geisinger Grays Woods
Ambulatory Care Campus – Phase II
April 16, 2014
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  Problem Identification
  Virtual Mockup Development
  Virtual Mockup Application
  Implementation & Recommendation
IV. Analysis #2: Façade Prefabrication
V. Analysis #3: Revaluating Comp. Slab
VI. Final Recommendations
VII. Acknowledgements
Analysis #1
Implementing Virtual Mockups on
Operating & Endoscopy Rooms

## Slide 5
In-Place Mockup Process
George M. Andonie │ Construction Option
Geisinger Grays Woods
Ambulatory Care Campus – Phase II
April 16, 2014
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  Problem Identification
  Virtual Mockup Development
  Virtual Mockup Application
  Implementation & Recommendation
IV. Analysis #2: Façade Prefabrication
V. Analysis #3: Revaluating Comp. Slab
VI. Final Recommendations
VII. Acknowledgements
Proposed Solution:
  Virtual Mockups for Design Reviews
Research Goal:
  Develop Virtual Mockup for Operating & Endoscopy Rooms
  Capture Efforts, Criteria & Workflow
  Schedule Analysis Implementation
‘In-Place Mockup’
Construction & Implementation
Current Schedule:
Problem Identification:
  8-week Mock-Up Process
  Low Level of Detail (LOD)
  Waste Generation
  Costly & Time Consuming Process
  Obstruction to Schedule
  Risk of Delays
8 weeks

## Slide 6
Virtual Mockup Development
George M. Andonie │ Construction Option
Geisinger Grays Woods
Ambulatory Care Campus – Phase II
April 16, 2014
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  Problem Identification
  Virtual Mockup Development
  Virtual Mockup Application
  Implementation & Recommendation
IV. Analysis #2: Façade Prefabrication
V. Analysis #3: Revaluating Comp. Slab
VI. Final Recommendations
VII. Acknowledgements
Development Process:
  Autodesk Revit:
    Model Building Space
    Model MEP Systems
    Model Equipment & Casework
    Populate & Arrange
  3ds Max:
    Material Placement
    Scale Adjustment
  Unity Game Engine:
    Scripting Model Interaction

## Slide 7
George M. Andonie │ Construction Option
Geisinger Grays Woods
Ambulatory Care Campus – Phase II
April 16, 2014
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  Problem Identification
  Virtual Mockup Development
  Virtual Mockup Application
  Implementation & Recommendation
IV. Analysis #2: Façade Prefabrication
V. Analysis #3: Revaluating Comp. Slab
VI. Final Recommendations
VII. Acknowledgements
Virtual Model Application
Model Application:
  Model Walkthrough:
    First Person Controller (FPC)
    Computer/Iconn Lab
  Design Review:
    Functionality & Room Layout
      Check Clearances
      Equipment/Casework Location
      Mounting heights
      General Appearance
  Provide Feedback:
    Online Survey Completion
    Welcome Menu:
    Feedback Survey
    Operating Room Design Review:
    Endoscopy Room Design Review:

## Slide 8
Virtual Mockup Implementation
George M. Andonie │ Construction Option
Geisinger Grays Woods
Ambulatory Care Campus – Phase II
April 16, 2014
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  Problem Identification
  Virtual Mockup Development
  Virtual Mockup Application
  Implementation & Recommendation
IV. Analysis #2: Façade Prefabrication
V. Analysis #3: Revaluating Comp. Slab
VI. Final Recommendations
VII. Acknowledgements
Time Requirements:
Cost Implications:
Recommendation:
  Implement Virtual Mockups for Operating & Endoscopy Rooms
Potential Value Added:
  Streamlining the design and construction process
  Subcontractor & end user feedback
  Reduce project waste (time & cost)
  Strong visualization/communication tool
  Ensuring the end product meets owner’s needs
  No disturbance to project schedule
Time Requirement |  | 
Step Description |  | Duration (Hrs.)
1. | Obtained Existing Revit Model | -
2. | Combine Architectural & MEP Revit Models | 2
3. | Strip Out Revit Model | 0.5
4. | Model all Owner Furnished Equipment | 8
5. | Export Model to 3Ds Max | 1
6. | Export Model to Unity | 1
7. | Develop Scripting and Textures in Unity | 8
Total |  | 20.5 Hrs
Cost Summary |  |  | 
Item Description | Mhrs | Hourly Wage | Total Cost
Develop & Modify Model | 23 | $35/hr | $805
Design-Review Meetings (GC) | 50 | $65/hr | $3,250
Total | $4,055 |  | 
*Costs taken from RS Means 2013 |  |  | 
Schedule Implications:
  Design Phase: Implement Early
    Design-Review meetings between project participants & end users
    Changes can be costly to implement later in the project lifecycle
  Construction Phase: Visual communication of built space
Impact of Changes
Cost of Changes
Planning
Implementation
    Source: Maing, M. (2012) Physical or Virtual

## Slide 9
George M. Andonie │ Construction Option
Geisinger Grays Woods
Ambulatory Care Campus – Phase II
April 16, 2014
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Panel Design
  Mechanical Breadth Analysis
  Panel Implementation
  Conclusion & Recommendations
V. Analysis #3: Revaluating Comp. Slab
VI. Final Recommendations
VII. Acknowledgements
Analysis #2
Brick Façade Prefabrication

## Slide 10
Façade Comparison
George M. Andonie │ Construction Option
Geisinger Grays Woods
Ambulatory Care Campus – Phase II
April 16, 2014
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Research Goals:
  Identify alternative panel
  Reduce schedule & cost
  Reduce site congestion & trade coordination on site
Original Façade:
  4” Brick on Metal Stud
  $674,000
  178 Day Construction Duration
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Panel Design
  Mechanical Breadth Analysis
  Panel Implementation
  Conclusion & Recommendations
V. Analysis #3: Revaluating Comp. Slab
VI. Final Recommendations
VII. Acknowledgements
Opportunity Identification:
  Time & Labor Intensive
  Site Congestion
  Weather Delays
  Critical Path
Proposed Facade:
  9” Insulated Precast Panel
  Embedded Thin Brick
  Cost = $25/SF
  Erection = 16 panels/ day
House of Quality:
Customer's Needs |  | Design Requirements
Façade Aesthetics |  | Face Material Type
Low Cost |  | Assembly Location
Short Schedule |  | Erection Time
Good Thermal Performance |  | Component Weight
Durability |  | Insulation Properties
Maintenance |  | Cost of Panel
    *Image Courtesy of www.veneerbricks.com
    *Image Courtesy of Nitterhouse Concrete

## Slide 11
Panel Design
George M. Andonie │ Construction Option
Geisinger Grays Woods
Ambulatory Care Campus – Phase II
April 16, 2014
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Panel Design
  Mechanical Breadth Analysis
  Panel Implementation
  Conclusion & Recommendations
V. Analysis #3: Revaluating Comp. Slab
VI. Final Recommendations
VII. Acknowledgements
Panel Design:
  Consistency & transportation
  Span Building Height (40’)
  Maximum width 12’
  Total 74 precast panels
    14 different panel widths
Panel Installation Durations |  |  | 
Façade Orientation | Panel Qty. | Calculated Duration | Adjusted Duration
East Façade | 19 | 1.27 Days | 2 Days
South Façade | 25 | 1.67 Days | 2 Days
West Façade | 22 | 1.47 Days | 2 Days
North Façade | 8 | 0.53 Days | 1 Day
Total | 74 | 4.93 Days | 7 Days
*Durations taken from Precast Panel Takeoff, and assume productivity of 16 Panels/Day. |  |  | 
    East Elevation:
    North Elevation:
    South Elevation:
    West Elevation:

## Slide 12
Mechanical Breadth
George M. Andonie │ Construction Option
Geisinger Grays Woods
Ambulatory Care Campus – Phase II
April 16, 2014
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Mechanical Analysis:
  Evaluate Thermal Performance
    Thermal Property Comparison
    Energy Performance
Breadth Conclusions:
  Improved Thermal Performance (By 20%)
    Heat Gain/Loss Reduction
    Reduced Heating/Cooling Costs
  No condensation in systems
  Potentially Downsize Mechanical System
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Panel Design
  Mechanical Breadth Analysis
  Panel Implementation
  Conclusion & Recommendations
V. Analysis #3: Revaluating Comp. Slab
VI. Final Recommendations
VII. Acknowledgements
  Annual Heating Fuel Consumption:
  Annual Cooling Energy Consumption:
-Value)*(Area)*(ΔT)
  Heat Transfer Rate:
Chart: BTU/hr
| Heat Loss (Winter) | Heat Gain (Summer)
Existing Brick | 48343.8785 | 20318.4417
Precast Wall | 38789.8463 | 16302.9789
Heat Loss & Heat Gain Calculations |  |  |  |  |  |  |  |  | 
Wall Assembly | R - Value | U-Value | Area (SF) | Heat Loss (Winter) |  |  | Heat Gain (Summer) |  | 
 |  |  |  | ΔT (°F) |  | BTU/Hr | ΔT (°F) |  | BTU/Hr
Existing Brick Assembly | 25.05 | 0.03992 | 17,551 | 69 |  | 48,344 | 29 |  | 20,318
Precast Wall Assembly | 31.22 | 0.03203 | 17,551 | 69 |  | 38,790 | 29 |  | 16,303
Difference | 6.17 | 0.00789 | - | 9,554 BTU/hr |  |  | 4,015 BTU/hr |  | 
*R-Values taken from Nitterhouse Manufacturer |  |  |  |  |  |  |  |  | 
Chart: Cost
| Annual Heating Cost | Annual Cooling Cost
Existing Brick | 1617 | 398
Precast Wall | 1297 | 319

## Slide 13
Panel Implementation
George M. Andonie │ Construction Option
Geisinger Grays Woods
Ambulatory Care Campus – Phase II
April 16, 2014
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Panel Design
  Mechanical Breadth Analysis
  Panel Implementation
  Conclusion & Recommendations
V. Analysis #3: Revaluating Comp. Slab
VI. Final Recommendations
VII. Acknowledgements
Site Layout:
Schedule Implications:
  Subcontractor & End User Feedback
  Eliminate coordination issues
  No disturbance to project Schedule
  Visualization of Built Space
  Shorten Brick Installation by 96 Days!
Schedule Savings = 3 weeks

## Slide 14
George M. Andonie │ Construction Option
Geisinger Grays Woods
Ambulatory Care Campus – Phase II
April 16, 2014
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Panel Design
  Mechanical Breadth Analysis
  Panel Implementation
  Conclusion & Recommendations
V. Analysis #3: Revaluating Comp. Slab
VI. Final Recommendations
VII. Acknowledgements
Panel Implementation
Cost Implications:
  Implement = Additional $10/SF
  Interior Components Same
    Vapor Barrier, Sheathing & Backup
  Cost Changes
    2” vs. 4” Insulation
    Caulking Panel Joints
  General Conditions Savings
    21 Days = $43,663
Final Conclusions:
  74 Architectural Precast Panels
  Improve Thermal Performance by 20%
  Schedule Reduction = 21 Days
  Implementation Cost = $50,000
Recommendation:
  Not in owner’s best interest to pursue
    Increased cost and planning for implementation outweigh savings in schedule and building performance
Building Enclosure Cost Comparison Summary |  | 
Item Description | Prefabricated Panels Total Cost | Existing Brick Total Cost
Cost of Assembly | $814,562.69 | $721,130
General Conditions Cost | $742,260.05 | $785,922
Total | $1,556,823 | $1,507,052
**Estimated Assembly costs based on RS Means 2013, Nitterhouse Concrete, and Actual Project Costs |  | 
Building Enclosure Construction Cost Comparison |  |  |  |  |  | 
Material Description | Total | Unit | Prefabricated Panels |  | Traditional Brick | 
 |  |  | Cost/SF | Total Cost | Cost/SF | Total Cost
Exterior Face Wall | 17,551 | SF | $25.00 | $438,775 | $16.10 | $282,571
Interior Component | 17,551 | SF | $19.63 | $344,485 | $19.63 | $344,485
Insulation (2" or 4") | 17,551 | SF | $1.37 | $24,045 | $2.68 | $47,037
Caulking | 3,360 | LF | $2.16 | $7,258 | - | -
Transportation | - | - | Included | Included | - | -
Erection Equipment (Scaffolding or Crane) | - | - | Included | Included | - | $47,037
Total |  |  | $48.2 | $814,563 | $38.4 | $721,130
Costs provided by Nitterhouse Concrete, RS Means 2013, and Actual Project Costs |  |  |  |  |  | 

## Slide 15
George M. Andonie │ Construction Option
Geisinger Grays Woods
Ambulatory Care Campus – Phase II
April 16, 2014
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Analysis #3
Re-evaluation of Structural Composite Slab
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
IV. Analysis #2: Façade Prefabrication
V. Analysis #3: Revaluating Comp. Slab
  Problem Identification
  Structural Breadth Analysis
  Project Impacts & Recommendations
VI. Final Recommendations
VII. Acknowledgements

## Slide 16
Existing Conditions
George M. Andonie │ Construction Option
Geisinger Grays Woods
Ambulatory Care Campus – Phase II
April 16, 2014
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Existing Conditions:
  38,000 SF of Composite Floor
  3 ¼” Lightweight Concrete
  2” Composite Metal Decking (18-Gauge)
  Typical 30’ x 30’ Bays (40)
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
IV. Analysis #2: Façade Prefabrication
V. Analysis #3: Revaluating Comp. Slab
  Problem Identification
  Structural Breadth Analysis
  Project Impacts & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Opportunity Identification:
  Vale Engineering on Structural System (20% of Building Costs)
    Reduce Overall Building Costs
Proposed Solution:
  Change Lightweight Composite Deck to Normal Concrete
    NW = Lower Material Cost
Research Goal:
  Reduce building costs
  Improve building performance
LIGHTWEIGHT
Unit Cost: $102/CY
Unit Weight: 150pcf
Low Fire Resistance
(4½" for 2-hr Rating)
Vibration Performance
Unit Cost: $134/CY
Unit Weight: 115pcf
High Fire Resistance
(3¼” for 2-hr Rating)
Retain More Moisture
NORMAL
BOTH
Strength
Placing
Finish
    Current Typical Bay (LW Concrete)

## Slide 17
Structural Breadth
George M. Andonie │ Construction Option
Geisinger Grays Woods
Ambulatory Care Campus – Phase II
April 16, 2014
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Existing LW Design | 
Item Description | Size
LW Concrete Material | 3.25"
Concrete Placing | <6"
Concrete Reinforcing | 6x6 W1.4xW1.4
Floor Decking | 2VLI18
Shear Studs | ½” Diameter
Steel Beams (4) | W18x35
Steel Girders (2) | W24x62
Steel Columns (2) | W10x49
Additional Fireproofing | -
Proposed NW Design | 
Item Description | Size
NW Concrete Material | 4.5"
Concrete Placing | <6"
Concrete Reinforcing | 6x6 W2.1xW2.1
Floor Decking | 2VLI18
Shear Studs | ½” Diameter
Steel Beams (4) | W18x35
Steel Girders (2) | W24x68
Steel Columns (2) | W10x49
Additional Fireproofing | -
CURRENT TYPICAL BAY
(LIGHTWEIGHT CONCRETE)
PROPOSED TYPICAL BAY DESIGN
(NORMAL CONCRETE)
Structural Calculations:
  Determine NW Deck Assembly
  Check Beam Sizing
  Check Girder Sizing
  Check Column Sizing
  Check Footing Sizing
Breadth Conclusions:
  4 ½” NW Composite Deck
    Increase Reinforcement
  Beam Spacing and Size
  Girder Sizes Increase to W24x68
    360lbs of Steel/Bay
  Column and Footing Sizes Acceptable
  Member Quantity Constant
  No Additional Fireproofing
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
IV. Analysis #2: Façade Prefabrication
V. Analysis #3: Revaluating Comp. Slab
  Problem Identification
  Structural Breadth Analysis
  Project Impacts & Recommendations
VI. Final Recommendations
VII. Acknowledgements
    Proposed Typical Bay (NW Concrete)
    Source: Vulcraft Decking Catalog

## Slide 18
Project Impacts
George M. Andonie │ Construction Option
Geisinger Grays Woods
Ambulatory Care Campus – Phase II
April 16, 2014
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Construction Implications:
  Floor-to-floor height:
      Loose 1.25” per floor
      Absorbed by ceiling plenum
  Beam Deflections:
      Impact on building’s serviceability
      Addressed in Structural Analysis
  Improved Quality Control:
    Moisture Content
    Fireproofing
Final Conclusions:
  Initial Goal = Reduce Project Costs
    Escalate Costs by $27,344
    Upsize Girders (Additional 7.2 Tons of Steel)
  Revised Goal = Improve Building Performance
    Vibration, Moisture, & Fireproofing
Recommend Change:
  Improved Quality Control
  Reduce Risks of Escalating Project Cost & Schedule
    Could have saved over $100,000 in project
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
IV. Analysis #2: Façade Prefabrication
V. Analysis #3: Revaluating Comp. Slab
  Problem Identification
  Structural Breadth Analysis
  Project Impacts & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Cost Implications:
  Implementing change increases system cost by 3%
    Concrete costs still increased
    Largest % Increase = Reinforcement
    Metal Decking & Studs Constant
Overall Cost Comparison |  |  | 
Item Description | System A: Proposed NW | System B: Existing LW | Cost Ratio (A/B)
Concrete Material & Placing | $85,068.00 | $80,643.60 | 1.05
Concrete Reinforcing | $15,480.00 | $12,960.00 | 1.19
Composite Metal Decking | $136,440.00 | $136,440.00 | 1.00
Headed Shear Stud Connectors | $22,080.00 | $22,080.00 | 1.00
Structural Steel Framing | $713,904.00 | $693,504.00 | 1.03
Additional Fireproofing | - | - | -
TOTAL | $972,972 | $945,627 | 1.03
Costs taken from 30x30' Typical Bay Detailed Estimate (Assuming 40 Bays) |  |  | 

## Slide 19
Conclusions
George M. Andonie │ Construction Option
Geisinger Grays Woods
Ambulatory Care Campus – Phase II
April 16, 2014
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
IV. Analysis #2: Façade Prefabrication
V. Analysis #3: Revaluating Comp. Slab
VI. Final Recommendations
VII. Acknowledgements
Analysis 1 │ Virtual Mockup Implementation:
  Implement Virtual Mockups for the facility’s Operating & Endoscopy Rooms
    Save Cost
    Save Time
    Reduce Risk
    Solve Constructability Issues
Analysis 2 │ Brick Façade Prefabrication
  Would not recommend the prefabrication of the building’s facade
    Increased Cost & Planning
    Reduced Schedule & Building Performance
Analysis 3 │ Re - evaluating Composite Slab
  Recommend Changing from LW to NW Composite Slab
    Improved Quality Control (Reduce Risk)
    Increased Cost
Improve Efficiency
Increased Collaboration
Streamline Process
Reduce Risk
Reduce Cost
Reduce Schedule
Improve Quality Control

## Slide 20
Acknowledgements
George M. Andonie │ Construction Option
Geisinger Grays Woods
Ambulatory Care Campus – Phase II
April 16, 2014
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
IV. Analysis #2: Façade Prefabrication
V. Analysis #3: Revaluating Comp. Slab
VI. Final Recommendations
VII. Acknowledgements
Architectural Engineering Faculty:
Dr. Rob Leicht (Advisor)
Dr. John Messner
Dr. Ali Memari
Special Thanks to:
My Family & Friends
Geisinger Health Systems
Douglas Workman, Josh Progar & Alexander’s Project Team
Mathew Hoerner - Alexander Building Construction
Ray Sowers & Ed Gannon - Penn State’s OPP
Mark Taylor – Nitterhouse Concrete
Sonali Kumar – Balfour Resource Group
George Burnley – High Concrete Group
PACE Industry Members
Industry Acknowledgements:

## Slide 21
Thank You
George M. Andonie │ Construction Option
Geisinger Grays Woods
Ambulatory Care Campus – Phase II
April 16, 2014
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Questions & Comments
**Rendering courtesy of Alexander Building Construction with Owner Permission
**Rendering courtesy of Alexander Building Construction with Owner Permission