## Slide 1
Jeremy Feath
Construction Option
University Engineering Building
Mid-Atlantic University, United States
(Courtesy of Owner)

## Slide 2
Project Overview
Jeremy Feath
Construction Option
University Engineering Building
Mid-Atlantic University, United States
Location: Mid-Atlantic, United States
Size: 95,000 SF
Project Cost: $43 million
Delivery Method: Design-Bid-Build
Project Duration: Jan. 2013 – Jan. 2015
Owner: Mid-Atlantic University
Design Architect: Stantec Arch. Inc.
General Contractor: Massaro Const.
Project Overview
Analysis 1: Clean Room Coordination
  Background
  Project Organization Results
  Coordination Results
Analysis 2: Roof System Redesign
  Background
  Schedule Results
  Cost Comparison
  Structural Breadth
Analysis 3: Underground Spring
  Background
  Results
  Mechanical Breadth
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
(Courtesy of Stantec)
(Courtesy of Google Maps)

## Slide 3
Project Overview
Jeremy Feath
Construction Option
University Engineering Building
Mid-Atlantic University, United States
Analysis 1: Clean Room Coordination
Reorganize project organization chart, along with creating and analyzing Clean Room coordination schedule & process
Analysis 2: Roof System Redesign
Propose a feasible alternative to the Fully-Adhered TPO roof system
Analysis 3: Underground Spring
Propose an alternative to the permanent sump pump to manage the underground spring located underneath the UEB’s foundation
Analysis 4: FM Information Delivery
Research and study the methods of information delivery from CM to FM and utilizing that information to manage facilities
Project Overview
Analysis 1: Clean Room Coordination
  Background
  Project Organization Results
  Coordination Results
Analysis 2: Roof System Redesign
  Background
  Schedule Results
  Cost Comparison
  Structural Breadth
Analysis 3: Underground Spring
  Background
  Results
  Mechanical Breadth
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
(Courtesy of Jeremy Feath)

## Slide 4
Analysis 1
Jeremy Feath
Construction Option
University Engineering Building
Mid-Atlantic University, United States
Analysis 1:
Clean Room Coordination
Project Overview
Analysis 1: Clean Room Coordination
  Background
  Project Organization Results
  Coordination Results
Analysis 2: Roof System Redesign
  Background
  Schedule Results
  Cost Comparison
  Structural Breadth
Analysis 3: Underground Spring
  Background
  Results
  Mechanical Breadth
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements

## Slide 5
Background
University Engineering Building
Mid-Atlantic University, United States
Analysis 1
Clean Room Coordination
Project Overview
Analysis 1: Clean Room Coordination
  Background
  Project Organization Results
  Coordination Results
Analysis 2: Roof System Redesign
  Background
  Schedule Results
  Cost Comparison
  Structural Breadth
Analysis 3: Underground Spring
  Background
  Results
  Mechanical Breadth
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Problem Identification:
Both Massaro and Hodess have separate contracts w/ the Owner
Coordination for the Clean Room is extremely intensive
  Scopes of Work
  Constructability
(Courtesy of Stantec)
(Courtesy of Stantec)
(Courtesy of Jeremy Feath)

## Slide 6
Project Organization
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
  Background
  Project Organization Results
  Coordination Results
Analysis 2: Roof System Redesign
  Background
  Schedule Results
  Cost Comparison
  Structural Breadth
Analysis 3: Underground Spring
  Background
  Results
  Mechanical Breadth
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Analysis 1
Clean Room Coordination
Original Design-Bid-Build
Hodess contract w/ Owner
Original Contractual Obligations:
Hodess used for Design Coordination, contracted to Owner at time
Massaro chosen as General Contractor, contracted to Owner
Owner unsuccessfully attempted to transfer Hodess’ contract to Massaro
(Courtesy of Jeremy Feath)

## Slide 7
Project Overview
Jeremy Feath
Construction Option
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
Analysis 2: Roof System Redesign
Analysis 3: Underground Spring
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Project Organization
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
  Background
  Project Organization Results
  Coordination Results
Analysis 2: Roof System Redesign
  Background
  Schedule Results
  Cost Comparison
  Structural Breadth
Analysis 3: Underground Spring
  Background
  Results
  Mechanical Breadth
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Analysis 1
Clean Room Coordination
Original Design-Bid-Build
Hodess contract w/ Owner
Original Contractual Obligations:
Hodess used for Design Coordination, contracted to Owner at time
Massaro chosen as General Contractor, contracted to Owner
Owner unsuccessfully attempted to transfer Hodess’ contract to Massaro
New Contractual Obligations:
Hodess has preconstruction contract with Owner
Massaro awarded bid, contract with the Owner
Hodess now acts as a subcontractor, construction contract with Massaro
New Design-Bid-Build
Hodess contract w/ Massaro
(Courtesy of Jeremy Feath)
(Courtesy of Jeremy Feath)

## Slide 8
Project Overview
Jeremy Feath
Construction Option
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
Analysis 2: Roof System Redesign
Analysis 3: Underground Spring
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
  Background
  Project Organization Results
  Coordination Results
Analysis 2: Roof System Redesign
  Background
  Schedule Results
  Cost Comparison
  Structural Breadth
Analysis 3: Underground Spring
  Background
  Results
  Mechanical Breadth
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Clean Room Coordination
Analysis 1
Clean Room Coordination
Problem Areas:
Clean Room Light Fixtures
Mezzanine AHUs
Clean Room Ceiling Grid
(Courtesy of Jeremy Feath)
(Courtesy of Jeremy Feath)
(Courtesy of Jeremy Feath)
(Courtesy of Stantec)

## Slide 9
Project Overview
Jeremy Feath
Construction Option
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
Analysis 2: Roof System Redesign
Analysis 3: Underground Spring
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
  Background
  Project Organization Results
  Coordination Results
Analysis 2: Roof System Redesign
  Background
  Schedule Results
  Cost Comparison
  Structural Breadth
Analysis 3: Underground Spring
  Background
  Results
  Mechanical Breadth
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Clean Room Coordination
Analysis 1
Clean Room Coordination
Problem Areas:
Clean Room Light Fixtures
Mezzanine AHUs
Clean Room Ceiling Grid
Savings:
Less RFIs, COs
Fewer Constructability Problems
Potential Schedule Savings
Tools:
3D Model Coordination
Hodess Precon experience
Early Problem Identification
(Courtesy of Jeremy Feath)
(Courtesy of Jeremy Feath)
(Courtesy of Stantec)
(Courtesy of Jeremy Feath)

## Slide 10
Project Overview
Jeremy Feath
Construction Option
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
Analysis 2: Roof System Redesign
Analysis 3: Underground Spring
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
  Background
  Project Organization Results
  Coordination Results
Analysis 2: Roof System Redesign
  Background
  Schedule Results
  Cost Comparison
  Structural Breadth
Analysis 3: Underground Spring
  Background
  Results
  Mechanical Breadth
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Analysis 2
Jeremy Feath
Construction Option
Analysis 2:
Roof System Redesign

## Slide 11
Project Overview
Jeremy Feath
Construction Option
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
Analysis 2: Roof System Redesign
Analysis 3: Underground Spring
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Analysis 2
Roof System Redesign
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
  Background
  Project Organization Results
  Coordination Results
Analysis 2: Roof System Redesign
  Background
  Schedule Results
  Cost Comparison
  Structural Breadth
Analysis 3: Underground Spring
  Background
  Results
  Mechanical Breadth
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Background
Lab Roof: 14,000 SF
Office Roof: 10,000 SF
(Courtesy of Stantec)

## Slide 12
Project Overview
Jeremy Feath
Construction Option
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
Analysis 2: Roof System Redesign
Analysis 3: Underground Spring
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Analysis 2
Roof System Redesign
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
  Background
  Project Organization Results
  Coordination Results
Analysis 2: Roof System Redesign
  Background
  Schedule Results
  Cost Comparison
  Structural Breadth
Analysis 3: Underground Spring
  Background
  Results
  Mechanical Breadth
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Background
Original Project Schedule
Lab Roof Activities – Total Duration: 61 days
Office Roof Activities – Total Duration: 30 days
Lab Roof: 14,000 SF
Office Roof: 10,000 SF
(Courtesy of Stantec)
(Courtesy of Massaro)

## Slide 13
Project Overview
Jeremy Feath
Construction Option
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
Analysis 2: Roof System Redesign
Analysis 3: Underground Spring
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Analysis 2
Roof System Redesign
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
  Background
  Project Organization Results
  Coordination Results
Analysis 2: Roof System Redesign
  Background
  Schedule Results
  Cost Comparison
  Structural Breadth
Analysis 3: Underground Spring
  Background
  Results
  Mechanical Breadth
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Background
Roof System Problems:
Cold-Weather Constructability Difficult
Increased General Conditions Costs
Delayed Interior Work (Fireproofing, MEP Rough-Ins)
Lab Roof: 14,000 SF
Office Roof: 10,000 SF
Original Project Schedule
Lab Roof Activities – Total Duration: 61 days
Office Roof Activities – Total Duration: 30 days
(Courtesy of Stantec)
(Courtesy of Jeremy Feath)
(Courtesy of Jeremy Feath)
(Courtesy of Massaro)

## Slide 14
Project Overview
Jeremy Feath
Construction Option
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
Analysis 2: Roof System Redesign
Analysis 3: Underground Spring
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Analysis 2
Roof System Redesign
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
  Background
  Project Organization Results
  Coordination Results
Analysis 2: Roof System Redesign
  Background
  Schedule Results
  Cost Comparison
  Structural Breadth
Analysis 3: Underground Spring
  Background
  Results
  Mechanical Breadth
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Background
Proposed Solution:
Firestone TPO InvisiWeld System
Improved Cold-Weather Constructability
Meets Owner Approval & Contractor Experience
(Courtesy of Firestone Building Products)
(Courtesy of Firestone Building Products)

## Slide 15
Project Overview
Jeremy Feath
Construction Option
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
Analysis 2: Roof System Redesign
Analysis 3: Underground Spring
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Analysis 2
Roof System Redesign
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
  Background
  Project Organization Results
  Coordination Results
Analysis 2: Roof System Redesign
  Background
  Schedule Results
  Cost Comparison
  Structural Breadth
Analysis 3: Underground Spring
  Background
  Results
  Mechanical Breadth
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Schedule Results
Location | Area (SF) | 4'x8' Board (SF) | # Boards | Avg. # of Plates | Total Plates | # Plates/Hr. | Total Hrs. | Total Days
Lab | 14000 | 32 | 437.5 | 14 | 6125 | 300 | 20.42 | 2.55
Office | 10000 | 32 | 312.5 | 14 | 4375 | 300 | 14.58 | 1.82
InvisiWeld Plate Weld Durations
Roof System | Lab Duration | Office Duration | Total Duration
Fully-Adhered TPO | 61 | 30 | 61
InvisiWeld | 35 | 25 | 40
Built-Up Roof | 51 | 47 | 65
Roof System Duration Comparison
Note: 300 plates/hr. based on Firestone literature
(All Courtesy of Jeremy Feath)

## Slide 16
Project Overview
Jeremy Feath
Construction Option
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
Analysis 2: Roof System Redesign
Analysis 3: Underground Spring
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Analysis 2
Roof System Redesign
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
  Background
  Project Organization Results
  Coordination Results
Analysis 2: Roof System Redesign
  Background
  Schedule Results
  Cost Comparison
  Structural Breadth
Analysis 3: Underground Spring
  Background
  Results
  Mechanical Breadth
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Schedule Results
Location | Area (SF) | 4'x8' Board (SF) | # Boards | Avg. # of Plates | Total Plates | # Plates/Hr. | Total Hrs. | Total Days
Lab | 14000 | 32 | 437.5 | 14 | 6125 | 300 | 20.42 | 2.55
Office | 10000 | 32 | 312.5 | 14 | 4375 | 300 | 14.58 | 1.82
InvisiWeld Plate Weld Durations
Roof System | Lab Duration | Office Duration | Total Duration
Fully-Adhered TPO | 61 | 30 | 61
InvisiWeld | 35 | 25 | 40
Built-Up Roof | 51 | 47 | 65
Roof System Duration Comparison
InvisiWeld Construction Schedule
Note: 300 plates/hr. based on Firestone literature
(All Courtesy of Jeremy Feath)

## Slide 17
Project Overview
Jeremy Feath
Construction Option
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
Analysis 2: Roof System Redesign
Analysis 3: Underground Spring
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Analysis 2
Roof System Redesign
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
  Background
  Project Organization Results
  Coordination Results
Analysis 2: Roof System Redesign
  Background
  Schedule Results
  Cost Comparison
  Structural Breadth
Analysis 3: Underground Spring
  Background
  Results
  Mechanical Breadth
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Cost Comparison
TOTAL |  |  | $1,610,845.00
TOTAL CONSTRUCTION COSTS * 6% |  |  | $1,962,000.00
COST DIFFERENCE |  |  | $351,155.00
% DIFFERENCE |  |  | 17.90
TOTAL |  |  | $1,618,545.00
TOTAL CONSTRUCTION COSTS * 6% |  |  | $1,962,000.00
COST DIFFERENCE |  |  | $343,455.00
% DIFFERENCE |  |  | 17.51
Original General Conditions Estimate
Revised General Conditions Estimate
Fully Adhered TPO Membrane Roof Estimate |  |  |  | 
Material | Quantity | Unit | Cost/Unit | Total Cost
TPO Membrane (80 mil) | 24000 | SF | $1.03 | $24,720.00
Multipurpose Adhesives | 40 | 600 SF | $145.00 | $5,800.00
Expansion Joint | 800 | LF | $2.00 | $1,600.00
1/2" Protection Board | 24000 | SF | $0.53 | $12,720.00
(2) 2" Rigid Insulation | 24000 | SF | $0.65 | $15,600.00
Single-Ply Memb. Sealants | 100 | 1 gal. Pail | $75.00 | $7,500.00
Sealant Primers | 100 | 1 gal. Pail | $67.00 | $6,700.00
Sheet Flashing | 24 | 100 SF | $251.00 | $6,024.00
Bonding Adhesive | 54 | 450 SF Pail | $145.00 | $7,830.00
Fasteners | 25 | 5" HD 1000/Pail | $190.00 | $4,750.00
Metal Termination Bar | 80 | 10 LF | $7.00 | $560.00
Total |  |  |  | $93,804.00
Fully-Adhered TPO System
General Conditions Increase - $7,700
Increase in Temporary Heating & Enclosure:
  Protect Penthouse Equipment & Stored Materials
  Enable interior rough-in work to continue
Note: The increase in GC does not occur for BUR or InvisiWeld
(All Courtesy of Jeremy Feath)

## Slide 18
Project Overview
Jeremy Feath
Construction Option
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
Analysis 2: Roof System Redesign
Analysis 3: Underground Spring
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Analysis 2
Roof System Redesign
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
  Background
  Project Organization Results
  Coordination Results
Analysis 2: Roof System Redesign
  Background
  Schedule Results
  Cost Comparison
  Structural Breadth
Analysis 3: Underground Spring
  Background
  Results
  Mechanical Breadth
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Cost Comparison
Traditional Built-Up Roof |  |  |  | 
Material | Quantity | Unit | Cost/Unit | Total Cost
Ply VI Membrane (4 Layers) | 96000 | SF (1 - Layer) | $0.85 | $81,600.00
Asphalt | 30 | ton | $820.00 | $24,600.00
(2) 2" Rigid Insulation | 24000 | SF | $0.65 | $15,600.00
Cover Board | 24000 | SF | $0.53 | $12,720.00
Total |  |  |  | $134,520.00
Labor Cost Estimate |  |  |  | 
Roof Type | Duration (days) | Hourly Rate | Daily Rate | Total Cost
Fully-Adhered TPO | 61 | $100.00 | $800.00 | $48,800.00
Built-Up Roof | 65 | $100.00 | $800.00 | $52,000.00
InvisiWeld TPO | 40 | $100.00 | $800.00 | $32,000.00
Fully Adhered TPO Membrane Roof Estimate |  |  |  | 
Material | Quantity | Unit | Cost/Unit | Total Cost
TPO Membrane (80 mil) | 24000 | SF | $1.03 | $24,720.00
Multipurpose Adhesives | 40 | 600 SF | $145.00 | $5,800.00
Expansion Joint | 800 | LF | $2.00 | $1,600.00
1/2" Protection Board | 24000 | SF | $0.53 | $12,720.00
(2) 2" Rigid Insulation | 24000 | SF | $0.65 | $15,600.00
Single-Ply Memb. Sealants | 100 | 1 gal. Pail | $75.00 | $7,500.00
Sealant Primers | 100 | 1 gal. Pail | $67.00 | $6,700.00
Sheet Flashing | 24 | 100 SF | $251.00 | $6,024.00
Bonding Adhesive | 54 | 450 SF Pail | $145.00 | $7,830.00
Fasteners | 25 | 5" HD 1000/Pail | $190.00 | $4,750.00
Metal Termination Bar | 80 | 10 LF | $7.00 | $560.00
Total |  |  |  | $93,804.00
(All Courtesy of Jeremy Feath)

## Slide 19
Project Overview
Jeremy Feath
Construction Option
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
Analysis 2: Roof System Redesign
Analysis 3: Underground Spring
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Analysis 2
Roof System Redesign
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
  Background
  Project Organization Results
  Coordination Results
Analysis 2: Roof System Redesign
  Background
  Schedule Results
  Cost Comparison
  Structural Breadth
Analysis 3: Underground Spring
  Background
  Results
  Mechanical Breadth
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Cost Comparison
InvisiWeld TPO Membrane Roof |  |  |  | 
Material | Quantity | Unit | Cost/Unit | Total Cost
TPO Membrane (80 mil) | 24000 | SF | $1.03 | $24,720.00
Expansion Joint | 800 | LF | $2.00 | $1,600.00
1/2" Protection Board | 24000 | SF | $0.53 | $12,720.00
(2) 2" Rigid Insulation | 24000 | SF | $0.65 | $15,600.00
Single-Ply Memb. Sealants | 100 | 1 gal. Pail | $75.00 | $7,500.00
Sealant Primers | 100 | 1 gal. Pail | $67.00 | $6,700.00
Sheet Flashing | 24 | 100 SF | $251.00 | $6,024.00
Fasteners | 25 | 5" HD 1000/Pail | $190.00 | $4,750.00
InvisiWeld Plates | 21 | 500 Pail | $90.00 | $1,890.00
InvisiWeld Machine | 1 | EA | $7,500.00 | $7,500.00
T-Patches | 5250 | EA | $0.44 | $2,310.00
Pipe Boots | 10 | EA | $23.00 | $230.00
Total |  |  |  | $91,544.00
Total Cost Savings:
$26,760.00
Traditional Built-Up Roof |  |  |  | 
Material | Quantity | Unit | Cost/Unit | Total Cost
Ply VI Membrane (4 Layers) | 96000 | SF (1 - Layer) | $0.85 | $81,600.00
Asphalt | 30 | ton | $820.00 | $24,600.00
(2) 2" Rigid Insulation | 24000 | SF | $0.65 | $15,600.00
Cover Board | 24000 | SF | $0.53 | $12,720.00
Total |  |  |  | $134,520.00
Labor Cost Estimate |  |  |  | 
Roof Type | Duration (days) | Hourly Rate | Daily Rate | Total Cost
Fully-Adhered TPO | 61 | $100.00 | $800.00 | $48,800.00
Built-Up Roof | 65 | $100.00 | $800.00 | $52,000.00
InvisiWeld TPO | 40 | $100.00 | $800.00 | $32,000.00
Fully Adhered TPO Membrane Roof Estimate |  |  |  | 
Material | Quantity | Unit | Cost/Unit | Total Cost
TPO Membrane (80 mil) | 24000 | SF | $1.03 | $24,720.00
Multipurpose Adhesives | 40 | 600 SF | $145.00 | $5,800.00
Expansion Joint | 800 | LF | $2.00 | $1,600.00
1/2" Protection Board | 24000 | SF | $0.53 | $12,720.00
(2) 2" Rigid Insulation | 24000 | SF | $0.65 | $15,600.00
Single-Ply Memb. Sealants | 100 | 1 gal. Pail | $75.00 | $7,500.00
Sealant Primers | 100 | 1 gal. Pail | $67.00 | $6,700.00
Sheet Flashing | 24 | 100 SF | $251.00 | $6,024.00
Bonding Adhesive | 54 | 450 SF Pail | $145.00 | $7,830.00
Fasteners | 25 | 5" HD 1000/Pail | $190.00 | $4,750.00
Metal Termination Bar | 80 | 10 LF | $7.00 | $560.00
Total |  |  |  | $93,804.00
(All Courtesy of Jeremy Feath)

## Slide 20
Analysis 2
Roof System Redesign
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
  Background
  Project Organization Results
  Coordination Results
Analysis 2: Roof System Redesign
  Background
  Schedule Results
  Cost Comparison
  Structural Breadth
Analysis 3: Underground Spring
  Background
  Results
  Mechanical Breadth
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Roof Deck Study
Purpose:
To study the affect increased roof load has on metal decking
TPO vs. Garden Roof
Original Deck: 1-1/2”, 20 gauge
(Courtesy of Stantec)
(Courtesy of Vulcraft)
(Courtesy of Jeremy Feath)

## Slide 21
Project Overview
Jeremy Feath
Construction Option
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
Analysis 2: Roof System Redesign
Analysis 3: Underground Spring
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
  Background
  Project Organization Results
  Coordination Results
Analysis 2: Roof System Redesign
  Background
  Schedule Results
  Cost Comparison
  Structural Breadth
Analysis 3: Underground Spring
  Background
  Results
  Mechanical Breadth
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Analysis 3
Jeremy Feath
Construction Option
Analysis 3:
Underground Spring

## Slide 22
Project Overview
Jeremy Feath
Construction Option
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
Analysis 2: Roof System Redesign
Analysis 3: Underground Spring
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Analysis 3
Underground Spring
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
  Background
  Project Organization Results
  Coordination Results
Analysis 2: Roof System Redesign
  Background
  Schedule Results
  Cost Comparison
  Structural Breadth
Analysis 3: Underground Spring
  Background
  Results
  Mechanical Breadth
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Background
Problems:
Spring & Rain delayed construction during Excavation & Foundations
Spring was NOT discovered during GeoTech Investigation
Proposed Solution:
Addition of Waterproofing Membrane to Lab Foundation Wall w/ Sump Pump backup
(Courtesy of Jeremy Feath)
(Courtesy of Stantec)

## Slide 23
Project Overview
Jeremy Feath
Construction Option
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
Analysis 2: Roof System Redesign
Analysis 3: Underground Spring
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Analysis 3
Underground Spring
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
  Background
  Project Organization Results
  Coordination Results
Analysis 2: Roof System Redesign
  Background
  Schedule Results
  Cost Comparison
  Structural Breadth
Analysis 3: Underground Spring
  Background
  Results
  Mechanical Breadth
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Background
Project Team Solution – Permanent Sump Pump
Material | Quantity | Unit | Cost per Unit | Total Cost
Sump Pump (Temporary) | 1 | EA | $120.00 | $120.00
Sump Pump (Permanent) | 1 | EA | $215.00 | $215.00
2" PVC | 160 | LF | $12.09 | $1,934.40
Check Valve | 1 | EA | $37.25 | $37.25
90° Elbow | 1 | EA | $46.86 | $46.86
45° Elbow | 3 | EA | $36.48 | $109.44
Total |  |  |  | $2,462.95
Sump Pump System Estimate
Proposed Solution:
Addition of Waterproofing Membrane to Lab Foundation Wall w/ Sump Pump backup
Problems:
Spring & Rain delayed construction during Excavation & Foundations
Spring was NOT discovered during GeoTech Investigation
(Const. DWGs Courtesy of Stantec)
(Photos & Table Courtesy of Jeremy Feath)

## Slide 24
Project Overview
Jeremy Feath
Construction Option
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
Analysis 2: Roof System Redesign
Analysis 3: Underground Spring
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Analysis 3
Underground Spring
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
  Background
  Project Organization Results
  Coordination Results
Analysis 2: Roof System Redesign
  Background
  Schedule Results
  Cost Comparison
  Structural Breadth
Analysis 3: Underground Spring
  Background
  Results
  Mechanical Breadth
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Results
Underground Spring Solution:
Tamko TW-60 Waterproofing Membrane
N Line 1 – 6
6 Line N – G
G Line 1 – 6
1 Line G - N
(Const. DWGs Courtesy of Stantec)
(Photos & Table Courtesy of Jeremy Feath)
(Courtesy of Tamko)

## Slide 25
Project Overview
Jeremy Feath
Construction Option
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
Analysis 2: Roof System Redesign
Analysis 3: Underground Spring
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Analysis 3
Underground Spring
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
  Background
  Project Organization Results
  Coordination Results
Analysis 2: Roof System Redesign
  Background
  Schedule Results
  Cost Comparison
  Structural Breadth
Analysis 3: Underground Spring
  Background
  Results
  Mechanical Breadth
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Results
Underground Spring Solution:
Tamko TW-60 Waterproofing Membrane
Level 0 & Mezzanine (Lab) | Roll Width (in.) | Roll Size | Area Coverage | Wall Area | # Rolls Needed | Cost per Roll | Total Cost
N Line 1 - 6 | 39.375 | 39.375" x 61' | 200 | 3404.88 | 18 | $292.00 | $5,256.00
6 Line N - G | 39.375 | 39.375" x 61' | 200 | 4173.36 | 21 | $292.00 | $6,132.00
G Line 1 - 6 | 39.375 | 39.375" x 61' | 200 | 2496.96 | 13 | $292.00 | $3,796.00
1 Line G - N | 39.375 | 39.375" x 61' | 200 | 2210.18 | 12 | $292.00 | $3,504.00
Total |  |  |  |  |  |  | $18,688.00
Tamko TW-60 Material Foundation Wall Costs
Material | Quantity | Unit | Cost per Unit | Total Cost
Sump Pump (Temporary) | 1 | EA | $120.00 | $120.00
Sump Pump (Permanent) | 1 | EA | $215.00 | $215.00
2" PVC | 160 | LF | $12.09 | $1,934.40
Check Valve | 1 | EA | $37.25 | $37.25
90° Elbow | 1 | EA | $46.86 | $46.86
45° Elbow | 3 | EA | $36.48 | $109.44
Total |  |  |  | $2,462.95
Sump Pump System Estimate
N Line 1 – 6
6 Line N – G
G Line 1 – 6
1 Line G - N
Cost Estimate Impact
Note: Labor Costs do NOT change
Total System Cost - $21,151.00
Cost difference made up from Roof System change
System is necessary to combat the Spring in combination with heavy rainfall
(Const. DWGs Courtesy of Stantec)
(Table s Courtesy of Jeremy Feath)
(Courtesy of Tamko)

## Slide 26
Project Overview
Jeremy Feath
Construction Option
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
Analysis 2: Roof System Redesign
Analysis 3: Underground Spring
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Analysis 3
Underground Spring
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
  Background
  Project Organization Results
  Coordination Results
Analysis 2: Roof System Redesign
  Background
  Schedule Results
  Cost Comparison
  Structural Breadth
Analysis 3: Underground Spring
  Background
  Results
  Mechanical Breadth
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Results
Underground Spring Solution:
Tamko TW-60 Waterproofing Membrane
N Line 1 – 6
6 Line N – G
G Line 1 – 6
1 Line G - N
Schedule Impact
Level 0 & Mezzanine (Lab) | LF Coverage | Wall Height | Daily Output (LF) | Daily Output (SF) | Coverage Area | Duration
N Line 1 - 6 | 141.87 | 24 | 80 | 1920 | 3404.88 | 1.77
6 Line N - G | 173.89 | 24 | 80 | 1920 | 4173.36 | 2.17
G Line 1 - 6 | 104.04 | 24 | 80 | 1920 | 2496.96 | 1.30
1 Line G - N | 157.87 | 14 | 80 | 1120 | 2210.18 | 1.97
Total |  |  |  |  |  | 7.22
Foundation Waterproofing Membrane Durations
Each Wall section follows same pattern
Duration from Table, broken down based on # of pours for the Wall section
Schedule increase acceptable, work can be completed around steel erection
Total Schedule Change = +4 days
Roughly 1 extra day per Wall section
(Const. DWGs Courtesy of Stantec)
(Table & Schedule Courtesy of Jeremy Feath)
(Courtesy of Tamko)

## Slide 27
Project Overview
Jeremy Feath
Construction Option
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
Analysis 2: Roof System Redesign
Analysis 3: Underground Spring
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Analysis 3
Underground Spring
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
  Background
  Project Organization Results
  Coordination Results
Analysis 2: Roof System Redesign
  Background
  Schedule Results
  Cost Comparison
  Structural Breadth
Analysis 3: Underground Spring
  Background
  Results
  Mechanical Breadth
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Sizing of a Sump Pump
Technical Data:
System Capacity = 30 GPM
Total Dynamic Head = 14’
  Static Head = 10’
  Friction Head = 3.27’
Level 0 Panelboards have the capacity to handle the additional load of a sump pump
(Const. DWGs Courtesy of Stantec)
(Equation Courtesy of Jeremy Feath) (Literature Courtesy of Hydromatic)

## Slide 28
Project Overview
Jeremy Feath
Construction Option
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
Analysis 2: Roof System Redesign
Analysis 3: Underground Spring
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Analysis 4
CM to FM Information Delivery
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
  Background
  Project Organization Results
  Coordination Results
Analysis 2: Roof System Redesign
  Background
  Schedule Results
  Cost Comparison
  Structural Breadth
Analysis 3: Underground Spring
  Background
  Results
  Mechanical Breadth
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Summary
Key Takeaways:
Necessary to weed out critical information from excess
It’s not always the information itself, but the means of using that information for O&M
(Images Courtesy of Google, Penn State & IBM)

## Slide 29
Project Overview
Jeremy Feath
Construction Option
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
Analysis 2: Roof System Redesign
Analysis 3: Underground Spring
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
  Background
  Project Organization Results
  Coordination Results
Analysis 2: Roof System Redesign
  Background
  Schedule Results
  Cost Comparison
  Structural Breadth
Analysis 3: Underground Spring
  Background
  Results
  Mechanical Breadth
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Final Recommendations
Jeremy Feath
Construction Option
Analysis 1: Clean Room Coordination:
Reorganize project team chart to reflect new contractual obligations for Hodess
Creation of Coordination Schedule to maximize early coordination for the Clean Room
Recommendation: PROCEED
Analysis 2: Roof System Redesign:
Replace Fully-Adhered TPO with InvisiWeld TPO system.
Saves 20+ working days on schedule
Saves $27,000 in costs
Recommendation: PROCEED
Analysis 3: Underground Spring:
Add Waterproofing Membrane in addition to the sump pump solution of the project team.
Schedule Impact is negligible
Cost Impact, while substantial, can be offset by Roof savings
Recommendation: PROCEED
Analysis 4: CM – FM Information Delivery:
Outline created to help Owners/FM incorporate technologies
Means of using information more important than information at times
Recommendation: PROCEED
(Courtesy of Owner)

## Slide 30
Project Overview
Jeremy Feath
Construction Option
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
Analysis 2: Roof System Redesign
Analysis 3: Underground Spring
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
  Background
  Project Organization Results
  Coordination Results
Analysis 2: Roof System Redesign
  Background
  Schedule Results
  Cost Comparison
  Structural Breadth
Analysis 3: Underground Spring
  Background
  Results
  Mechanical Breadth
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Acknowledgements
Jeremy Feath
Construction Option
A Special Thanks to …
AE Faculty & Staff
Dr. Craig Dubler
Dr. Ed Gannon
Todd Bookwalter
Bud Curry
The University Project Team
Massaro Project Team
Friends & Family
(Courtesy of Stantec)

## Slide 31
Project Overview
Jeremy Feath
Construction Option
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
Analysis 2: Roof System Redesign
Analysis 3: Underground Spring
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
University Engineering Building
Mid-Atlantic University, United States
Project Overview
Analysis 1: Clean Room Coordination
  Background
  Project Organization Results
  Coordination Results
Analysis 2: Roof System Redesign
  Background
  Schedule Results
  Cost Comparison
  Structural Breadth
Analysis 3: Underground Spring
  Background
  Results
  Mechanical Breadth
Analysis 4: FM Information Delivery
Final Recommendations
Acknowledgements
Questions
Jeremy Feath
Construction Option
Analysis 1: Clean Room Coordination:
Reorganize project team chart to reflect new contractual obligations for Hodess
Creation of Coordination Schedule to maximize early coordination for the Clean Room
Recommendation: PROCEED
Analysis 2: Roof System Redesign:
Replace Fully-Adhered TPO with InvisiWeld TPO system.
Saves 20+ working days on schedule
Saves $27,000 in costs
Recommendation: PROCEED
Analysis 3: Underground Spring:
Add Waterproofing Membrane in addition to the sump pump solution of the project team.
Schedule Impact is negligible
Cost Impact, while substantial, can be offset by Roof savings
Recommendation: PROCEED
Analysis 4: CM – FM Information Delivery:
Outline created to help Owners/FM incorporate technologies
Means of using information more important than information at times
Recommendation: PROCEED
(Courtesy of Owner)