## Slide 1: 2B + G + M + 7 Mansoura Development Doha, Qatar
Penn State Architectural Engineering Senior Capstone Project
Ramy Labna | Construction Option | Advisor: Prof Ray Sowers

## Slide 2
Project Overview
OUTLINE
Project Background
Analysis 1: Construction Precast Vs. Cast in Place Concrete
Analysis 2: Comparison of Construction Practices between US & Qatar
Analysis 3: Field Labor Management & Alteration
Conclusion
Analysis 1: Precast Vs. Cast in Place
Analysis 2: Comparison of Construction Practices between US & Qatar
Analysis 3: Field Labor Management & Alteration
Ramy Labna | Construction Option
2B + G + M + 7 Mansoura Development
Photo Courtesy of www.beautifulholidays.com.au
Photo Courtesy of www.mcentirerentalproperties.com
Photo Courtesy of www.cutcaster.com

## Slide 3
Project Background
  Building Name | 2B + G + M + 7 Development at Mansoura
  Size | 106,000 Gross Square Feet
  No. of Stories | 9 stories above grade & 2 stories below
  Dates of Construction | April 15, 2013 – April 15, 2015
  Cost of overall Project | $7M
  Project Delivery Method | Design-Bid-Build
  Payment Method | Lump Sum Method
  Owner| Fakhriya Radhwani
  Architect | Petra Design
  Contractor | Commitment Construction
PROJECT INFO
Ramy Labna | Construction Option
2B + G + M + 7 Mansoura Development
OUTLINE
Project Background
Analysis 1: Construction Precast Vs. Cast in Place Concrete
Analysis 2: Comparison of Construction Practices between US & Qatar
Analysis 3: Field Labor Management & Alteration
Conclusion

## Slide 4
Analysis 1: Construction of Precast Vs. Cast in Place Construction
Ramy Labna | Construction Option
2B + G + M + 7 Mansoura Development
Opportunity Identification
Schedule & Construction acceleration scenarios
Reduction of Schedule with the use of Precast Panels
Existing System
Cast in Place Concrete – Entire Structure
Concrete transported in unhardened state as ready-mix
Used for its long-term durability & structural support
Current superstructure schedule takes approximately 13 months
OUTLINE
Project Background
Analysis 1: Construction Precast Vs. Cast in Place Concrete
  Introduction
  Design
  Manufacturing & Quality
  Delivery & Erection
  Cost Impact
  Schedule Impacts
  Mechanical Breadth
  Conclusions & Recommendations
Analysis 2: Comparison of Construction Practices between US & Qatar
Analysis 3: Field Labor Management & Alteration
Conclusion

## Slide 5
Ramy Labna | Construction Option
2B + G + M + 7 Mansoura Development
Current Design
10” of concrete with no insulation
Paint Finish
Proposed Design
2” of Rigid Insulation
Sandwiched by two 3” Concrete panels
Paint Finish
Existing System
Cast in Place Concrete – Entire Structure
Concrete transported in unhardened state as ready-mix
Used for its long-term durability & structural support
Proposed System
Precast Concrete Exterior Wall Panels
Floor Beams & Columns and Slabs are cast in place
OUTLINE
Project Background
Analysis 1: Construction Precast Vs. Cast in Place Concrete
  Introduction
  Design
  Manufacturing & Quality
  Delivery & Erection
  Cost Impact
  Schedule Impacts
  Mechanical Breadth
  Conclusions & Recommendations
Analysis 2: Comparison of Construction Practices between US & Qatar
Analysis 3: Field Labor Management & Alteration
Conclusion
Analysis 1: Construction of Precast Vs. Cast in Place Concrete
Photo Courtesy of www.enconunited.com

## Slide 6
Ramy Labna | Construction Option
2B + G + M + 7 Mansoura Development
Design
Aim: To reduce amount of panels used
Panels designed to fit between each floor beams
Repetitive floors (1-7)
Same concrete mold can be used for multiple panels
Total of 33 Different Panels
West & East façades are completely identical
OUTLINE
Project Background
Analysis 1: Construction Precast Vs. Cast in Place Concrete
  Introduction
  Design
  Manufacturing & Quality
  Delivery & Erection
  Cost Impact
  Schedule Impacts
  Mechanical Breadth
  Conclusions & Recommendations
Analysis 2: Comparison of Construction Practices between US & Qatar
Analysis 3: Field Labor Management & Alteration
Conclusion
North Elevation
Analysis 1: Construction of Precast Vs. Cast in Place Concrete

## Slide 7
Ramy Labna | Construction Option
2B + G + M + 7 Mansoura Development
OUTLINE
Project Background
Analysis 1: Construction Precast Vs. Cast in Place Concrete
  Introduction
  Design
  Manufacturing & Quality
  Delivery & Erection
  Cost Impact
  Schedule Impacts
  Mechanical Breadth
  Conclusions & Recommendations
Analysis 2: Comparison of Construction Practices between US & Qatar
Analysis 3: Field Labor Management & Alteration
Conclusion
West & East Elevation
South Elevation
Analysis 1: Construction of Precast Vs. Cast in Place Concrete

## Slide 8
Ramy Labna | Construction Option
2B + G + M + 7 Mansoura Development
Manufacturing
Offsite controlled working environment
Better efficiency due to repetitive process
Favorable working conditions
Less material wasted
Better safety practices
Quality
PCI Certified
Controlled air entrainment and cuing procedures
Better & more consistent quality of work
OUTLINE
Project Background
Analysis 1: Construction Precast Vs. Cast in Place Concrete
  Introduction
  Design
  Manufacturing & Quality
  Delivery & Erection
  Cost Impact
  Schedule Impacts
  Mechanical Breadth
  Conclusions & Recommendations
Analysis 2: Comparison of Construction Practices between US & Qatar
Analysis 3: Field Labor Management & Alteration
Conclusion
Analysis 1: Construction of Precast Vs. Cast in Place Concrete
Photo Courtesy of www.concretetissues.com
Photo Courtesy of www.atmiprecast.com

## Slide 9
Ramy Labna | Construction Option
2B + G + M + 7 Mansoura Development
Delivery
12’ x 50’ truck bed
Transported on non-staining, shock absorbing material
Manage ‘just-in-time’ deliveries
Delivery within 20-35 miles
Erection
Duration of erection reduced
40 ton lifting crane
1 floor erected per day
OUTLINE
Project Background
Analysis 1: Construction Precast Vs. Cast in Place Concrete
  Introduction
  Design
  Manufacturing & Quality
  Delivery & Erection
  Cost Impact
  Schedule Impacts
  Mechanical Breadth
  Conclusions & Recommendations
Analysis 2: Comparison of Construction Practices between US & Qatar
Analysis 3: Field Labor Management & Alteration
Conclusion
Analysis 1: Construction of Precast Vs. Cast in Place Concrete
Photo Courtesy of www.truckfax.blogspot.com
Photo Courtesy of www.sicklesteelcranes.com

## Slide 10
Ramy Labna | Construction Option
2B + G + M + 7 Mansoura Development
Cast in Place Concrete
Price retrieved from RSMeans (Location factor: Philadelphia)
Cost includes Labor, Material & Erection
Cost: $550.50/CY
Precast Concrete Wall Panels
Price retrieved from Encon United Precast Company
Cost includes Material, Transportation, Insulation & Erection
Cost: $25/SF – without architectural finish
  $30/SF – with architectural finish
Cost Comparison
Further detail can be seen in Appendix I in final report
OUTLINE
Project Background
Analysis 1: Construction Precast Vs. Cast in Place Concrete
  Introduction
  Design
  Manufacturing & Quality
  Delivery & Erection
  Cost Impact
  Schedule Impacts
  Mechanical Breadth
  Conclusions & Recommendations
Analysis 2: Comparison of Construction Practices between US & Qatar
Analysis 3: Field Labor Management & Alteration
Conclusion
Analysis 1: Construction of Precast Vs. Cast in Place Concrete

## Slide 11
Ramy Labna | Construction Option
2B + G + M + 7 Mansoura Development
Actual Savings
Superstructure completed on 17th Sept, 2014 (9 days ahead of schedule)
Minimum difference due to:
  Sequencing and coordination of current schedule
Proposed Schedule Savings
Further detail can be seen in Appendix H for revised schedule
OUTLINE
Project Background
Analysis 1: Construction Precast Vs. Cast in Place Concrete
  Introduction
  Design
  Manufacturing & Quality
  Delivery & Erection
  Cost Impact
  Schedule Impacts
  Mechanical Breadth
  Conclusions & Recommendations
Analysis 2: Comparison of Construction Practices between US & Qatar
Analysis 3: Field Labor Management & Alteration
Conclusion
Analysis 1: Construction of Precast Vs. Cast in Place Concrete

## Slide 12
Ramy Labna | Construction Option
2B + G + M + 7 Mansoura Development
Thermal Properties
Affects users comfort level
Notes disparity of energy efficiency
R-Value Analysis
Performance of system in terms of Heating & Cooling
OUTLINE
Project Background
Analysis 1: Construction Precast Vs. Cast in Place Concrete
  Introduction
  Design
  Manufacturing & Quality
  Delivery & Erection
  Cost Impact
  Schedule Impacts
  Mechanical Breadth
  Conclusions & Recommendations
Analysis 2: Comparison of Construction Practices between US & Qatar
Analysis 3: Field Labor Management & Alteration
Conclusion
Analysis 1: Construction of Precast Vs. Cast in Place Concrete

## Slide 13
Ramy Labna | Construction Option
2B + G + M + 7 Mansoura Development
Winter Condensation Analysis
Summer Condensation Analysis
Addition of Vapor Barrier - $4,024.44
OUTLINE
Project Background
Analysis 1: Construction Precast Vs. Cast in Place Concrete
  Introduction
  Design
  Manufacturing & Quality
  Delivery & Erection
  Cost Impact
  Schedule Impacts
  Mechanical Breadth
  Conclusions & Recommendations
Analysis 2: Comparison of Construction Practices between US & Qatar
Analysis 3: Field Labor Management & Alteration
Conclusion
Analysis 1: Construction of Precast Vs. Cast in Place Concrete

## Slide 14
Ramy Labna | Construction Option
2B + G + M + 7 Mansoura Development
Conclusions
Accelerated Schedule by 9 days
Increase in Superstructure cost by $459,729
Better thermal properties using Precast
Recommendations
Resizing of Mechanical Equipment
Re-sequencing of activities
Use of Precast Concrete Wall Panels
OUTLINE
Project Background
Analysis 1: Construction Precast Vs. Cast in Place Concrete
  Introduction
  Design
  Manufacturing & Quality
  Delivery & Erection
  Cost Impact
  Schedule Impacts
  Mechanical Breadth
  Conclusions & Recommendations
Analysis 2: Comparison of Construction Practices between US & Qatar
Analysis 3: Field Labor Management & Alteration
Conclusion
Analysis 1: Construction of Precast Vs. Cast in Place Concrete

## Slide 15
Ramy Labna | Construction Option
2B + G + M + 7 Mansoura Development
Opportunity Identification
Improvement of construction practices
Improve schedule
Reduce project cost
Improve overall quality
Potential Comparisons
Labor Wages
Safety Programs
Quality Control Programs
OUTLINE
Project Background
Analysis 1: Construction Precast Vs. Cast in Place Concrete
Analysis 2: Comparison of Construction Practices between US & Qatar
  Introduction
  Common Construction Practices in Qatar
  Case Study: HHD Project (Penn State)
  Comparison of Labor Wages
  Comparison of Safety Programs
  Comparison of Quality Control Programs
  Conclusions & Recommendations
Analysis 3: Field Labor Management & Alteration
Conclusion
Analysis 2: Comparison of Construction Practices

## Slide 16
Ramy Labna | Construction Option
2B + G + M + 7 Mansoura Development
Cast in Place Construction
Cheaper
Material readily available
Material/Resource Availability
Shipped from neighboring countries
No natural resources
Special material delivery can be timely process
OUTLINE
Project Background
Analysis 1: Construction Precast Vs. Cast in Place Concrete
Analysis 2: Comparison of Construction Practices between US & Qatar
  Introduction
  Common Construction Practices in Qatar
  Case Study: HHD Project (Penn State)
  Comparison of Labor Wages
  Comparison of Safety Programs
  Comparison of Quality Control Programs
  Conclusions & Recommendations
Analysis 3: Field Labor Management & Alteration
Conclusion
Analysis 2: Comparison of Construction Practices
Photo Courtesy of www.allsortsconcrete.com
Photo Courtesy of Google Maps

## Slide 17
Ramy Labna | Construction Option
2B + G + M + 7 Mansoura Development
Human Health Development (HHD) Project
Academic/Research building
93,000 SF of new construction
Anticipated completion by Spring 2015
Multiple Prime Contract
OUTLINE
Project Background
Analysis 1: Construction Precast Vs. Cast in Place Concrete
Analysis 2: Comparison of Construction Practices between US & Qatar
  Introduction
  Common Construction Practices in Qatar
  Case Study: HHD Project (Penn State)
  Comparison of Labor Wages
  Comparison of Safety Programs
  Comparison of Quality Control Programs
  Conclusions & Recommendations
Analysis 3: Field Labor Management & Alteration
Conclusion
Analysis 2: Comparison of Construction Practices
Photo Courtesy of www.opp.psu.edu

## Slide 18
Ramy Labna | Construction Option
2B + G + M + 7 Mansoura Development
Mansoura Development
No minimum wage rate
Free medical service
Unskilled workers – negative impact to project
OUTLINE
Project Background
Analysis 1: Construction Precast Vs. Cast in Place Concrete
Analysis 2: Comparison of Construction Practices between US & Qatar
  Introduction
  Common Construction Practices in Qatar
  Case Study: HHD Project (Penn State)
  Comparison of Labor Wages
  Comparison of Safety Programs
  Comparison of Quality Control Programs
  Conclusions & Recommendations
Analysis 3: Field Labor Management & Alteration
Conclusion
HHD Project
State funded job
State prevailing wage rate
Analysis 2: Comparison of Construction Practices
Notes: As you can Qatar is much more cheaper due to having no minimum wage, free medical service and large availability of unskilled workers. This however can negatively affect the jobsite due to the workers lack of knowledge.
In comparison to the US which is ___% more

## Slide 19
Ramy Labna | Construction Option
2B + G + M + 7 Mansoura Development
Mansoura Development
No safety administration (like OSHA) in Qatar
Abide by company own Health & Safety Policy
4 Step safety program:
  Make regular job site inspections
  Enforce use of safety equipment
  Follow safety procedures
  Provide on-going safety training
Suspension of pay if rules not followed
8 recordable injuries as of yet
OUTLINE
Project Background
Analysis 1: Construction Precast Vs. Cast in Place Concrete
Analysis 2: Comparison of Construction Practices between US & Qatar
  Introduction
  Common Construction Practices in Qatar
  Case Study: HHD Project (Penn State)
  Comparison of Labor Wages
  Comparison of Safety Programs
  Comparison of Quality Control Programs
  Conclusions & Recommendations
Analysis 3: Field Labor Management & Alteration
Conclusion
HHD Project
All contractors have OSHA 30 – Safety Course
Daily Meetings to highlight safety issues
Safety toolbox topics meeting – Once a week
Zero Recordable accidents
Analysis 2: Comparison of Construction Practices
Notes: US prove to have much stricter safety standards than Qatar, which is why HHD has 0 recordable accidents compared to Mansoura's 8.
Qatar does not have a safety administration such as OSHA this can result in lack of safety in the actual jobsite, resulting in extra costs and schedule delays.

## Slide 20
Ramy Labna | Construction Option
2B + G + M + 7 Mansoura Development
Mansoura Development
No actual program followed
Engineer on site check current work
Lifetime of Building – 50-70 years
OUTLINE
Project Background
Analysis 1: Construction Precast Vs. Cast in Place Concrete
Analysis 2: Comparison of Construction Practices between US & Qatar
  Introduction
  Common Construction Practices in Qatar
  Case Study: HHD Project (Penn State)
  Comparison of Labor Wages
  Comparison of Safety Programs
  Comparison of Quality Control Programs
  Conclusions & Recommendations
Analysis 3: Field Labor Management & Alteration
Conclusion
HHD Project
Three-Phase Control System:
  Preparatory Phase
  Initial Phase
  Follow-Up Phase
Lifetime of Building – 100 years
Analysis 2: Comparison of Construction Practices
Notes: Rather than have a three phase QC program much like the HHD project, the Mansoura development they have an engineer on site to check the work, which isnt very proficient.
Not having a QC program can negatively impact the quality of the building and result in many problems along the future.

## Slide 21
Ramy Labna | Construction Option
2B + G + M + 7 Mansoura Development
Recommendations
Acquire/Train more experienced workers
OSHA trained personnel on site
Regular unscheduled site safety inspections
Implement Quality Control program similar to HHD Project
OUTLINE
Project Background
Analysis 1: Construction Precast Vs. Cast in Place Concrete
Analysis 2: Comparison of Construction Practices between US & Qatar
  Introduction
  Common Construction Practices in Qatar
  Case Study: HHD Project (Penn State)
  Comparison of Labor Wages
  Comparison of Safety Programs
  Comparison of Quality Control Programs
  Conclusions & Recommendations
Analysis 3: Field Labor Management & Alteration
Conclusion
Conclusions
Potential to cut down on project costs
Potential delivery of project on or before time
Huge potential to improve safety of construction site
Analysis 2: Comparison of Construction Practices

## Slide 22
Ramy Labna | Construction Option
2B + G + M + 7 Mansoura Development
Potential Solutions
Re-evaluate/Re-sequence activities in schedule
Increasing labor force pre-summer months
SIPS implementation of superstructure
Man Power Loaded schedule
OUTLINE
Project Background
Analysis 1: Construction Precast Vs. Cast in Place Concrete
Analysis 2: Comparison of Construction Practices between US & Qatar
Analysis 3: Field Labor Management & Alteration
  Introduction
  Evaluate Current Schedule
  Labor Increase
  SIPS Analysis
  Man Power Loaded Schedule
  Conclusions & Recommendations
Conclusion
Problem Identification
Immense heat of summer months (Over 122 degrees)
Government halts construction during the day
Delays in schedule
Analysis 3: Field Labor Management & Alteration
Notes: Consists of finding ways to by pass the halt of construction which is implemented during the summer months where temp can rise over 122 degrees.

## Slide 23
Ramy Labna | Construction Option
2B + G + M + 7 Mansoura Development
Possible Solutions
Completion of Superstructure before July, 2014
Phasing construction by trade
Increase man power for superstructure completion
OUTLINE
Project Background
Analysis 1: Construction Precast Vs. Cast in Place Concrete
Analysis 2: Comparison of Construction Practices between US & Qatar
Analysis 3: Field Labor Management & Alteration
  Introduction
  Evaluate Current Schedule
  Labor Increase
  SIPS Analysis
  Man Power Loaded Schedule
  Conclusions & Recommendations
Conclusion
Current Schedule
Superstructure construction goes through summer
Floor by floor phasing
*See Appendix E for current project schedule
Analysis 3: Field Labor Management & Alteration

## Slide 24
Ramy Labna | Construction Option
2B + G + M + 7 Mansoura Development
OUTLINE
Project Background
Analysis 1: Construction Precast Vs. Cast in Place Concrete
Analysis 2: Comparison of Construction Practices between US & Qatar
Analysis 3: Field Labor Management & Alteration
  Introduction
  Evaluate Current Schedule
  Labor Increase
  SIPS Analysis
  Man Power Loaded Schedule
  Conclusions & Recommendations
Conclusion
Cost Analysis
$1.37 – Labor Cost
13 extra laborers added
Overall reduction: $22,906.40
Analysis 3: Field Labor Management & Alteration

## Slide 25
Ramy Labna | Construction Option
2B + G + M + 7 Mansoura Development
OUTLINE
Project Background
Analysis 1: Construction Precast Vs. Cast in Place Concrete
Analysis 2: Comparison of Construction Practices between US & Qatar
Analysis 3: Field Labor Management & Alteration
  Introduction
  Evaluate Current Schedule
  Labor Increase
  SIPS Analysis
  Man Power Loaded Schedule
  Conclusions & Recommendations
Conclusion
SIPS
Implementation on superstructure (Concrete Casting)
5 activities per floor
Construction start: 26th August, 2013
Ground & Mezzanine floors – 9900 GSF
Floors 1-7 – 7900 GSF
Analysis 3: Field Labor Management & Alteration

## Slide 26
Ramy Labna | Construction Option
2B + G + M + 7 Mansoura Development
OUTLINE
Project Background
Analysis 1: Construction Precast Vs. Cast in Place Concrete
Analysis 2: Comparison of Construction Practices between US & Qatar
Analysis 3: Field Labor Management & Alteration
  Introduction
  Evaluate Current Schedule
  Labor Increase
  SIPS Analysis
  Man Power Loaded Schedule
  Conclusions & Recommendations
Conclusion
Schedule Reduction
New finish date: 30th May, 2014
120 Days ahead of schedule
  27th Sept, 2014
*See Appendix L for Full version of SIPS Schedule
Analysis 3: Field Labor Management & Alteration

## Slide 27
Ramy Labna | Construction Option
2B + G + M + 7 Mansoura Development
OUTLINE
Project Background
Analysis 1: Construction Precast Vs. Cast in Place Concrete
Analysis 2: Comparison of Construction Practices between US & Qatar
Analysis 3: Field Labor Management & Alteration
  Introduction
  Evaluate Current Schedule
  Labor Increase
  SIPS Analysis
  Man Power Loaded Schedule
  Conclusions & Recommendations
Conclusion
Man Power Loaded Schedule
Based on SIPS Schedule
Ensures SIPS feasibility
Over-allocation of Laborers
Analysis 3: Field Labor Management & Alteration

## Slide 28
Ramy Labna | Construction Option
2B + G + M + 7 Mansoura Development
Recommendations
Implement SIPS over original schedule
Further consideration to apply SIPS on all trades
OUTLINE
Project Background
Analysis 1: Construction Precast Vs. Cast in Place Concrete
Analysis 2: Comparison of Construction Practices between US & Qatar
Analysis 3: Field Labor Management & Alteration
  Introduction
  Evaluate Current Schedule
  Labor Increase
  SIPS Analysis
  Man Power Loaded Schedule
  Conclusions & Recommendations
Conclusion
Conclusions
Superstructure schedule reduced by 120 days
By-pass halt in construction
Promotion of safer site
Analysis 3: Field Labor Management & Alteration

## Slide 29
Conclusion
Ramy Labna | Construction Option
2B + G + M + 7 Mansoura Development
OUTLINE
Project Background
Analysis 1: Construction Precast Vs. Cast in Place Concrete
Analysis 2: Comparison of Construction Practices between US & Qatar
Analysis 3: Field Labor Management & Alteration
Conclusion
Conclusion
Schedule acceleration primary concern for owner
Potential in resizing of Mechanical equipment
Potential schedule accelerations through re-sequencing of activities for Precast
Analysis 1 | Precast Vs. Cast in Place
Accelerates schedule by 9 days
Increases cost by $459,729
Analysis 2 | Comparison of Construction Practices between US & Qatar
  Increase in skilled workers
  Introduction to OSHA personnel
  Implementation of Quality Control Program
Analysis 3 | Field Labor Management & Alteration
Decreases labor cost by $22,906.40
Accelerates superstructure schedule by 120 days

## Slide 30
Acknowledgements
Ramy Labna | Construction Option
2B + G + M + 7 Mansoura Development
OUTLINE
Project Background
Analysis 1: Construction Precast Vs. Cast in Place Concrete
Analysis 2: Comparison of Construction Practices between US & Qatar
Analysis 3: Field Labor Management & Alteration
Conclusion
THANKS!
Special Thanks
Petra Design – Mahmoud El-Salti
Commitment Construction Project Team
John Bechtel
My Family & Friends
Academic Acknowledgements
Prof. Ray Sowers – CM Faculty Advisor
Dr. Craig Dubler
Dr. Robert Leicht
Dr. John Messner
Penn State AE Faculty
Industry Acknowledgements