## Slide 1: The Housing and Food Service Warehouse and Bakery Expansion
Penn State AE
Senior Capstone Project
Joseph Rutt
Construction Option
Advisor: anumba
April 13th, 2016

## Slide 2
`
Joseph Rutt│ Construction Option
The HFS Warehouse and Bakery
Addition & Renovation
April 13, 2016
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Rooftop Solar Panels
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: SIPS Analysis
IV. Analysis #2: BIM Utilization
V. Analysis #3: Indoor Air Quality
VI. Analysis #4: LEED Certification
VII. Final Recommendations
VIII. Acknowledgements
Introduction
Analysis 3 │Indoor Air Quality
Project Overview
Analysis 1 │ SIPS Analysis
Analysis 2 │BIM Utilization
Googlemaps.com
The Pennsylvania State University BIM Execution Planning Guide
Analysis 4 │LEED Certification
LEED USGBC
ASHRAE

## Slide 3
Joseph Rutt│ Construction Option
The HFS Warehouse and Bakery
Addition & Renovation
April 13, 2016
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
  Project Background
III. Analysis #1: SIPS Analysis
IV. Analysis #2: BIM Utilization
V. Analysis #3: Indoor Air Quality
VI. Analysis #4: LEED Certification
VII. Final Recommendations
VIII. Acknowledgements
Project Background
Building Information:
  Original Size 94,000SF
  44,500SF renovation of existing building
  25,000SF Warehouse addition
  Approximately $13 Million Project
  March 2015 – March 2016
  Design Build
Kinsley Construction
Notes: 4 classroom school in 1870
Addition in 1950s to k-8
Closed in 2008 due to high cost of hvac

## Slide 4
Joseph Rutt│ Construction Option
The HFS Warehouse and Bakery
Addition & Renovation
April 13, 2016
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: SIPS Analysis
  Problem Identification
  Schedule Matrix
  Feasibility Analysis
  Recommendation
IV. Analysis #2: BIM Utilization
V. Analysis #3: Indoor Air Quality
VI. Analysis #4: LEED Certification
VII. Final Recommendations
VIII. Acknowledgements
Analysis #1
SIPS Analysis

## Slide 5
SIPS Schedule
Joseph Rutt│ Construction Option
The HFS Warehouse and Bakery
Addition & Renovation
April 13, 2016
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: SIPS Analysis
  Problem Identification
  Schedule Matrix
  Feasibility Analysis
  Recommendation
IV. Analysis #2: BIM Utilization
V. Analysis #3: Indoor Air Quality
VI. Analysis #4: LEED Certification
VII. Final Recommendations
VIII. Acknowledgements
Proposed Solution:
  SIPS Analysis of office renovation
Research Goal:
  Decrease time to renovate offices
  Schedule Matrix
Problem Identification:
  Cannot occupy office space during renovations
  Renovations during two different phases
Notes: 7 apts for 30% below medium income
20 for 50%
21 for 60%
5 for homeless

## Slide 6
Schedule Matrix
Joseph Rutt│ Construction Option
The HFS Warehouse and Bakery
Addition & Renovation
April 13, 2016
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: SIPS Analysis
  Problem Identification
  Schedule Matrix
  Feasibility Analysis
  Recommendation
IV. Analysis #2: BIM Utilization
V. Analysis #3: Indoor Air Quality
VI. Analysis #4: LEED Certification
VII. Final Recommendations
VIII. Acknowledgements

## Slide 7
Joseph Rutt│ Construction Option
The HFS Warehouse and Bakery
Addition & Renovation
April 13, 2016
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: SIPS Analysis
  Problem Identification
  Schedule Matrix
  Feasibility Analysis
  Recommendation
IV. Analysis #2: BIM Utilization
V. Analysis #3: Indoor Air Quality
VI. Analysis #4: LEED Certification
VII. Final Recommendations
VIII. Acknowledgements
Feasibility Analysis
Schedule:
  About 5 weeks to completely finish one room
  Total of 10 weeks and 2 days to complete
  Finished 5 weeks ahead of the 16 week schedule
  Renovation of both office space during Phase 3
Provided by Kinsley Construction
Provided by Kinsley Construction

## Slide 8
Recommendations
Joseph Rutt│ Construction Option
The HFS Warehouse and Bakery
Addition & Renovation
April 13, 2016
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: SIPS Analysis
  Problem Identification
  Schedule Matrix
  Feasibility Analysis
  Recommendation
IV. Analysis #2: BIM Utilization
V. Analysis #3: Indoor Air Quality
VI. Analysis #4: LEED Certification
VII. Final Recommendations
VIII. Acknowledgements
Recommendation:
  Implement the SIPS Analysis for office renovations
Potential Value Added:
  Occupant Satisfaction
  Organized trades
  Decreased schedule
Schedule Impact:
  Decreased schedule by 37 Days
Manpower
25
29
Schedule
16 Weeks
11 Weeks

## Slide 9
Joseph Rutt│ Construction Option
The HFS Warehouse and Bakery
Addition & Renovation
April 13, 2016
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: SIPS Analysis
IV. Analysis #2: BIM Utilization
  Problem Identification
  Feasibility Analysis
  Recommendation
V. Analysis #3: Indoor Air Quality
VI. Analysis #4: LEED Certification
VII. Final Recommendations
VIII. Acknowledgements
Analysis #2
BIM Utilization

## Slide 10
Joseph Rutt│ Construction Option
The HFS Warehouse and Bakery
Addition & Renovation
April 13, 2016
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: SIPS Analysis
IV. Analysis #2: BIM Utilization
  Problem Identification
  Feasibility Analysis
  Recommendation
V. Analysis #3: Indoor Air Quality
VI. Analysis #4: LEED Certification
VII. Final Recommendations
VIII. Acknowledgements
BIM Utilization
Proposed Solution:
  3D and 4D coordination
Potential Outcomes:
  Cost of creating 3D and 4D model is too high
    outweighs the costs saved from the use of BIM.
  Amount of time saved by limiting RFI’s is substantial and therefore BIM should be utilized.
  Amount of time added by the creation of the 3D and 4D model is more than the time saved.
Problem Identification:
  BIM was not used on this project
  Many RFI’s and ASI’s
  Large contingency held

## Slide 11
Joseph Rutt│ Construction Option
The HFS Warehouse and Bakery
Addition & Renovation
April 13, 2016
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: SIPS Analysis
IV. Analysis #2: BIM Utilization
  Problem Identification
  Feasibility Analysis
  Recommendation
V. Analysis #3: Indoor Air Quality
VI. Analysis #4: LEED Certification
VII. Final Recommendations
VIII. Acknowledgements
Feasibility Analysis
Tasks:
  Create a 3D model of existing building
  Utilize clash detection
  4D model of warehouse bay and storage
Predicted Outcome
  3D model relieves issues with as-built drawings
  Eliminate RFI’s and ASI’s
  4D model sequence phases and create maps for construction site

## Slide 12
Joseph Rutt│ Construction Option
The HFS Warehouse and Bakery
Addition & Renovation
April 13, 2016
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: SIPS Analysis
IV. Analysis #2: BIM Utilization
  Problem Identification
  Feasibility Analysis
  Recommendation
V. Analysis #3: Indoor Air Quality
VI. Analysis #4: LEED Certification
VII. Final Recommendations
VIII. Acknowledgements
Recommendation
Recommendation:
  BIM is recommended for this project
  Reduces problems with as-built model
  Reduces RFI’s and ASI’s

## Slide 13
Joseph Rutt│ Construction Option
The HFS Warehouse and Bakery
Addition & Renovation
April 13, 2016
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Analysis #3
Indoor Air Quality
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: SIPS Analysis
IV. Analysis #2: BIM Utilization
V. Analysis #3: Indoor Air Quality
  Problem Identification
  Feasibility Analysis
  Recommendation
  Mechanical Breadth
VI. Analysis #4: LEED Certification
VII. Final Recommendations
VIII. Acknowledgements

## Slide 14
Joseph Rutt│ Construction Option
The HFS Warehouse and Bakery
Addition & Renovation
April 13, 2016
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: SIPS Analysis
IV. Analysis #2: BIM Utilization
V. Analysis #3: Indoor Air Quality
  Problem Identification
  Feasibility Analysis
  Recommendation
  Mechanical Breadth
VI. Analysis #4: LEED Certification
VII. Final Recommendations
VIII. Acknowledgements
Indoor Air Quality
Problem Identification:
  Poor air quality can effect occupant’s health
Proposed Solution:
  Increase the quality of air for the occupants
Research Goal:
  Find breathing zone outdoor airflow
  Air distribution effectiveness
  Zone outdoor airflow
ASHRAE Standard 62.1 - 2013
Unit H – Office Space

## Slide 15
Joseph Rutt│ Construction Option
The HFS Warehouse and Bakery
Addition & Renovation
April 13, 2016
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Indoor Air Quality
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: SIPS Analysis
IV. Analysis #2: BIM Utilization
V. Analysis #3: Indoor Air Quality
  Problem Identification
  Feasibility Analysis
  Recommendation
  Mechanical Breadth
VI. Analysis #4: LEED Certification
VII. Final Recommendations
VIII. Acknowledgements
Calculating Breathing Zone Outdoor Air Flow (Vbz):
Where
Zone floor area, the net occupiable floor area of the ventilation zone, ft2
Zone population, the number of people in the ventilation zone during typical usage
Outdoor airflow rate required per person as determined from Table 6.2.2.1
Outdoor airflow rate required per unit area as determined from Table 6.2.2.

## Slide 16
Joseph Rutt│ Construction Option
The HFS Warehouse and Bakery
Addition & Renovation
April 13, 2016
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Indoor Air Quality
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: SIPS Analysis
IV. Analysis #2: BIM Utilization
V. Analysis #3: Indoor Air Quality
  Problem Identification
  Feasibility Analysis
  Recommendation
  Mechanical Breadth
VI. Analysis #4: LEED Certification
VII. Final Recommendations
VIII. Acknowledgements
Determine Zone Air Distribution Effectiveness (Ez):
Ez is determined using Table 6.2.2.2 in Standard 62.1

## Slide 17
Joseph Rutt│ Construction Option
The HFS Warehouse and Bakery
Addition & Renovation
April 13, 2016
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Indoor Air Quality
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: SIPS Analysis
IV. Analysis #2: BIM Utilization
V. Analysis #3: Indoor Air Quality
  Problem Identification
  Feasibility Analysis
  Recommendation
  Mechanical Breadth
VI. Analysis #4: LEED Certification
VII. Final Recommendations
VIII. Acknowledgements
Calculating Zone Outdoor Airflow (Voz):

## Slide 18
Joseph Rutt│ Construction Option
The HFS Warehouse and Bakery
Addition & Renovation
April 13, 2016
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Recommendation
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: SIPS Analysis
IV. Analysis #2: BIM Utilization
V. Analysis #3: Indoor Air Quality
  Problem Identification
  Feasibility Analysis
  Recommendation
  Mechanical Breadth
VI. Analysis #4: LEED Certification
VII. Final Recommendations
VIII. Acknowledgements
Conclusion:
Uncorrected Outdoor Air Intake: 295 CFM
Outdoor Air Intake Flow (+30%): 383 CFM
The mechanical system requires an additional 383 CFM of outdoor air to reach the requirement for the LEED Credit.

## Slide 19
Joseph Rutt│ Construction Option
The HFS Warehouse and Bakery
Addition & Renovation
April 13, 2016
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Mechanical Breadth
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: SIPS Analysis
IV. Analysis #2: BIM Utilization
V. Analysis #3: Indoor Air Quality
  Problem Identification
  Feasibility Analysis
  Recommendation
  Mechanical Breadth
VI. Analysis #4: LEED Certification
VII. Final Recommendations
VIII. Acknowledgements
Determining the cooling load for Unit H:
The cooling load the design parameters for Summer Design Cooling are:
90.1 Dry bulb
74.5 Wet bulb
Relative humidity of 60%
Indoor temperature of 75° F.
𝑞̇(𝑏𝑡𝑢) = 4.5 𝐶𝐹𝑀 𝛥ℎ
𝑞̇(𝑏𝑡𝑢) = 4.5 (383) (38.8 − 30.4)
𝑞̇(𝑏𝑡𝑢) = 14,477.4 𝑏𝑡𝑢ℎ = 𝟏𝟒. 𝟓 𝒎𝒃𝒉

## Slide 20
Joseph Rutt│ Construction Option
The HFS Warehouse and Bakery
Addition & Renovation
April 13, 2016
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Mechanical Breadth
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: SIPS Analysis
IV. Analysis #2: BIM Utilization
V. Analysis #3: Indoor Air Quality
  Problem Identification
  Feasibility Analysis
  Recommendation
  Mechanical Breadth
VI. Analysis #4: LEED Certification
VII. Final Recommendations
VIII. Acknowledgements
Determine the heating load for Unit H:
From the Psychrometric Chart:
h1 = 38.8 btu/lbm
h2 = 30.4 btu/lbm
𝑞̇ 𝑠𝑒𝑛𝑠 = 1.08 𝐶𝐹𝑀 𝛥𝑇
𝑞̇ 𝑠𝑒𝑛𝑠 = 1.08 (383) (75 − 15.8)
𝑞̇ 𝑠𝑒𝑛𝑠 = 24,487.5 𝑏𝑡𝑢ℎ = 𝟐𝟒. 𝟓 𝒎𝒃𝒉
The heating load above is added to the current load of 100 mbh for a total of 124.5 mbh load for Unit H

## Slide 21
Joseph Rutt│ Construction Option
The HFS Warehouse and Bakery
Addition & Renovation
April 13, 2016
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Mechanical Breadth
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: SIPS Analysis
IV. Analysis #2: BIM Utilization
V. Analysis #3: Indoor Air Quality
  Problem Identification
  Feasibility Analysis
  Recommendation
  Mechanical Breadth
VI. Analysis #4: LEED Certification
VII. Final Recommendations
VIII. Acknowledgements
Recommendation:
  100% outdoor air system
  Cost of change is low and may be negligible
  Provides occupants with a higher quality work environment
𝑞̇(𝑏𝑡𝑢) = 14,477.4 𝑏𝑡𝑢ℎ = 𝟏𝟒. 𝟓 𝒎𝒃𝒉
𝑞̇ 𝑠𝑒𝑛𝑠 = 24,487.5 𝑏𝑡𝑢ℎ = 𝟐𝟒. 𝟓 𝒎𝒃𝒉
Total of 124.5 mbh load for Unit H

## Slide 22
Joseph Rutt│ Construction Option
The HFS Warehouse and Bakery
Addition & Renovation
April 13, 2016
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: SIPS Analysis
IV. Analysis #2: BIM Utilization
V. Analysis #3: Indoor Air Quality
VI. Analysis #4: LEED Certification
  Problem Identification
  Feasibility Analysis
  Recommendation
VII. Final Recommendations
VIII. Acknowledgements
Analysis #4
LEED Certification

## Slide 23
Joseph Rutt│ Construction Option
The HFS Warehouse and Bakery
Addition & Renovation
April 13, 2016
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
LEED Certification
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: SIPS Analysis
IV. Analysis #2: BIM Utilization
V. Analysis #3: Indoor Air Quality
VI. Analysis #4: LEED Certification
  Problem Identification
  Feasibility Analysis
  Recommendation
VII. Final Recommendations
VIII. Acknowledgements
Problem Identification:
  No considerations to pursue LEED Certification
  Project is capable of achieving at least 40 points
Proposed Solution:
  Acquire at minimum 40 points to become a LEED Certified building
Research Goal:
  Benefits lifespan of project
  Lower operating costs
  Reduced project waste
  Energy conservation
  Reduced greenhouse gas emissions
  Tax rebates

## Slide 24
Joseph Rutt│ Construction Option
The HFS Warehouse and Bakery
Addition & Renovation
April 13, 2016
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
LEED Certification
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: SIPS Analysis
IV. Analysis #2: BIM Utilization
V. Analysis #3: Indoor Air Quality
VI. Analysis #4: LEED Certification
  Problem Identification
  Feasibility Analysis
  Recommendation
VII. Final Recommendations
VIII. Acknowledgements

## Slide 25
Joseph Rutt│ Construction Option
The HFS Warehouse and Bakery
Addition & Renovation
April 13, 2016
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Recommendation
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: SIPS Analysis
IV. Analysis #2: BIM Utilization
V. Analysis #3: Indoor Air Quality
VI. Analysis #4: LEED Certification
  Problem Identification
  Feasibility Analysis
  Recommendation
VII. Final Recommendations
VIII. Acknowledgements
Recommendation:
  Pursue the lowest LEED Certification with a minimum of 40 points
Components:
  Integrative Process – 1 point
  Location & Transportation – 10 points
  Sustainable Site – 3 points
  Water Efficiency – 5 points
  Energy & Atmosphere – 9 points
  Material & Resources – 2 points
  Indoor Environmental Quality – 9 points
  Innovation – 1 point
  Regional Priority – 2 points
  Total points: 42
  LEED Certified

## Slide 26
Joseph Rutt│ Construction Option
The HFS Warehouse and Bakery
Addition & Renovation
April 13, 2016
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: SIPS Analysis
IV. Analysis #2: BIM Utilization
V. Analysis #3: Indoor Air Quality
VI. Analysis #4: LEED Certification
VII. Final Recommendations
VIII. Acknowledgements
Conclusion
Analysis 1 │ SIPS Analysis
Analysis 2 │BIM Utilization
Analysis 3 │Indoor Air Quality
Analysis 4 │LEED Certification
Implement the SIPS Analysis for office renovations
  Occupant Satisfaction
  Organized trades
  Decreased schedule
BIM is recommended for this project
  Reduces problems with as-built model
  Reduces RFI’s and ASI’s
Implementation of the mechanical system is recommended to achieve the LEED credit
Provided by Kinsley Construction
There are at least 42 possible points for this building, strongly recommend pursuit of LEED Certified Building

## Slide 27
Acknowledgements
Joseph Rutt│ Construction Option
The HFS Warehouse and Bakery
Addition & Renovation
April 13, 2016
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: SIPS Analysis
IV. Analysis #2: BIM Utilization
V. Analysis #3: Indoor Air Quality
VI. Analysis #4: LEED Certification
VII. Final Recommendations
VIII. Acknowledgements
Architectural Engineering Faculty:
Dr. Chimay Anumba (Advisor)
Special Thanks to:
My Family & Friends
Kevin Finke – Kinsley Construction
Justin Osmolinski – Kinsley Construction
PACE Industry Members
Industry Acknowledgements:

## Slide 28
Thank You
Joseph Rutt│ Construction Option
The HFS Warehouse and Bakery
Addition & Renovation
April 13, 2016
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Questions & Comments
Provided by Kinsley Construction