## Slide 1: C-5 Fuel cell facility 167th airlift wing martinsburg, wv
Kyle Goodyear
BAE in Construction Management
Pennsylvania State University
Senior Thesis Presentation
April 12, 2010

## Slide 2: Presentation Outline
Project Background Information
Solar Energy Collection
  Electrical Breadth
Precast Concrete Walls
  Structural Breadth
Hangar Slab Sequence
Design/Build Productivity
Conclusions
Questions and Answers
Special Thanks to:
Kinsley Construction, Inc.
167th Airlift Wing
Penn State AE Faculty

## Slide 3: Project Background
Client: 167th Airlift Wing – WV Air National Guard
Project Background Information
Solar Energy Collection
  Electrical Breadth
Precast Concrete Walls
  Structural Breadth
Hangar Slab Sequence
Design/Build Productivity
Conclusions
Questions and Answers
Presentation Outline
Purpose
  C-5 Galaxy Conversion Project
Site: Martinsburg, WV
  WV Eastern Regional Airport

## Slide 4: Project Background
Project Background Information
Solar Energy Collection
  Electrical Breadth
Precast Concrete Walls
  Structural Breadth
Hangar Slab Sequence
Design/Build Productivity
Conclusions
Questions and Answers
Presentation Outline
Design/Build Contract
  Kinsley Construction – Design/Build Manager
    Holds all subcontracts
  LSC Design – contracted by Kinsley Construction
    Holds all design team subcontracts
  All contracts based on lump sum
167th Airlift Wing
Owner
Kinsley Construction
LSC Design
Design Team
Subcontractors

## Slide 5: Project Background
Cost: $26.8 million
Project Background Information
Solar Energy Collection
  Electrical Breadth
Precast Concrete Walls
  Structural Breadth
Hangar Slab Sequence
Design/Build Productivity
Conclusions
Questions and Answers
Presentation Outline
Schedule
  NTP for design: October 2008
  Office Mobilization: March 2009
  Scheduled Completion: March 2010
  Expected Completion: July 2010 – extensions granted for additions to scope and weather delays

## Slide 6: Breadth Topics
Electrical Breadth Study
  Addition of solar collection system
Project Background Information
Solar Energy Collection
  Electrical Breadth
Precast Concrete Walls
  Structural Breadth
Hangar Slab Sequence
Design/Build Productivity
Conclusions
Questions and Answers
Presentation Outline
Structural Breadth Study
  Design of load-bearing concrete walls in place of masonry

## Slide 7: Solar Energy Collection
Goal of Analysis
  Determine if the installation of Solyndra panels is a positive addition
    Potential energy production
    Building power usage
    Purchase and installation costs
    Payback period
Project Background Information
Solar Energy Collection
  Electrical Breadth
Precast Concrete Walls
  Structural Breadth
Hangar Slab Sequence
Design/Build Productivity
Conclusions
Questions and Answers
Presentation Outline

## Slide 8: Solar Energy Collection
Solyndra, Inc. Panels
  Array of cylinders
  Collects direct, diffuse, and reflected light
    Reflected light gain based on roof material
  Airflow between cylinders
    Reduced wind uplift
    Cooler operating temperatures
Project Background Information
Solar Energy Collection
  Electrical Breadth
Precast Concrete Walls
  Structural Breadth
Hangar Slab Sequence
Design/Build Productivity
Conclusions
Questions and Answers
Presentation Outline

## Slide 9: Electrical Breadth Study
How many Solyndra panels can be installed on the roof?
  Orientation of building
  Dimensions of panels vs. Dimensions of roof
Project Background Information
Solar Energy Collection
    Electrical Breadth
Precast Concrete Walls
  Structural Breadth
Hangar Slab Sequence
Design/Build Productivity
Conclusions
Questions and Answers
Presentation Outline
3 sections of usable roof space on SW side
13 panels lengthwise along slope of roof
78 panels across the roof
1014 panels total

## Slide 10: Electrical Breadth Study
Energy Production Potential
  Power Rating of Solyndra panel
  Monthly insolation values for location
  Max annual output: 274 kWh/panel
  Reflectivity reduction: 88%
  Potential annual output: 241 kWh/panel
  241kWh/panel/year x 1014 panels = 244,374 kWh/year
Project Background Information
Solar Energy Collection
  Electrical Breadth
Precast Concrete Walls
  Structural Breadth
Hangar Slab Sequence
Design/Build Productivity
Conclusions
Questions and Answers
Presentation Outline

## Slide 11: Electrical Breadth Study
Building Energy Usage
  Existing hangar energy usage
  Average office energy usage
  Total Expected Energy Usage = 213,773 kWh/year
Project Background Information
Solar Energy Collection
  Electrical Breadth
Precast Concrete Walls
  Structural Breadth
Hangar Slab Sequence
Design/Build Productivity
Conclusions
Questions and Answers
Presentation Outline
Cost of Installing Solyndra System
  $7 per Watt per panel
  $7/W/panel x 200W x 1014 panels
  $1,419,600 to purchase and install

## Slide 12: Electrical Breadth Study
Payback Period of System
  Cost of electricity: 6.64 cents per kWh in WV
  Expected savings plus sale of electricity
    $0.0664/kWh x 244,374 kWh/year = $16, 226/year
Project Background Information
Solar Energy Collection
  Electrical Breadth
Precast Concrete Walls
  Structural Breadth
Hangar Slab Sequence
Design/Build Productivity
Conclusions
Questions and Answers
Presentation Outline
$1,419,600 / $16,226/year = 87.5 years

## Slide 13: Conclusion and Recommendation
System produces more than building uses
Payback period is extremely long
  Low cost of energy for project location
  More feasible in higher cost region
Project Background Information
Solar Energy Collection
  Electrical Breadth
Precast Concrete Walls
  Structural Breadth
Hangar Slab Sequence
Design/Build Productivity
Conclusions
Questions and Answers
Presentation Outline
Recommendation: Do not install Solyndra system on this project.

## Slide 14: Precast Concrete Walls
Goal of Analysis
  Is precast concrete a better option than CMU for wall construction?
    Exterior façade
    Interior load-bearing walls
Project Background Information
Solar Energy Collection
  Electrical Breadth
Precast Concrete Walls
  Structural Breadth
Hangar Slab Sequence
Design/Build Productivity
Conclusions
Questions and Answers
Presentation Outline

## Slide 15: Precast Concrete Walls
Exterior Façade
  Currently split-face CMU to match existing buildings
  Carbon Cast panels
    Thin-brick technology to match aesthetics
    Produced in controlled conditions
    Higher quality product than masonry
Project Background Information
Solar Energy Collection
  Electrical Breadth
Precast Concrete Walls
  Structural Breadth
Hangar Slab Sequence
Design/Build Productivity
Conclusions
Questions and Answers
Presentation Outline

## Slide 16: Structural Breadth Study
Load Determination
  Dead Load: 21.3 PSF
  Live Load: 20 PSF
Project Background Information
Solar Energy Collection
  Electrical Breadth
Precast Concrete Walls
  Structural Breadth
Hangar Slab Sequence
Design/Build Productivity
Conclusions
Questions and Answers
Presentation Outline
Strength Design Method
  Load combination: 1.2D + 1.6L
  Total Axial Load = 3.22 kips
PD = 1193 lbs
PL = 1120 lbs
PU = 1.2PD + 1.6PL = 3223 lbs = 3.22 kips

## Slide 17: Structural Breadth Study
Using 8” wall thickness
  Bearing Capacity
  Axial Load Capacity
Project Background Information
Solar Energy Collection
  Electrical Breadth
Precast Concrete Walls
  Structural Breadth
Hangar Slab Sequence
Design/Build Productivity
Conclusions
Questions and Answers
Presentation Outline
Minimum Reinforcement
  #4’s @ 18”oc in vertical direction
  #4’s @ 12”oc in horizontal direction

## Slide 18: Structural Breadth Study
Cost Comparison
  Masonry package: $230,011
  Precast package: $506,084
    $38/SF estimate from High Concrete
Project Background Information
Solar Energy Collection
  Electrical Breadth
Precast Concrete Walls
  Structural Breadth
Hangar Slab Sequence
Design/Build Productivity
Conclusions
Questions and Answers
Presentation Outline
Increased Floor Space
  Change from 12” masonry to 8” concrete walls
  117 SF added at $340/SF
  $39,720 worth additional usable space

## Slide 19: Structural Breadth Study
Schedule Comparison
  Masonry package: 25 days on-site
  Precast concrete package: 15 days on-site
  Not on critical path: does not change project schedule
Project Background Information
Solar Energy Collection
  Electrical Breadth
Precast Concrete Walls
  Structural Breadth
Hangar Slab Sequence
Design/Build Productivity
Conclusions
Questions and Answers
Presentation Outline
Productivity Impact
  Fewer workers for precast
  More moving equipment for precast
PRECAST LOGISTICS PLAN
MASONRY LOGISTICS PLAN

## Slide 20: Conclusion and Recommendation
Cost of change is more than double
Overall schedule not reduced
Increased floor space
Higher quality facade
Project Background Information
Solar Energy Collection
  Electrical Breadth
Precast Concrete Walls
  Structural Breadth
Hangar Slab Sequence
Design/Build Productivity
Conclusions
Questions and Answers
Presentation Outline
Recommendation: Use the masonry system as designed instead of precast concrete option.

## Slide 21: Hangar Slab Sequence
Goal of Analysis
  Determine most efficient sequence for concrete placement in hangar area
    Cost
    Duration
    Productivity
Project Background Information
Solar Energy Collection
  Electrical Breadth
Precast Concrete Walls
  Structural Breadth
Hangar Slab Sequence
Design/Build Productivity
Conclusions
Questions and Answers
Presentation Outline

## Slide 22: Hangar Slab Sequence
Industry Survey
  Larger pour size = higher productivity
Project Background Information
Solar Energy Collection
  Electrical Breadth
Precast Concrete Walls
  Structural Breadth
Hangar Slab Sequence
Design/Build Productivity
Conclusions
Questions and Answers
Presentation Outline
3 Sequences
  As-built
  More pours/smaller width
  Less pours/greater width

## Slide 23: Hangar Slab Sequence
Cost and Duration Comparison
  Larger pour width costs less and completed faster
  Smaller pour width costs more and completed slower
Project Background Information
Solar Energy Collection
  Electrical Breadth
Precast Concrete Walls
  Structural Breadth
Hangar Slab Sequence
Design/Build Productivity
Conclusions
Questions and Answers
Presentation Outline
Quality Comparison
  Larger width makes finishing more difficult
  Higher quality with smaller width pours

## Slide 24: Conclusion and Recommendation
Quality vs. Cost
Hangar dimensions
Project Background Information
Solar Energy Collection
  Electrical Breadth
Precast Concrete Walls
  Structural Breadth
Hangar Slab Sequence
Design/Build Productivity
Conclusions
Questions and Answers
Presentation Outline
Recommendation: Employ the slab pour sequence that was chosen by project team.
  Slightly larger pours if dimensions allow

## Slide 25: Design/Build Productivity
Goal of Analysis
  Does design/build construction increase productivity for the management and design team as well as in the field?
Project Background Information
Solar Energy Collection
  Electrical Breadth
Precast Concrete Walls
  Structural Breadth
Hangar Slab Sequence
Design/Build Productivity
Conclusions
Questions and Answers
Presentation Outline

## Slide 26: Design/Build Productivity
Measurements
  Preconstruction activity time
  Paperwork during construction
  Ability to work ahead
Project Background Information
Solar Energy Collection
  Electrical Breadth
Precast Concrete Walls
  Structural Breadth
Hangar Slab Sequence
Design/Build Productivity
Conclusions
Questions and Answers
Presentation Outline

## Slide 27: Design/Build Productivity
Project Background Information
Solar Energy Collection
  Electrical Breadth
Precast Concrete Walls
  Structural Breadth
Hangar Slab Sequence
Design/Build Productivity
Conclusions
Questions and Answers
Presentation Outline
Research Steps
  Project Manager Survey
  Owner Perspective
  Causes of Delays
  Potential Benefits

## Slide 28: Design/Build Productivity
Findings of Research
  Preconstruction time reduced
    Design is better the first time
    Estimating is completed simultaneously
    Subcontractors acquired earlier for design-assist
Project Background Information
Solar Energy Collection
  Electrical Breadth
Precast Concrete Walls
  Structural Breadth
Hangar Slab Sequence
Design/Build Productivity
Conclusions
Questions and Answers
Presentation Outline
  Less paperwork during construction
    RFI’s handled in open meetings
    Change Orders almost completely eliminated
    Submittal process much shorter: subcontractors know the specifications

## Slide 29: Design/Build Productivity
Findings of Research continued
  Able to start activities sooner
    Procurement of long-lead items
    Subcontractors determine means and methods of construction during design phase
    Subcontractors can schedule labor and equipment to reduce chance of delays
Project Background Information
Solar Energy Collection
  Electrical Breadth
Precast Concrete Walls
  Structural Breadth
Hangar Slab Sequence
Design/Build Productivity
Conclusions
Questions and Answers
Presentation Outline
  Success of delivery method depends on the team
    Good contractor with good design can make any method work
    D/B requires background knowledge of project
    Owner must know what they want

## Slide 30: Conclusion
If the design/build team and owner coordinate well, there is potential for higher productivity
Project Background Information
Solar Energy Collection
  Electrical Breadth
Precast Concrete Walls
  Structural Breadth
Hangar Slab Sequence
Design/Build Productivity
Conclusions
Questions and Answers
Presentation Outline

## Slide 31: Conclusions
Project Background Information
Solar Energy Collection
  Electrical Breadth
Precast Concrete Walls
  Structural Breadth
Hangar Slab Sequence
Design/Build Productivity
Conclusions
Questions and Answers
Presentation Outline
Project Team made good decisions in selection of systems and design methods
For other projects, proposed changes may be more beneficial
Use of Design/Build delivery should continue to be implemented at greater levels

## Slide 32: QUESTIONS?
Project Background Information
Solar Energy Collection
  Electrical Breadth
Precast Concrete Walls
  Structural Breadth
Hangar Slab Sequence
Design/Build Productivity
Conclusions
Questions and Answers
Presentation Outline