## Slide 1
Research Facility Core and Shell (RFCS)
Presented by Tim Maffett on April 8th, 2013
Notes: Personal Introduction: Name, Construction Management, Plans for after Graduation

## Slide 2
Research Facility Core and Shell (RFCS)
Presented by Tim Maffett on April 8th, 2013
| Introduction
Introduction | Presentation Overview
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks

## Slide 3
Name | Research Facility Core and Shell (RFCS)
Location | Southern California
Building Use | Research Facility with Office Space
Owner | Faction
Architect | Dowler-Gruman Architects
General Contractor | DPR Construction
| Introduction
Introduction | Building Statistics
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks

## Slide 4
Name | Research Facility Core and Shell (RFCS)
Project Delivery Method | Design-Bid-Build
Contract Type | GMP
Size | 130,000 SF
Cost | $20,000,000
Schedule | 18 Months
| Introduction
Introduction | Building Statistics
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks

## Slide 5
Design Goal
| Introduction
Introduction | Design Goal
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Increase value through innovative and efficient construction.

## Slide 6
| Introduction
Prefabricated Exterior Panels | Overview
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Prefabricated Exterior Wall Panels

## Slide 7
| Introduction
Prefabricated Exterior Panels | Problem Identification
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Existing System
Stick-built metal stud wall with sheathing and masonry veneer
Critical Path item for 24 weeks (1/3 of total schedule)
Created congestion on site
$1,507,959 to complete
Typical Wall Section

## Slide 8
| Introduction
Prefabricated Exterior Panels | Solution
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Proposed Solution?
Prefabricate exterior wall as panel modules.

## Slide 9
| Introduction
Prefabricated Exterior Panels | Alternative #1
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Section of C-CAPP System
C-CAPP Prefabricated Panel System
Architectural, lightweight, precast concrete panel system
2” thick concrete skin attached to a steel frame
Durable, lightweight, closest match to existing facade
Produced by Clark Pacific
Notes: Chosen based on industry references. Prefabricated off-site and brought in

## Slide 10
| Introduction
Prefabricated Exterior Panels | Alternative #1
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Results
Total Cost of C-CAPP System | $1,115,000
Critical Path Duration | 7 Weeks
12’ x 22’ Typical Module for C-CAPP System
Quote on C-CAPP Prefabricated Panel System |  |  | 
Cost Breakdown ($) |  | Schedule (Duration) | 
Base Budget | $907,500 | Preliminary | Variable
Staining Panels | $99,500 |  | 
Preweld Connections to Steel Structure | $75,000 | Layout and Preweld | 3 weeks
Caulking | $33,000 | Hanging Panels | 1 week
----------------------------------------------- | -------------- | Final Aligning and Welding | 3 weeks
Total Cost of System | $1,115,000 | Total Duration on site | 7 weeks
Notes: Schedule and Cost quote given by business development manager at Clark Pacific

## Slide 11
| Introduction
Prefabricated Exterior Panels | Alternative #2
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
On-Site Partial Panel Prefabrication
Panel Prefabrication at Hospital in Temecula, CA

## Slide 12
| Introduction
Prefabricated Exterior Panels | Alternative #2
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Results
Total Cost of Partially Prefabricated System | $1,502,007
Critical Path Duration | 21 Weeks

## Slide 13
| Introduction
Prefabricated Exterior Panels | Chosen Alternative
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Chosen Alternative
On-Site Partial Panel Prefabrication
Architectural Properties | Aesthetic Match
Planning | Later in Process
Owner Hesitance| Less Anxiety
Cost | Decrease
Schedule | Decrease
Safety| Increase

## Slide 14
| Introduction
Prefabricated Exterior Panels | System Comparison
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
On-Site Partial Panel Prefabrication vs. Stick-built Wall Construction
Partially Prefabricated Panel Alternative vs. Original Stick Built Design |  | 
Description | Partially Prefabricated Panels | Original Stick-Built Design
Overall Cost | $1,502,007 | $1,507,960
Difference +/- | $5,953 Savings | 
Overall Schedule | 21 Weeks | 24 Weeks
Difference +/- | 3 Week Schedule Reduction | 
Cost Savings | $5,953
Schedule Reduction | 3 Weeks
Notes: Decrease in scaffolding costs, reduction in schedule, increase in crane costs

## Slide 15
| Introduction
Prefabricated Exterior Panels | Recommendation
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Implement Partially Prefabricated Wall Panel Strategy as opposed to original stick-built construction
Recommendation
Notes: Save cost and reduce schedule allowing the building to be in use sooner thus generating profits sooner. Creates buffer period in schedule

## Slide 16
| Introduction
Detailed Sequencing | Overview
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Detailed Sequencing of Exterior Wall Panels

## Slide 17
| Introduction
Detailed Sequencing | Constructability Concerns
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Constructability Concerns
Where on site will we build panels?
How do we modularize most efficiently?
How do we plan necessary supplies?
How do we schedule this activity?
In what order will the panels be erected?
How do we educate and create a safe environment?
?
Notes: How do we modularize this building most efficiently? How do we plan for the necessary supplies? How do we schedule this activity? How will it be erected?

## Slide 18
| Introduction
Detailed Sequencing | Prefabrication Tent & Staging
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Prefabrication Tent and Staging
Location | On-site and near building
Description | Metal framed tent to provide cover during construction
Staging | Tarp to cover and protect completed panels

## Slide 19
| Introduction
Detailed Sequencing | Module Breakdown
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Module Types
Panel Module Take-Off | 
Description | Amount
Module Type #1 | 28
Module Type #2 | 21
Module Type #3 | 3
Total | 52 Panels
Module Breakdown

## Slide 20
| Introduction
Detailed Sequencing | Building the Panel
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Building the Panel
Step 1: Build Outer Framing
Step 2: Frame Full Length Studs
Step 3: Frame Window Opening 1
Step 4: Frame Window Opening 2
Step 5: Frame Window Opening 3
Step 6: Install Window Supports
Step 7: Sheath Panel
Notes: Helped to quantify the materials and duration of the activity

## Slide 21
| Introduction
Detailed Sequencing | Erection Sequence
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Erection Sequence
South Façade Phase A and B
East Façade Phase C
Sequencing

## Slide 22
| Introduction
Detailed Sequencing | Erection Sequence
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Erection Sequence
North Façade Phase D
West Façade Phase E
Sequencing

## Slide 23
| Introduction
Detailed Sequencing | Benefits and Outcomes
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Benefits and Outcomes
Thorough planning
Accurate material, schedule, and cost estimate
Provides training and management tool
Increased efficiency
Increased safety
Protection against crane sitting on site stagnantly

## Slide 24
| Introduction
Sizing of Rigging Beam | Overview
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Sizing of Rigging Beam

## Slide 25
| Introduction
Sizing of Rigging Beam | Outcome
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Outcome of Structural Breadth
Rigging Beam at Hospital in Temecula, CA
Results of Structural Calculations on Steel Beam in Rigging | 
Description | Value
Dead Weight of Panel | 1580 lb.
Maximum Shear | .790 kip
Maximum Moment | .790 kip-ft.
Rigging Beam Necessary for RFCS | W 8x10
Notes: Sized the beam for the largest forces it would see >> used largest panel for calculations

## Slide 26
| Introduction
Solar Panel Installation | Overview
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Solar Panel Installation at Roof Level

## Slide 27
| Introduction
Solar Panel Installation | Problem Identification
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Requests of the Owner
Achieve LEED Gold Certification
Develop solution without simply point chasing
Improve sustainability
Take advantage of Southern California location
Notes: The project team finds out that they are only a few leed credits away from leed gold. Owner decides it might be worth it if appropriate solution is found.

## Slide 28
| Introduction
Solar Panel Installation | Problem Identification
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Proposed Solution?
Investigate implementation of solar panels on roof.

## Slide 29
| Introduction
Solar Panel Installation | Background Information
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Background Information
Roof made of EPDM membrane, rigid insulation, concrete on metal deck
30,250 SF total roof space (125’ x 242’)
9,900 SF centrally located mechanical space (50’ x 198’)
Mechanical space surrounded by 13 ½’ screen wall
Parapet walls 4’
Photo of Rooftop and Plan View of Rooftop
Notes: The project team finds out that they are only a few leed credits away from leed gold. Owner decides it might be worth it if appropriate solution is found.

## Slide 30
| Introduction
Solar Panel Installation | Design Decisions
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Design Decisions
Grid Direct System (DC to AC Power) connected to utility
Inverter placed at east side of the rooftop mechanical zone
Circuit breakers and utility tie-in placed in basement main electrical room
Rooftop
Basement

## Slide 31
| Introduction
Solar Panel Installation | Shading Analysis
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Shading Analysis

## Slide 32
| Introduction
Solar Panel Installation | Shading Analysis
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Shading Analysis

## Slide 33
| Introduction
Solar Panel Installation | System Design
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Module, Inverter, and Racking
Criteria | Best efficiency for cost
Efficiency | 15.3%
Maximum Power | 250 W
Size | 3 ¼’ x 5 ½’
Module: Trinamount TSM-250PA05
Inverter: Sunny Tower by SMA
Criteria | Large, single inverter
Efficiency | 96%
Maximum Load | 42 kWdc power
Racking: Trinamount III
Type | Ballasted racking system
Tilt | 11 degrees
Notes: Key notes: Module picked based on best cost for highest efficiency, inverter picked in order to have one central connection point, ballast racking system chosen to reduce roof penetrations and ease installation. 11 degree tilt in order to fit more panels

## Slide 34
| Introduction
Solar Panel Installation | System Design
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Array Placement
Array Layout
Module Amount | 143 modules
System Max Output | 36 kWdc

## Slide 35
| Introduction
Solar Panel Installation | System Design
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Electrical Sizing and Design
Conductor Sizing Summary |  | 
Connection | Description | Legend
Panels String to Inverter (DC Side) |  | 
Conductor Sizing (One Way) | (5) #12 AWG’s per PV Output Circuit String | 
Maximum Run Length | 187 ft. one way for 2% Voltage Drop | 
Inverter to Circuit Breakers (AC Side) |  | 
Conductor Sizing (One Way) | (3) #4 AWG conductors per 80-amp breaker | 
Maximum Run Length | 85 ft. one way for 1.5% Voltage Drop | 
Circuit Breaker Sizing | (2) 80-amp circuit breakers | 
13 Strings, 11 Modules per string
Riser Diagram of PV System

## Slide 36
| Introduction
Solar Panel Installation | Construction Analysis
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
System Direct Cost | $180,534
System Production | 47,000 kWh / year
System Production ($) | $6,110 / year
Incentives | 30% Fed. Tax Credit, $.05 / kWh State Credit
Cost Analysis
14 year Payback Period

## Slide 37
| Introduction
Solar Panel Installation | Construction Analysis
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Schedule Analysis
Duration | 4 weeks
Construction Concerns | Roof membrane, organization, system balance
Schedule for Photovoltaic System Installation
Notes: Construction Concerns: racking and roof, organization based on space, balancing systems

## Slide 38
| Introduction
Solar Panel Installation | Recommendation
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Do not install solar panels at roof level.
Notes: To much shading, not large enough system or production. If owner does feel as though it is worth it to attain LEED Gold, then go for it

## Slide 39
| Introduction
Mobile Technology Integration | Overview
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Mobile Technology Integration
-Tablet Computers-

## Slide 40
| Introduction
Mobile Technology Integration | Problem Identification
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Problem
Engineers and site management following inefficient processes
Data entry, field coordination, communication, organization- inefficient
Available technology underutilized
General Conditions competitive in this market

## Slide 41
| Introduction
Mobile Technology Integration | Case Study #1
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
ASCE Journal: Making the Case for Mobile IT in Construction
Industry slow to change and adopt new information technologies
Barriers include: low profit margin for GC, hesitation towards benefits, lack of awareness, lack of success stories
Analyzed 11 construction projects
Results
Reports generate faster and easier
Increased customer service
Ability to identify trends
Reduced task turn around time
Increased quality and efficiency

## Slide 42
| Introduction
Mobile Technology Integration | Case Study #2
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
DFW Airport- Terminal Renovation and Improvement Project
Cost | $900M
Duration | 7 years
Size | 2,000,000 SF
Main Implementation
Updated Electronic Drawings
Coordination in the Field
Results
Improved Efficiency
Reprographics Cost Decrease of 71% or $5.1M
Lessons Learned
Technology Must Have an Implementation Plan
Architect Must be On-board
Project Closeout and Archiving
Engineers Save 1 hr/day from Tablet Integration
Must Have Sole "Gatekeeper" of E-Documents
Results

## Slide 43
| Introduction
Mobile Technology Integration | Case Study #3
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Pharmaceutical Processing Plant
(Los Angeles, CA)
Cost | $150M
Duration | 2 ½ years
Size | 90,000 SF
Main Implementation
Updated Electronic Drawings
Coordination in the Field and RFI's
Results
Lessons Learned
Tablet Becomes Integral. Must Keep With You
Roadblocks with Technology (3D Model, Opening File Types)
Safety Evaluations
Engineers Save 1.1 hr/day from Tablet Use
Must Have Sole "Gatekeeper" of E-Documents
Reprographics Cost Decrease $4000/Addendum
Superintendents Save 1.5 hr/day from Tablet Use
Results

## Slide 44
| Introduction
Mobile Technology Integration | Means and Methods
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Original Practices
On Site Management | 4 people
Technology | Laptop Computers in Jobsite Office
Drawings | Electronic and Paper (Mainly Paper)
Storage | Cloud Server

## Slide 45
| Introduction
Mobile Technology Integration | Application to RFCS
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Proposed Tablet Integration Plan
Accessing Drawings in the Field
Documenting Field Issues
Email and Correspondence
Safety Evaluations
Daily Forms and Checklists
Coordination in the Field
On Site Management | 4 people
Technology | Table Computers & Laptop Computers in Jobsite Office
Drawings | Electronic and Paper (Mainly Electronic)
Storage | Cloud Server
Proposed Uses for Tablet Computers at RFCS

## Slide 46
| Introduction
Mobile Technology Integration | Analysis
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Direct Costs of Tablet Computer Implementation |  |  | 
Description | Quantity | Cost/Unit | Cost
Tablet Computers | 4 | $500/iPad | -($2,000)
Contingency for Software & Add-ons | 4 | $300/iPad | -($1,200)
Training Project Manager | 6 hours | - | -($624)
Training Superintendent | 6 hours | - | -($624)
Training Project Engineer #1 | 6 hours | - | -($408)
Training Project Engineer #2 | 6 hours | - | -($408)
Total | - | - | -($5,264)
Human Resource Costs of Tablet Integration (Weekly) |  |  | 
Description | Quantity | Cost/Unit | Cost
Costs |  |  | 
IT Champion Time | 2 hours | $68/hour | -($136)
Savings |  |  | 
Project Manager Time | 4 | - | $416
Superintendent Time | 7 | - | $728
Project Engineer #1 Time | 5 | - | $340
Project Engineer #2 Time | 5 | - | $340
Total | - | - | $1688/week
Costs of Tablet Computer Integration
Costs of Tablet Computer Implementation
Direct Costs | -($5,264)
Weekly Human Resource Savings | $1,688/ week
Overall Project Savings | $116,272
Benefits | Efficiency, Quality, Customer Service

## Slide 47
| Introduction
Mobile Technology Integration | Recommendations
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Implement tablet computers at RFCS.

## Slide 48
| Introduction
Recommendations | Overview
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Final Recommendations

## Slide 49
| Introduction
Recommendations | Overall Thoughts
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
1. Implement Partially Prefabricated Wall Panel Strategy as opposed to original stick-built construction.
2. Do not install solar panels at roof level.
3. Implement tablet computers at RFCS.
Final Recommendations

## Slide 50
| Introduction
Concluding Remarks | Overview
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Concluding Remarks

## Slide 51
| Introduction
Concluding Remarks | Reflection
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Increase value through innovative and efficient construction.
Reflection
Design Goal
Outcome
Schedule savings through innovative panel prefabrication.
Alternative energy system analyzed
Comprehensive and beneficial study of mobile technology integration
Successful Study

## Slide 52
| Introduction
Concluding Remarks | Acknowledgements
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Thank you!
DPR Construction
AE Faculty
PSU Department of Sustainability
Audience

## Slide 53
| Introduction
Concluding Remarks | Appendix
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Quote on C-CAPP Prefabricated Panel System |  |  | 
Cost Breakdown ($) |  | Schedule (Duration) | 
Base Budget | $907,500 | Preliminary | Variable
Staining Panels | $99,500 |  | 
Preweld Connections to Steel Structure | $75,000 | Layout and Preweld | 3 weeks
Caulking | $33,000 | Hanging Panels | 1 week
----------------------------------------------- | -------------- | Final Aligning and Welding | 3 weeks
Total Cost of System | $1,115,000 | Total Duration on site | 7 weeks
C-CAPP Estimate
Partial Panel Prefabrication Estimate

## Slide 54
| Introduction
Concluding Remarks | Appendix
| Prefabricated Exterior Wall Panels
| Detailed Sequencing
| Sizing of Rigging Beam
| Solar Panel Installation at Roof Level
| Mobile Technology Integration- Tablet Computers
| Recommendations
| Concluding Remarks
Solar Panel System Estimate
Direct Costs for Solar Panel Installation |  |  |  | 
Description | Cost/Unit | Quantity | Total Cost | Reference
Modules | $190/Module | 144 | $27,360 | Sunwize Quote
Ballast Racking System | $0.30/Watt | 35730 | $10,720 | Rocky Mountain Institute
Inverter | $19553/Unit | 1 | $19,553 | Affordable Solar Quote
DC Wiring #12 AWG | $0.74/LF | 12400 | $9,176 | RSMEANS
DC Conduit 3/4" | $10.50/LF | 2480 | $26,040 | RSMEANS
AC Wiring #4 AWG | $2.29/LF | 250 | $573 | RSMEANS
AC Conduit 1" | $12.45/LF | 250 | $3,113 | RSMEANS
Circuit Breakers 80 AMP | $1025/Ea | 2 | $2,050 | RSMEANS
Crane Rental (Truck Crane 4,000 lb. Capacity) | $4200/day | 2 | $8,400 | RSMEANS
Shipping | $190/Pallet | 11 | $2,090 | Sunwize Quote
Labor | $3/Watt | 35730 | $107,190 | Sunwize Rec.
Total | - | - | $180,534 | 
Major Costs for Research Facility Core and Shell |  | 
 | Construction Cost | Cost/SF
Actual Building Construction | $16,031,402 | $125.86
Total Project | $20,035,000 | $157.29
Mechanical System | $1,574,261 | $12.36
Electrical System | $1,014,666 | $7.97
Plumbing System | $662,250 | $5.20
Fire Protection | $298,462 | $2.34
Structural System | $5,238,945 | $41.13
Exterior Skin | $4,089,261 | $32.10
Building Use Description |  | 
Level | Size | Use
Underground Parking Garage | 31,197 SF | Parking; UPS, Electrical & Elevator Machine Rooms
First Floor | 31,850 SF | Lobby, Laboratory Space
Second Floor | 31,850 SF | Offices, Laboratory Rooms
Third Floor | 31,850 SF | Offices, Laboratory Rooms
Fourth Floor | 31,850 SF | Offices
Roof | 31,850 SF | Large Mechanical Equipment
RFCS Costs and Building Use