## Slide 1
The Office Building
Washington, D.C.
Penn State Architectural Engineering Senior Capstone Project
Brett Miller | Construction Option
Advisor: Dr. Ed Gannon

## Slide 2
Brett Miller
Construction
Introduction
The Office Building
Washington, D.C.
Project Overview
Analysis 1 | Foundation Walls
Analysis 2 | Neighboring Foundation Support
Research| Retaining Structures
Analysis 3 | Value Engineering
Notes: I) Project Overview
II)

## Slide 3
Project Size | 108,000 SF
Height Above Grade | 9 Stories
Contract Value | $30.5 million
Dates of Construction | March 2013 – March 2015
Occupant | Undetermined
Primary Use | Office Building
Owner | Mid Atlantic Realty
General Contractor | James G. Davis Construction
Architect | Gensler
Brett Miller
Construction
Project Overview
The Office Building
Washington, D.C.
Presentation Outline
Project Overview
Research | Retaining Structures
Analysis 1 | Foundation Walls
Cost
Schedule
Conclusion
Analysis 2 | Neighboring Foundation Support
Cost
Schedule
Conclusion
Analysis 3 | Value Engineering
Electrical Breadth | Sizing wire/Busway
Cost
Schedule
Conclusion
Conclusion & Recommendations
Acknowledgements

## Slide 4
 | Advantages | Disadvantages
Sheet Piling (A) | Watertight Excavation | Costly Time Consuming
Soldier Piles and Lagging (B) | Less Expensive Faster | Loud Installation Not Watertight
Concrete Slurry Walls (C) | Watertight Extreme Depths Foundation Walls | Extremely Costly Time Consuming
Top Down Construction (D) | Fast Ground Stability | Geotech. Considerations
Brett Miller
Construction
Research | Retaining Structures
The Office Building
Washington, D.C.
A
B
C
D
Presentation Outline
Project Overview
Research | Retaining Structures
Analysis 1 | Foundation Walls
Cost
Schedule
Conclusion
Analysis 2 | Neighboring Foundation Support
Cost
Schedule
Conclusion
Analysis 3 | Value Engineering
Electrical Breadth | Sizing wire/Busway
Cost
Schedule
Conclusion
Conclusion & Recommendations
Acknowledgements

## Slide 5
Brett Miller
Construction
Analysis 1 | Foundation Walls
The Office Building
Washington, D.C.
Problem Identification
Extensive support of excavation
60 Foundation wall box-outs
Formwork time/cost
Potential Solutions
Replace CIP with shotcrete to reduce formwork
Presentation Outline
Project Overview
Research | Retaining Structures
Analysis 1 | Foundation Walls
Cost
Schedule
Conclusion
Analysis 2 | Neighboring Foundation Support
Cost
Schedule
Conclusion
Analysis 3 | Value Engineering
Electrical Breadth | Sizing wire/Busway
Cost
Schedule
Conclusion
Conclusion & Recommendations
Acknowledgements

## Slide 6
Brett Miller
Construction
Analysis 1 | Foundation Walls
The Office Building
Washington, D.C.
Chart: Total Cost Savings
 | 237816.54 | 77127.42
Total Cost | 
Cast-in-Place | $314,943.96
Shotcrete | $237,816.54
Savings | $77,127.42
24.5% Savings
Chart: Cost Comparison
| Material | Labor | Equipment
Cast-in-Place | 229583.19 | 69120 | 16240.77
Shotcrete | 186587.54 | 30240 | 20989
Presentation Outline
Project Overview
Research | Retaining Structures
Analysis 1 | Foundation Walls
Cost
Schedule
Conclusion
Analysis 2 | Neighboring Foundation Support
Cost
Schedule
Conclusion
Analysis 3 | Value Engineering
Electrical Breadth | Sizing wire/Busway
Cost
Schedule
Conclusion
Conclusion & Recommendations
Acknowledgements

## Slide 7
Brett Miller
Construction
Analysis 1 | Foundation Walls
The Office Building
Washington, D.C.
Chart: Schedule Comparison
| P1 | P2 | P3
Cast-in-Place | 12 | 12 | 24
Shotcrete | 4.5 | 4 | 6.5
Final Schedule | 
Cast-in-Place | 48 Days
Shotcrete | 15 Days
Savings | 33 Days
Chart: Total Schedule Savings
 | 15 | 33
68.8% Savings
Presentation Outline
Project Overview
Research | Retaining Structures
Analysis 1 | Foundation Walls
Cost
Schedule
Conclusion
Analysis 2 | Neighboring Foundation Support
Cost
Schedule
Conclusion
Analysis 3 | Value Engineering
Electrical Breadth | Sizing wire/Busway
Cost
Schedule
Conclusion
Conclusion & Recommendations
Acknowledgements

## Slide 8
Brett Miller
Construction
Analysis 1 | Foundation Walls
The Office Building
Washington, D.C.
$77,000
33 Days
Chart: Cost
| Cast-in-Place | Shotcrete
 | 314943.96 | 237816.34
Chart: Schedule
| Cast-in-Place | Shotcrete
 | 48 | 15
Cast-in-Place
Shotcrete
Presentation Outline
Project Overview
Research | Retaining Structures
Analysis 1 | Foundation Walls
Cost
Schedule
Conclusion
Analysis 2 | Neighboring Foundation Support
Cost
Schedule
Conclusion
Analysis 3 | Value Engineering
Electrical Breadth | Sizing wire/Busway
Cost
Schedule
Conclusion
Conclusion & Recommendations
Acknowledgements

## Slide 9
Brett Miller
Construction
Analysis 2 | Neighboring Foundation Support
The Office Building
Washington, D.C.
Problem Identification
Historic building on West property line
Foundation needs supported
Secant Wall duration
Potential Solutions
Replace Secant Wall with Slurry Wall
Presentation Outline
Project Overview
Research | Retaining Structures
Analysis 1 | Foundation Walls
Cost
Schedule
Conclusion
Analysis 2 | Neighboring Foundation Support
Cost
Schedule
Conclusion
Analysis 3 | Value Engineering
Electrical Breadth | Sizing wire/Busway
Cost
Schedule
Conclusion
Conclusion & Recommendations
Acknowledgements

## Slide 10
Brett Miller
Construction
Analysis 2 | Neighboring Foundation Support
The Office Building
Washington, D.C.
Chart: Cost Comparison
| Material | Labor | Equipment | Mob/Demob
Secant Wall | 230000 | 117000 | 78000 | 126000
24" Slurry Wall | 408000 | 86000 | 70000 | 180000
Chart: 
Secant Wall | 551000
Chart: 
| Secant Wall | Savings
 | 551000 | -193000
35% Increase
+
Total Cost | 
Secant Wall | $551,000
24” Slurry Wall | $744,000
Additional Costs | $193,000
Presentation Outline
Project Overview
Research | Retaining Structures
Analysis 1 | Foundation Walls
Cost
Schedule
Conclusion
Analysis 2 | Neighboring Foundation Support
Cost
Schedule
Conclusion
Analysis 3 | Value Engineering
Electrical Breadth | Sizing wire/Busway
Cost
Schedule
Conclusion
Conclusion & Recommendations
Acknowledgements

## Slide 11
Brett Miller
Construction
Analysis 2 | Neighboring Foundation Support
The Office Building
Washington, D.C.
Chart: Schedule Comparison
| Mob/Demob | Installation
Secant Wall | 5 | 10
24" Slurry Wall | 10 | 5
Final Schedule | 
Secant Wall | 15 Days
Slurry Wall | 15 Days
Savings | 0 Days
Chart: Total Schedule Savings
 | 15 | 0
0% Savings
Presentation Outline
Project Overview
Research | Retaining Structures
Analysis 1 | Foundation Walls
Cost
Schedule
Conclusion
Analysis 2 | Neighboring Foundation Support
Cost
Schedule
Conclusion
Analysis 3 | Value Engineering
Electrical Breadth | Sizing wire/Busway
Cost
Schedule
Conclusion
Conclusion & Recommendations
Acknowledgements

## Slide 12
Brett Miller
Construction
Analysis 2 | Neighboring Foundation Support
The Office Building
Washington, D.C.
$193,000
0 Days
Chart: Cost
| Secant Wall | 24" Slurry Wall
 | 551000 | 744000
Chart: Schedule
| Secant Wall | 24" Slurry Wall
 | 15 | 15
Secant Wall
24” Slurry Wall
Presentation Outline
Project Overview
Research | Retaining Structures
Analysis 1 | Foundation Walls
Cost
Schedule
Conclusion
Analysis 2 | Neighboring Foundation Support
Cost
Schedule
Conclusion
Analysis 3 | Value Engineering
Electrical Breadth | Sizing wire/Busway
Cost
Schedule
Conclusion
Conclusion & Recommendations
Acknowledgements

## Slide 13
Brett Miller
Construction
Analysis 3 | Value Engineering
The Office Building
Washington, D.C.
Problem Identification
Unforeseen costs
Over budget
Expensive copper feeder
Potential Solutions
Replace copper wiring with less expensive system
Presentation Outline
Project Overview
Research | Retaining Structures
Analysis 1 | Foundation Walls
Cost
Schedule
Conclusion
Analysis 2 | Neighboring Foundation Support
Cost
Schedule
Conclusion
Analysis 3 | Value Engineering
Electrical Breadth | Sizing wire/Busway
Cost
Schedule
Conclusion
Conclusion & Recommendations
Acknowledgements

## Slide 14
Brett Miller
Construction
Analysis 3 | Value Engineering
The Office Building
Washington, D.C.
15.0”
4.5”
Sizing Aluminum Wiring
Sizing Aluminum Busway
Presentation Outline
Project Overview
Research | Retaining Structures
Analysis 1 | Foundation Walls
Cost
Schedule
Conclusion
Analysis 2 | Neighboring Foundation Support
Cost
Schedule
Conclusion
Analysis 3 | Value Engineering
Electrical Breadth | Sizing wire/Busway
Cost
Schedule
Conclusion
Conclusion & Recommendations
Acknowledgements

## Slide 15
Chart: Aluminum Wiring Cost Savings
 | 313076.71 | 17360.14
Brett Miller
Construction
Analysis 3 | Value Engineering
The Office Building
Washington, D.C.
Total Cost | 
Copper Wiring | $330,436.85
Aluminum Wiring | $313,076.71
Aluminum Busway | $225,346.06
Chart: Aluminum Busway Cost Savings
 | 225346.06 | 137998.26
32% Savings
5% Savings
Presentation Outline
Project Overview
Research | Retaining Structures
Analysis 1 | Foundation Walls
Cost
Schedule
Conclusion
Analysis 2 | Neighboring Foundation Support
Cost
Schedule
Conclusion
Analysis 3 | Value Engineering
Electrical Breadth | Sizing wire/Busway
Cost
Schedule
Conclusion
Conclusion & Recommendations
Acknowledgements
Chart: Cost Comparison
| Material | Labor
Copper Wiring | 181477.67 | 148959.18
Aluminum Wiring | 131210.06 | 181866.65
Aluminum Busway | 171568.7 | 53777.36

## Slide 16
Brett Miller
Construction
Analysis 3 | Value Engineering
The Office Building
Washington, D.C.
Chart: Schedule Comparison
| Conductor | Conduit | Accessories
Copper Wiring | 23 | 24 | 0
Aluminum Wiring | 24 | 26 | 0
Aluminum Busway | 38 | 0 | 4
Final Schedule | 
Copper Wiring | 46 Days
Aluminum Wiring | 50 Days
Aluminum Busway | 41 Days
Chart: 
Copper Wiring | 46
Chart: 
 | 46 | -4
Chart: 
 | 41 | 5
Aluminum Wiring Schedule Increase
Aluminum Busway Schedule Savings
8.7% Increase
10.9% Savings
+
Presentation Outline
Project Overview
Research | Retaining Structures
Analysis 1 | Foundation Walls
Cost
Schedule
Conclusion
Analysis 2 | Neighboring Foundation Support
Cost
Schedule
Conclusion
Analysis 3 | Value Engineering
Electrical Breadth | Sizing wire/Busway
Cost
Schedule
Conclusion
Conclusion & Recommendations
Acknowledgements

## Slide 17
Brett Miller
Construction
Analysis 3 | Value Engineering
The Office Building
Washington, D.C.
Chart: Schedule
| Copper Wiring | Aluminum Wiring
 | 46 | 50
Copper Wiring
Aluminum Wiring
Chart: Schedule
| Copper Wiring | Aluminum Busway
 | 46 | 41
Copper Wiring
Aluminum Busway
4 Days
$17,000
$105,000
5 Days
Presentation Outline
Project Overview
Research | Retaining Structures
Analysis 1 | Foundation Walls
Cost
Schedule
Conclusion
Analysis 2 | Neighboring Foundation Support
Cost
Schedule
Conclusion
Analysis 3 | Value Engineering
Electrical Breadth | Sizing wire/Busway
Cost
Schedule
Conclusion
Conclusion & Recommendations
Acknowledgements
Chart: Cost
| Copper Wiring | Aluminum Wiring
 | 330436.85 | 313076.71
Chart: Cost
| Copper Wiring | Aluminum Busway
 | 330436.85 | 225346.06

## Slide 18
Brett Miller
Construction
Conclusion & Recommendations
The Office Building
Washington, D.C.
Analysis 1 | Foundation Walls
Cost Impact: Save $77,000
Schedule: Save 33 Days
Recommendation: Select Shotcrete
Analysis 2 | Neighboring Foundation Support
Cost Impact: $193,000 More Expensive
Schedule: No Advantage
Recommendation: Select Secant Wall
Analysis 3 | Value Engineering
Cost Impact: Aluminum Wire Saves $17,000
Aluminum Busway Saves $105,000
Schedule: Aluminum Wire Takes 4 More Days
Aluminum Busway Saves 5 Days
Recommendation: Select Aluminum Busway
Total Savings
$182,000
38 Days
Presentation Outline
Project Overview
Research | Retaining Structures
Analysis 1 | Foundation Walls
Cost
Schedule
Conclusion
Analysis 2 | Neighboring Foundation Support
Cost
Schedule
Conclusion
Analysis 3 | Value Engineering
Electrical Breadth | Sizing wire/Busway
Cost
Schedule
Conclusion
Conclusion & Recommendations
Acknowledgements

## Slide 19
Brett Miller
Construction
Acknowledgements
The Office Building
Washington, D.C.
Academic Acknowledgements
Dr. Ed Gannon
Dr. Robert Leicht
Dr. Craig Dubler
Special Thanks
The DAVIS Project Team
Will Cox – DAVIS Project Manager
Drew Heilman – DAVIS Project Engineer
Rebecca Nordby – Balfour Beatty Project Executive
PACE Industry Members
Friends and Family
Industry Acknowledgements

## Slide 21
System | P1 | P2 | P3 | Total
Cast-in-Place | 12 | 12 | 24 | 48
Shotcrete | 4.5 | 4 | 6.5 | 15
Savings | 19.5 | 8 | 5.5 | 33
System | Material | Labor | Equipment | Total
Cast-in-Place | $229,583.19 | $69,120.00 | $16,240.77 | $314,943.96
Shotcrete | $186,587.54 | $30,240.00 | $20,989.00 | $237,816.54
Savings | $42,995.65 | $38,880.00 | -$4,748.23 | $77,127.42
Brett Miller
Construction
Appendix A | Foundation Walls
The Office Building
Washington, D.C.
Chart: Material Breakdown
| Concrete | Formwork | Rebar
Cast-in-Place | 78269.01 | 83503.24 | 67810.94
Shotcrete | 118776.6 | 0 | 67810.94

## Slide 22
Brett Miller
Construction
Appendix A | Foundation Walls
The Office Building
Washington, D.C.
Cast-in-Place Concrete Cost Breakdown |  |  |  |  |  |  |  |  |  |  |  | 
Floor | Volume (cu yd) | Concrete Unit Cost ($/cu yd) | Concrete Cost | Formwork Unit Cost ($/ft) | Formwork Cost | Rebar Cost | Total Material Cost | Labor Unit Cost ($/Day) | Labor Cost | Equipment Unit Cost ($/cu yd) | Equipment Cost | Total
P3 | 205 | 118.41 | $24,274.05 | $78.37 | $25,901.29 | $21,021.39 | $71,196.73 | $1,440.00 | $34,560.00 | 24.57 | 5036.85 | $110,793.58
P2 | 188 | 118.41 | $22,261.08 | $78.37 | $23,746.11 | $18,987.06 | $64,994.25 | $1,440.00 | $17,280.00 | 24.57 | 4619.16 | $86,893.41
P1 | 268 | 118.41 | $31,733.88 | $78.37 | $33,855.84 | $27,802.49 | $93,392.21 | $1,440.00 | $17,280.00 | 24.57 | 6584.76 | $117,256.97
Total: |  |  | $78,269.01 |  | $83,503.24 | $67,810.94 | $229,583.19 |  | $69,120.00 |  | $16,240.77 | $314,943.96
Shotcrete Cost Breakdown |  |  |  |  |  |  |  |  |  | 
Floor | Volume (cu yd) | Concrete Unit Cost ($/cu yd) | Concrete Cost | Rebar Cost | Total Material Cost | Labor Unit Cost ($/Day) | Labor Cost | Equipment Unit Cost ($/cu yd) | Equipment Cost | Total
P3 | 234 | $157.32 | $36,812.88 | $21,021.39 | $57,834.27 | $2,016.00 | $9,072.00 | $27.80 | $6,505.20 | $73,411.47
P2 | 216 | $157.32 | $33,981.12 | $18,987.06 | $52,968.18 | $2,016.00 | $8,064.00 | $27.80 | $6,004.80 | $67,036.98
P1 | 305 | $157.32 | $47,982.60 | $27,802.49 | $75,785.09 | $2,016.00 | $13,104.00 | $27.80 | $8,479.00 | $97,368.09
Total | 755 |  | $118,776.60 | $67,810.94 | $186,587.54 |  | $30,240.00 |  | $20,989.00 | $237,816.54
Shotcrete Schedule Breakdown |  | 
Floor | Volume (cu yd) | Duration (Day)
P3 | 234 | 4.5
P2 | 216 | 4
P1 | 305 | 6.5
Total | 755 | 15
CIP Schedule Breakdown |  | 
Floor | Wall Length (ft) | Duration (Day)
P3 | 330.5 | 24
P2 | 303.0 | 12
P1 | 432.0 | 12
Total | 1066 | 48

## Slide 23
Brett Miller
Construction
Appendix B | Neighboring Foundation
The Office Building
Washington, D.C.
Cost Comparison |  |  |  |  | 
System | Material | Labor / Manpower | Equipment | Transportation / Mobilization | Grand Total
Secant Wall System | $230,000 | $117,000 | $78,000 | $126,000 | $551,000
24" thick Slurry Wall | $408,000 | $86,000 | $70,000 | $180,000 | $744,000
Savings | -$178,000 | $31,000 | $8,000 | -$54,000 | -$193,000
Schedule Comparison |  | 
System | Duration | 
Secant Wall System | Mob/demob | 1 Week
 | Wall | 2 Weeks
24" thick Slurry Wall | Mob/demob | 2 Weeks
 | Wall | 1 Week

## Slide 24
Brett Miller
Construction
Appendix C | Electrical Breadth
The Office Building
Washington, D.C.

## Slide 25
Master Format Code | Description | Unit | Length | Material Unit Cost | Total Material | Labor Unit Cost | Total Labor | Total | Crew | # of Crews | Labor Hours | Duration (hrs)
260519900490 | 500 kcmil Copper Conductor | CLF | 96.46 | $1,186.75 | $114,473.91 | $833.04 | $80,355.04 | $194,828.94 | 3 Elec | 3 | 5 | 161
260519900260 | 1/0 kcmil Copper Grounding Conductor | CLF | 24.115 | $253.51 | $6,113.39 | $402.48 | $9,705.81 | $15,819.20 | 2 Elec | 3 | 2.424 | 20
260533131140 | 4" Diameter Metal Conduit | LF | 2411.5 | $25.25 | $60,890.38 | $38.07 | $91,805.81 | $152,696.18 | 2 Elec | 3 | 0.229 | 185
Total |  |  |  |  | $181,477.67 |  | $148,959.18 | $330,436.85 |  |  |  | 366
Master Format Code | Description | Unit | Length | Material Unit Cost | Total Material | Labor Unit Cost | Total Labor | Total | Crew | # of Crews | Labor Hours | Duration (hrs)
260519900800 | 500 kcmil Aluminum Conductor | C.L.F. | 124.02 | $398.95 | $49,477.78 | $221.52 | $27,472.91 | $76,950.69 | 3 Elec | 3 | 4 | 166
260519900620 | 1/0 Aluminum Grounding Conductor | C.L.F. | 31.005 | $111.10 | $3,444.66 | $111.28 | $3,450.24 | $6,894.89 | 2 Elec | 3 | 2 | 21
260533131140 | 4" Diameter Metal Conduit | L.F. | 3100.5 | $25.25 | $78,287.63 | $38.07 | $118,036.04 | $196,323.66 | 2 Elec | 3 | 0.2 | 207
Total |  |  |  |  | $131,210.06 |  | $181,866.65 | $313,076.71 |  |  |  | 394
Master Format Code | Description | Unit | Length | Material Unit Cost | Total Material | Labor Unit Cost | Total Labor | Total | Crew | # of Crews | Labor Hours | Duration (hrs)
262513104620 | Feeder Al Busway 2500 amp | L.F | 200.5 | $484.80 | $97,202.40 | $147.68 | $29,609.84 | $126,812.24 | 2 Elec | 2 | 1.333 | 134
262513100330 | Plug-in Al Busway 2500 amp | L.F | 144 | $398.95 | $57,448.80 | $126.88 | $18,270.72 | $75,719.52 | 2 Elec | 2 | 1.143 | 83
262513106470 | Busway End Box 2500 amp | Ea. | 2 | $1,136.25 | $2,272.50 | $738.40 | $1,476.80 | $3,749.30 | 2 Elec | 1 | 13.333 | 27
262513105520 | Busway Elbow 2500 amp | Ea. | 10 | $1,464.50 | $14,645.00 | $442.00 | $4,420.00 | $19,065.00 | 2 Elec | 1 | 8 | 80
Total |  |  |  |  | $171,568.70 |  | $53,777.36 | $225,346.06 |  |  |  | 324
Brett Miller
Construction
Appendix D | Value Engineering
The Office Building
Washington, D.C.
Copper Wiring Breakdown
Aluminum Wiring Breakdown
Aluminum Busway Breakdown