## Slide 1
Wardman West Residential
Penn State AE Senior Thesis Project
Kevin Kroener │Construction Option
Faculty Advisor │Ray Sowers

## Slide 2
Introduction
Project Background
    Location │ Woodley Park, NW Washington, DC
    Building Type │Midrise Luxury Apartment Building
    Project Size│321,000 GSF (132,500 SF Below Grade)
    Number of Stories│8 Above - Grade / 2 Below - Grade
    Contract Value│$88 million
    Contract Type │Negotiated GMP
    Dates of Construction │June 16, 2011 – March 14, 2014
    GC │Clark Construction Group, LLC
    Owner/Developer │The JBG Companies
    Architect │Cooper Carry
Wardman West Residential
Woodley Park, NW Washington, DC
AE Senior Thesis Project
Kevin Kroener │Construction Option
Introduction
  Project Background
  Analysis Overview
Depth 1: APC Panel Prefabrication
Depth 2: SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
Courtesy of Clark Construction

## Slide 3
Introduction
Thesis Focus
Slow Exterior Brick Masonry Work
Introduction
  Project Background
  Analysis Overview
Depth 1: APC Panel Prefabrication
Depth 2: SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
Wardman West Residential
Woodley Park, NW Washington, DC
AE Senior Thesis Project
Kevin Kroener │Construction Option
Courtesy of Clark Construction
Courtesy of Clark Construction

## Slide 4
Introduction
Thesis Focus
Slow Exterior Brick Masonry Work
Analysis Overview
  Analysis 1: Architectural Precast Concrete Wall Panels
  Thermal Performance Study
  Structural Feasibility & Redesign Study
  Analysis 2: SIPS (Short Interval Production Schedule)
  Analysis 3: Safety Evaluation
  Analysis 4: General Contractor Implementation Plan for APC Wall Panels
Introduction
  Project Background
  Analysis Overview
Depth 1: APC Panel Prefabrication
Depth 2: SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
Wardman West Residential
Woodley Park, NW Washington, DC
AE Senior Thesis Project
Kevin Kroener │Construction Option
Courtesy of Clark Construction
Courtesy of Clark Construction

## Slide 5
APC Wall Panel Prefabrication
Problem:
  Lagging Exterior Brick Masonry Work
Proposed Solution:
  Substitute Architectural Precast Concrete Wall Panels for Brick Veneer Wall
Introduction
Depth 1: APC Panel Prefabrication
  Overview & Existing Wall System
  Product Selection
  Transportation & Logistics
  Cost Savings & Schedule Acceleration
  Structural Feasibility Study
Depth 2: SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
AE Senior Thesis Project
Kevin Kroener │Construction Option
Wardman West Residential
Woodley Park, NW Washington, DC

## Slide 6
Overview
APC Wall Panel Prefabrication
Problem:
  Lagging Exterior Brick Masonry Work
Proposed Solution:
  Substitute Architectural Precast Concrete Wall Panels for Brick Veneer Wall
Benefits to Architectural Precast Concrete Wall Panels
Aesthetic Flexibility
Product Quality
Energy Performance
Cost Savings
Schedule Acceleration
Introduction
Depth 1: APC Panel Prefabrication
  Overview & Existing Wall System
  Product Selection
  Transportation & Logistics
  Cost Savings & Schedule Acceleration
  Structural Feasibility Study
Depth 2: SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
AE Senior Thesis Project
Kevin Kroener │Construction Option
Wardman West Residential
Woodley Park, NW Washington, DC
Courtesy of PCI

## Slide 7
Overview
APC Wall Panel Prefabrication
Problem:
  Lagging Exterior Brick Masonry Work
Proposed Solution:
  Substitute Architectural Precast Concrete Wall Panels for Brick Veneer Wall
Benefits to Architectural Precast Concrete Wall Panels
Aesthetic Flexibility
Product Quality
Energy Performance
Cost Savings
Schedule Acceleration
Material | Thickness (inches)
1. Standard Brick (Glen Gery 52 DD) | 4
2. Air Cavity | 2
3. Rigid Insulation (Dow EPS) | 3
4. Permeable Air Barrier | --
5. Exterior Sheathing | 5/8
6. Cold-Formed 18 Ga. Metal Stud (16’’ OC) | 4
7. Polyethylene Vapor Barrier | --
8. 5/8’’ Gypsum Wall Board | 5/8
Existing Wall System
Introduction
Depth 1: APC Panel Prefabrication
  Overview & Existing Wall System
  Product Selection
  Transportation & Logistics
  Cost Savings & Schedule Acceleration
  Structural Feasibility Study
Depth 2: SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
AE Senior Thesis Project
Kevin Kroener │Construction Option
Wardman West Residential
Woodley Park, NW Washington, DC
Courtesy of PCI
Courtesy of Clark Construction

## Slide 8
Product Selection
APC Wall Panel Prefabrication
C-GRID Carbon Fiber Grid:
Shear connector between concrete wythes
Minimum wythe thickness of 1 ¾’’
Up to 40% lighter
Introduction
Depth 1: APC Panel Prefabrication
  Overview & Existing Wall System
  Product Selection
  Transportation & Logistics
  Cost Savings & Schedule Acceleration
  Structural Feasibility Study
Depth 2: SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
Selection:
CarbonCast Insulated Architectural Cladding
Product Advantages:
Reduced load on building structure
Lower transportation cost
Smaller cranes can be used to pick and erect CarbonCast panels
Lower carbon footprint
Aesthetic Versatility
Meets ASHRAE requirement for continuous insulation
AE Senior Thesis Project
Kevin Kroener │Construction Option
Wardman West Residential
Woodley Park, NW Washington, DC
Courtesy of AltusGroup

## Slide 9
Product Selection
APC Wall Panel Prefabrication
Selection:
CarbonCast Insulated Architectural Cladding
Product Advantages:
Reduced load on building structure
Lower transportation cost
Smaller cranes can be used to pick and erect CarbonCast panels
Lower carbon footprint
Aesthetic Versatility
Meets ASHRAE requirement for continuous insulation
C-GRID Carbon Fiber Grid:
Shear connector between concrete wythes
Minimum wythe thickness of 1 ¾’’
Up to 40% lighter
EPS, XPS or Poly-Iso foam Rigid Insulation
Introduction
Depth 1: APC Panel Prefabrication
  Overview & Existing Wall System
  Product Selection
  Transportation & Logistics
  Cost Savings & Schedule Acceleration
  Structural Feasibility Study
Depth 2: SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
AE Senior Thesis Project
Kevin Kroener │Construction Option
Wardman West Residential
Woodley Park, NW Washington, DC
Courtesy of AltusGroup
Courtesy of AltusGroup
Courtesy of AltusGroup

## Slide 10
Crane Use
APC Wall Panel Prefabrication
Introduction
Depth 1: APC Panel Prefabrication
  Overview & Existing Wall System
  Product Selection
  Transportation & Logistics
  Cost Savings & Schedule Acceleration
  Structural Feasibility Study
Depth 2: SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
Mobile Crane
Precast Subcontractor
20 ton Tower Crane
Clark Concrete
Jib Length shorten from 213’ to 180’
Capacity increased from 11,680 lb. to 17,200 lb.
AE Senior Thesis Project
Kevin Kroener │Construction Option
Wardman West Residential
Woodley Park, NW Washington, DC

## Slide 11
Crane Use
APC Wall Panel Prefabrication
Tower Crane Relocation
Introduction
Depth 1: APC Panel Prefabrication
  Overview & Existing Wall System
  Product Selection
  Transportation & Logistics
  Cost Savings & Schedule Acceleration
  Structural Feasibility Study
Depth 2: SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
Mobile Crane
Precast Subcontractor
20 ton Tower Crane
Clark Concrete
Jib Length shorten from 213’ to 180’
Capacity increased from 11,680 lb. to 17,200 lb.
AE Senior Thesis Project
Kevin Kroener │Construction Option
Wardman West Residential
Woodley Park, NW Washington, DC

## Slide 12
Crane Use
APC Wall Panel Prefabrication
Workflow Sequence
Tower Crane Relocation
Introduction
Depth 1: APC Panel Prefabrication
  Overview & Existing Wall System
  Product Selection
  Transportation & Logistics
  Cost Savings & Schedule Acceleration
  Structural Feasibility Study
Depth 2: SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
Elevations
North
East
Mobile Crane
Tower Crane
Elevations
South
Courtyard
Mobile Crane
Precast Subcontractor
20 ton Tower Crane
Clark Concrete
Jib Length shorten from 213’ to 180’
Capacity increased from 11,680 lb. to 17,200 lb.
AE Senior Thesis Project
Kevin Kroener │Construction Option
Wardman West Residential
Woodley Park, NW Washington, DC

## Slide 13
Transportation
APC Wall Panel Prefabrication
Introduction
Depth 1: APC Panel Prefabrication
  Overview & Existing Wall System
  Product Selection
  Transportation & Logistics
  Cost Savings & Schedule Acceleration
  Structural Feasibility Study
Depth 2: SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
Flatbed or Low-deck Trailers:
Used for precast panels < 12’ x 40’
AE Senior Thesis Project
Kevin Kroener │Construction Option
Wardman West Residential
Woodley Park, NW Washington, DC
Courtesy of Oldcastle

## Slide 14
Transportation
APC Wall Panel Prefabrication
Shipping:
Oldcastle Precast Building Systems
Plant Location – Edgewood, Maryland
Delivery
Introduction
Depth 1: APC Panel Prefabrication
  Overview & Existing Wall System
  Product Selection
  Transportation & Logistics
  Cost Savings & Schedule Acceleration
  Structural Feasibility Study
Depth 2: SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
Flatbed or Low-deck Trailers:
Used for precast panels < 12’ x 40’
AE Senior Thesis Project
Kevin Kroener │Construction Option
Wardman West Residential
Woodley Park, NW Washington, DC
Rest Stop Staging
I-95 Maryland Rest and Welcome Area
32 Miles from Beltway (I-495)
Courtesy of Oldcastle

## Slide 15
Transportation
APC Wall Panel Prefabrication
Shipping:
Oldcastle Precast Building Systems
Plant Location – Edgewood, Maryland
Site Staging
Delivery
Mobile Crane
Tower Crane
Staging Area
Introduction
Depth 1: APC Panel Prefabrication
  Overview & Existing Wall System
  Product Selection
  Transportation & Logistics
  Cost Savings & Schedule Acceleration
  Structural Feasibility Study
Depth 2: SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
Flatbed or Low-deck Trailers:
Used for precast panels < 12’ x 40’
AE Senior Thesis Project
Kevin Kroener │Construction Option
Wardman West Residential
Woodley Park, NW Washington, DC
Courtesy of Oldcastle

## Slide 16
APC Wall Panel Prefabrication
Cost Savings
Item | Amount
Brick | $2,676,060
Backup, Sheathing and Insulation | $55,834
Metals | $292,500
Misc. | $246,375
Limestone | $843,570
Total | $4,114,339
Existing Brick Veneer Wall System
APC Wall Panels
Introduction
Depth 1: APC Panel Prefabrication
  Overview & Existing Wall System
  Product Selection
  Transportation & Logistics
  Cost Savings & Schedule Acceleration
  Structural Feasibility Study
Depth 2: SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
AE Senior Thesis Project
Kevin Kroener │Construction Option
Wardman West Residential
Woodley Park, NW Washington, DC
Item | Amount
Architectural Precast Concrete Panels (including attachment hardware) | $2,768,480
Penthouse Brick | $205,905
Metals | $292,500
Misc. | $407,355
Total | $3,468,335
Chart: 
| Brick | APC Wall Panels
Series 1 | 2676060 | 2768480
Series 2 | 1436279 | 699855

## Slide 17
APC Wall Panel Prefabrication
Schedule Acceleration
Cost Savings
Item | Amount
Brick | $2,676,060
Backup, Sheathing and Insulation | $55,834
Metals | $292,500
Misc. | $246,375
Limestone | $843,570
Total | $4,114,339
Existing Brick Veneer Wall System
APC Wall Panels
Accelerated Duration for APC Wall Panels:
32 Days
Introduction
Depth 1: APC Panel Prefabrication
  Overview & Existing Wall System
  Product Selection
  Transportation & Logistics
  Cost Savings & Schedule Acceleration
  Structural Feasibility Study
Depth 2: SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
AE Senior Thesis Project
Kevin Kroener │Construction Option
Activity | Start | Finish | Duration (Work Days)
APC Wall Panels | 2 Jan 2012 | 15 Feb 2013 | 32
Windows | 18 Jan 2013 | 14 Jun 2013 | 105
Stone | 6 Mar 2013 | 17 Aug 2013 | 118
Penthouse Brick | 11 Jul 2013 | 7 Aug 2013 | 20
Balcony Front Brick | 10 Jul 2013 | 10 Aug 2013 | 23
Revised Ext. Skin Total Duration | 2 Jan 2012 | 17 Aug 2013 | 163
Schedule Acceleration w/ Earlier Finish Date |  |  | 46
Activity | Duration (Work Days)
APC Wall Panels (Raw) | 57
APC Wall Panel w/ Phasing | 32
Schedule Acceleration | 88
w/ Phasing | 113
Original Duration for Brick Work:
145 Days
Wardman West Residential
Woodley Park, NW Washington, DC
Item | Amount
Architectural Precast Concrete Panels (including attachment hardware) | $2,768,480
Penthouse Brick | $205,905
Metals | $292,500
Misc. | $407,355
Total | $3,468,335
Chart: 
| Brick | APC Wall Panels
Series 1 | 2676060 | 2768480
Series 2 | 1436279 | 699855

## Slide 18
Results
APC Wall Panel Prefabrication
Schedule Acceleration
Cost Savings
Item | Amount
Brick | $2,676,060
Backup, Sheathing and Insulation | $55,834
Metals | $292,500
Misc. | $246,375
Limestone | $843,570
Total | $4,114,339
Existing Brick Veneer Wall System
APC Wall Panels
SAVINGS = $646,000
16 % Cost Compared Existing System
5 % Cost of Building Enclosure
+ 46 Days to Project
Schedule
Original Duration for Brick Work:
145 Days
Accelerated Duration for APC Wall Panels:
32 Days
Introduction
Depth 1: APC Panel Prefabrication
  Overview & Existing Wall System
  Product Selection
  Transportation & Logistics
  Cost Savings & Schedule Acceleration
  Structural Feasibility Study
Depth 2: SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
AE Senior Thesis Project
Kevin Kroener │Construction Option
Wardman West Residential
Woodley Park, NW Washington, DC
Activity | Start | Finish | Duration (Work Days)
APC Wall Panels | 2 Jan 2012 | 15 Feb 2013 | 32
Windows | 18 Jan 2013 | 14 Jun 2013 | 105
Stone | 6 Mar 2013 | 17 Aug 2013 | 118
Penthouse Brick | 11 Jul 2013 | 7 Aug 2013 | 20
Balcony Front Brick | 10 Jul 2013 | 10 Aug 2013 | 23
Revised Ext. Skin Total Duration | 2 Jan 2012 | 17 Aug 2013 | 163
Schedule Acceleration w/ Earlier Finish Date |  |  | 46
Activity | Duration (Work Days)
APC Wall Panels (Raw) | 57
APC Wall Panel w/ Phasing | 32
Schedule Acceleration | 88
w/ Phasing | 113
Item | Amount
Architectural Precast Concrete Panels (including attachment hardware) | $2,768,480
Penthouse Brick | $205,905
Metals | $292,500
Misc. | $407,355
Total | $3,468,335
Chart: 
| Brick | APC Wall Panels
Series 1 | 2676060 | 2768480
Series 2 | 1436279 | 699855

## Slide 19
APC Wall Panel Prefabrication
Wind & Seismic Loading
Introduction
Depth 1: APC Panel Prefabrication
  Overview & Existing Wall System
  Product Selection
  Transportation & Logistics
  Cost Savings & Schedule Acceleration
  Structural Feasibility Study
Depth 2: SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
Code:
IBC 2006 / ASCE 7-05
Assumption:
Panel Weight (12’ x 30’ @ 40 PSF) – 14,400 lb.
Seismic:
Wind:
Horizontal Seismic Force = 850 lb. (10% of Wind Load)
Windward exposure
Leeward exposure
Max Suction Force = 8,424 lb.
AE Senior Thesis Project
Kevin Kroener │Construction Option
Wardman West Residential
Woodley Park, NW Washington, DC

## Slide 20
Hardware Selection
APC Wall Panel Prefabrication
Wind & Seismic Loading
Introduction
Depth 1: APC Panel Prefabrication
  Overview & Existing Wall System
  Product Selection
  Transportation & Logistics
  Cost Savings & Schedule Acceleration
  Structural Feasibility Study
Depth 2: SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
Code:
IBC 2006 / ASCE 7-05
Assumption:
Panel Weight (12’ x 30’ @ 40 PSF) – 14,400 lb.
Seismic:
Wind:
Horizontal Seismic Force = 850 lb. (10% of Wind Load)
Windward exposure
Leeward exposure
Max Suction Force = 8,424 lb.
Working Capacity = 2,680 lb. < 2,106 lb. (Max Suction Force per attachment point)
AE Senior Thesis Project
Kevin Kroener │Construction Option
Wardman West Residential
Woodley Park, NW Washington, DC
Courtesy of JVI

## Slide 21
Hardware Selection
APC Wall Panel Prefabrication
Lateral Attachment & Spandrel Beam Redesign
Wind & Seismic Loading
Introduction
Depth 1: APC Panel Prefabrication
  Overview & Existing Wall System
  Product Selection
  Transportation & Logistics
  Cost Savings & Schedule Acceleration
  Structural Feasibility Study
Depth 2: SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
Code:
IBC 2006 / ASCE 7-05
Assumption:
Panel Weight (12’ x 30’ @ 40 PSF) – 14,400 lb.
Seismic:
Wind:
Horizontal Seismic Force = 850 lb. (10% of Wind Load)
Windward exposure
Leeward exposure
Max Suction Force = 8,424 lb.
Working Capacity = 2,680 lb. < 2,106 lb. (Max Suction Force per attachment point)
16’’ x 9’’ Spandrel Beam
Added Cost:
$ 54,000
AE Senior Thesis Project
Kevin Kroener │Construction Option
Wardman West Residential
Woodley Park, NW Washington, DC
Courtesy of JVI

## Slide 22
Introduction
Depth 1: APC Panel Prefabrication
Depth 2: SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
AE Senior Thesis Project
Kevin Kroener │Construction Option
Wardman West Residential
Woodley Park, NW Washington, DC

## Slide 23
SIPS
Original Brick Masonry Schedule
Introduction
Depth 1: APC Panel Prefabrication
Depth 2: SIPS
  Original Schedule Analysis
  Brick SIPS
  APC Panel SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
Elevation | Activity | Start | Finish | Duration
South | Brick | 8 Mar 2013 | 15 June 2013 | 71
 | Washdown & Balcony Fronts | 19 Sept 2013 | 22 Oct 2013 | 33
Court | Brick | 8 Mar 2013 | 13 June 2013 | 69
 | Washdown & Balcony Fronts | 16 Aug 2013 | 10 Sept 2013 | 25
East | Brick | 15 June 2013 | 20 Sept 2013 | 69
 | Washdown & Balcony Fronts | 27 Sept 2013 | 22 Oct 2013 | 25
North | Brick | 15 June 2013 | 20 Sept 2013 | 69
 | Washdown & Balcony Fronts | 20 Sept 2013 | 15 Oct 2013 | 25
Total |  | 8 Mar 2013 | 22 Oct 2013 | 162
Total (excluding washdown & balcony fronts) |  | 8 Mar 2013 | 27 Sept 2013 | 145
Typical Elevation Duration – 70 Days
Total Brick Duration – 145 Days
AE Senior Thesis Project
Kevin Kroener │Construction Option
Wardman West Residential
Woodley Park, NW Washington, DC
Courtesy of Clark Construction

## Slide 24
SIPS
Brick SIPS Schedule
Introduction
Depth 1: APC Panel Prefabrication
Depth 2: SIPS
  Original Schedule Analysis
  Brick SIPS
  APC Panel SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
Floor Level | Productivity Rate (per mason)
1 | 175 brick/day
2 | 175 brick/day
3 | 175 brick/day
4 | 170 brick/day
5 | 165 brick/day
6 | 160 brick/day
7 | 155 brick/day
8 | 150 brick/day
AE Senior Thesis Project
Kevin Kroener │Construction Option
Wardman West Residential
Woodley Park, NW Washington, DC

## Slide 25
SIPS
Brick SIPS Schedule
Introduction
Depth 1: APC Panel Prefabrication
Depth 2: SIPS
  Original Schedule Analysis
  Brick SIPS
  APC Panel SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
4th Floor – Zone E (East Elevation)
Total Area – 375 S.F.
375 S.F. × (6.55 brick)/(S.F.) = 2,457 brick
2,457 ÷ (170 (brick )/(per mason) × 3 masons) × 1.25 (6 hrs. of labor) = 6 days
Sample Calculation:
Floor Level | Productivity Rate (per mason)
1 | 175 brick/day
2 | 175 brick/day
3 | 175 brick/day
4 | 170 brick/day
5 | 165 brick/day
6 | 160 brick/day
7 | 155 brick/day
8 | 150 brick/day
AE Senior Thesis Project
Kevin Kroener │Construction Option
Wardman West Residential
Woodley Park, NW Washington, DC

## Slide 26
SIPS
Brick SIPS Schedule
Introduction
Depth 1: APC Panel Prefabrication
Depth 2: SIPS
  Original Schedule Analysis
  Brick SIPS
  APC Panel SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
4th Floor – Zone E (East Elevation)
Total Area – 375 S.F.
Sample Calculation:
Floor Level | Productivity Rate (per mason)
1 | 175 brick/day
2 | 175 brick/day
3 | 175 brick/day
4 | 170 brick/day
5 | 165 brick/day
6 | 160 brick/day
7 | 155 brick/day
8 | 150 brick/day
AE Senior Thesis Project
Kevin Kroener │Construction Option
375 S.F. × (6.55 brick)/(S.F.) = 2,457 brick
2,457 ÷ (170 (brick )/(per mason) × 3 masons) × 1.25 (6 hrs. of labor) = 6 days
Wardman West Residential
Woodley Park, NW Washington, DC

## Slide 27
SIPS
Brick SIPS Schedule
Introduction
Depth 1: APC Panel Prefabrication
Depth 2: SIPS
  Original Schedule Analysis
  Brick SIPS
  APC Panel SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
4th Floor – Zone E (East Elevation)
Total Area – 375 S.F.
375 S.F. × (6.55 brick)/(S.F.) = 2,457 brick
2,457 ÷ (170 (brick )/(per mason) × 3 masons) × 1.25 (6 hrs. of labor) = 6 days
Sample Calculation:
Floor Level | Productivity Rate (per mason)
1 | 175 brick/day
2 | 175 brick/day
3 | 175 brick/day
4 | 170 brick/day
5 | 165 brick/day
6 | 160 brick/day
7 | 155 brick/day
8 | 150 brick/day
Total Brick SIPS Duration - 133 Days
Schedule Acceleration - 12 Days
AE Senior Thesis Project
Kevin Kroener │Construction Option
Wardman West Residential
Woodley Park, NW Washington, DC

## Slide 28
SIPS
APC Wall Panel SIPS Schedule
Introduction
Depth 1: APC Panel Prefabrication
Depth 2: SIPS
  Original Schedule Analysis
  Brick SIPS
  APC Panel SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
Zone G1
Zone G2
Panel Erection Productivity Rate – 6 panels/day
Construction Zone | Elevation | # of Panels | Crane | Duration (Days)
A1 | East | 22 | Mobile | 4
A2 | East | 26 | Mobile | 5
A3 | East | 22 | Mobile | 4
B | North | 38 | Mobile | 7
C | Northwest | 21 | Mobile | 4
D | South Courtyard | 29 | Tower | 5
E | West Courtyard | 34 | Tower | 6
F | North Courtyard | 26 | Tower | 5
G1 | South | 26 | Tower | 5
G2 | South | 25 | Tower | 5
H | Southwest | 21 | Tower | 4
Total |  | 290 |  | 54
Average # of Panels per Zone - 27
AE Senior Thesis Project
Kevin Kroener │Construction Option
Wardman West Residential
Woodley Park, NW Washington, DC

## Slide 29
SIPS
APC Wall Panel SIPS Schedule
Introduction
Depth 1: APC Panel Prefabrication
Depth 2: SIPS
  Original Schedule Analysis
  Brick SIPS
  APC Panel SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
Zone G1
Zone G2
Panel Erection Productivity Rate – 6 panels/day
Total APC Wall Panel SIPS Duration - 54 Days
Schedule Acceleration - 3 Days
Construction Zone | Elevation | # of Panels | Crane | Duration (Days)
A1 | East | 22 | Mobile | 4
A2 | East | 26 | Mobile | 5
A3 | East | 22 | Mobile | 4
B | North | 38 | Mobile | 7
C | Northwest | 21 | Mobile | 4
D | South Courtyard | 29 | Tower | 5
E | West Courtyard | 34 | Tower | 6
F | North Courtyard | 26 | Tower | 5
G1 | South | 26 | Tower | 5
G2 | South | 25 | Tower | 5
H | Southwest | 21 | Tower | 4
Total |  | 290 |  | 54
Average # of Panels per Zone - 27
AE Senior Thesis Project
Kevin Kroener │Construction Option
Wardman West Residential
Woodley Park, NW Washington, DC

## Slide 30
Introduction
Depth 1: APC Panel Prefabrication
Depth 2: SIPS
Depth 3: Safety Evaluation
  Scoring System Comparison
Conclusions & Recommendations
Acknowledgements
Safety Evaluation
Scoring Criteria:
AE Senior Thesis Project
Kevin Kroener │Construction Option
Wardman West Residential
Woodley Park, NW Washington, DC
Scoring Value | Level of Concern
1 | Safety Category is considered fairly safe with a low level of safety concern involved.
2 | Safety Category is considered somewhat hazardous with a moderate level of safety concern involved.
3 | Safety Category is considered very dangerous with a high level of safety concern involved.
Safety Category | Precast Wall Panel Erection & Installation | Brick Masonry Installation
Fall Protection | 3 | 3
Equipment Inspection | 2 | 3
Safety Training | 2 | 1
Hazardous Materials | 2 | 2
Incidents/Injuries | 3 | 2
Total Score | 12 | 11

## Slide 31
Introduction
Depth 1: APC Panel Prefabrication
Depth 2: SIPS
Depth 3: Safety Evaluation
  Scoring System Comparison
Conclusions & Recommendations
Acknowledgements
Safety Evaluation
Safety Category | Precast Wall Panel Erection & Installation | Brick Masonry Installation
Fall Protection | 3 | 3
Equipment Inspection | 2 | 3
Safety Training | 2 | 1
Hazardous Materials | 2 | 2
Incidents/Injuries | 3 | 2
Total Score | 12 | 11
Scoring Criteria:
Scoring Value | Level of Concern
1 | Safety Category is considered fairly safe with a low level of safety concern involved.
2 | Safety Category is considered somewhat hazardous with a moderate level of safety concern involved.
3 | Safety Category is considered very dangerous with a high level of safety concern involved.
AE Senior Thesis Project
Kevin Kroener │Construction Option
Wardman West Residential
Woodley Park, NW Washington, DC

## Slide 32
Introduction
Depth 1: APC Panel Prefabrication
Depth 2: SIPS
Depth 3: Safety Evaluation
  Scoring System Comparison
Conclusions & Recommendations
Acknowledgements
Safety Evaluation
Scoring Criteria:
Activity Hazard Analysis:
Principle Steps
Potential Hazards
Recommended Controls
Required Equipment
Inspection Requirements
Training Requirements
AE Senior Thesis Project
Kevin Kroener │Construction Option
Wardman West Residential
Woodley Park, NW Washington, DC
Scoring Value | Level of Concern
1 | Safety Category is considered fairly safe with a low level of safety concern involved.
2 | Safety Category is considered somewhat hazardous with a moderate level of safety concern involved.
3 | Safety Category is considered very dangerous with a high level of safety concern involved.
Safety Category | Precast Wall Panel Erection & Installation | Brick Masonry Installation
Fall Protection | 3 | 3
Equipment Inspection | 2 | 3
Safety Training | 2 | 1
Hazardous Materials | 2 | 2
Incidents/Injuries | 3 | 2
Total Score | 12 | 11

## Slide 33
Introduction
Depth 1: APC Panel Prefabrication
Depth 2: SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
AE Senior Thesis Project
Kevin Kroener │Construction Option
Conclusions & Recommendations
Wardman West Residential
Woodley Park, NW Washington, DC
  Analysis 1: Architectural Precast Concrete Wall Panels
  Accelerated Schedule – 46 Days
  Saved $ 646,000
  Improved Quality
  Structurally Feasible

## Slide 34
Introduction
Depth 1: APC Panel Prefabrication
Depth 2: SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
AE Senior Thesis Project
Kevin Kroener │Construction Option
      Analysis 2: SIPS (Short Interval Production Schedule)
      Accelerated Schedule
        Brick – 12 Days
        APC Wall Panels – 3 Days
      Improved Productivity
Conclusions & Recommendations
Wardman West Residential
Woodley Park, NW Washington, DC
  Analysis 1: Architectural Precast Concrete Wall Panels
  Accelerated Schedule – 46 Days
  Saved $ 646,000
  Improved Quality
  Structurally Feasible

## Slide 35
Introduction
Depth 1: APC Panel Prefabrication
Depth 2: SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
AE Senior Thesis Project
Kevin Kroener │Construction Option
      Analysis 2: SIPS (Short Interval Production Schedule)
      Accelerated Schedule
        Brick – 12 Days
        APC Wall Panels – 3 Days
      Improved Productivity
Conclusions & Recommendations
          Analysis 3: Safety Evaluation
          Identified Safety Concerns
          Improved Site Safety w/ AHA
Wardman West Residential
Woodley Park, NW Washington, DC
  Analysis 1: Architectural Precast Concrete Wall Panels
  Accelerated Schedule – 46 Days
  Saved $ 646,000
  Improved Quality
  Structurally Feasible

## Slide 36
Introduction
Depth 1: APC Panel Prefabrication
Depth 2: SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
AE Senior Thesis Project
Kevin Kroener │Construction Option
Acknowledgements
Industry Acknowledgements
Special Thanks
Academic Acknowledgments
Ray Sowers – Faculty Advisor &
The Architectural Engineering Department
Abe Vogel - Clark Construction Group, LLC
Sara Hand - Clark Construction Group, LLC
Wardman West Residential Project Team
John O’Keefe – Atkinson Construction
Matt Quigg – Gate Precast Company
Ed Kroener – WorleyParsons
Julia Gamble
My Family and Friends
Wardman West Residential
Woodley Park, NW Washington, DC

## Slide 37
Wardman West Residential
Introduction
Depth 1: APC Panel Prefabrication
Depth 2: SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
Wardman West Residential
Woodley Park, NW Washington, DC
AE Senior Thesis Project
Kevin Kroener │Construction Option
Questions?

## Slide 38
Introduction
Depth 1: APC Panel Prefabrication
Depth 2: SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
AE Senior Thesis Project
Kevin Kroener │Construction Option
Wardman West Residential
Woodley Park, NW Washington, DC

## Slide 39
Introduction
Depth 1: APC Panel Prefabrication
Depth 2: SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
AE Senior Thesis Project
Kevin Kroener │Construction Option
Wardman West Residential
Woodley Park, NW Washington, DC

## Slide 40
Introduction
Depth 1: APC Panel Prefabrication
Depth 2: SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
AE Senior Thesis Project
Kevin Kroener │Construction Option
Wardman West Residential
Woodley Park, NW Washington, DC

## Slide 41
Introduction
Depth 1: APC Panel Prefabrication
Depth 2: SIPS
Depth 3: Safety Evaluation
Conclusions & Recommendations
Acknowledgements
AE Senior Thesis Project
Kevin Kroener │Construction Option
Wardman West Residential
Woodley Park, NW Washington, DC