## Slide 1: The Duffy School addition & renovation
**Rendering of building supplied by Gary Gardner with Owner Permission
Penn State AE
Senior Capstone Project
Jeremy Drummond
Construction Option
Advisor: anumba
April 14th, 2014

## Slide 2
`
Jeremy Drummond│ Construction Option
The Duffy School
Addition & Renovation
April 14, 2015
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Rooftop Solar Panels
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Rooftop Solar Panels
IV. Analysis #2: Historical Requirements
V. Analysis #3: Prefab Exterior Walls
VI. Final Recommendations
VII. Acknowledgements
Introduction
Analysis 3 │Prefabricated Exterior Wall Panels
Project Overview
Analysis 1 │ Rooftop Solar Panels
Analysis 2 │Historical Requirements
Googlemaps.com
http://www.solar.excluss.com/solar-equipment/solar-panels/
Taken by Jeremy Drummond
http://cptmfg.com/portfolio/pews.php

## Slide 3
Jeremy Drummond │ Construction Option
The Duffy School
Addition & Renovation
April 14, 2015
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
  Project Background
III. Analysis #1: Rooftop Solar Panels
IV. Analysis #2: Historical Requirements
V. Analysis #3: Prefab Exterior Walls
VI. Final Recommendations
VII. Acknowledgements
Project Background
General Building Information | 
Building Name | The Duffy School Addition and Renovation
Location | Florence, NJ
Function | Residential
Size | 70,593 GSF
Height | 3 Stories
Cost | $9.3 Million GMP
Construction | April ‘14- April '15
Delivery | Design-Bid-Build
Building History:
  Marcella. L Duffy School 1870
  Expansion 1950
  Closed 2008
Building Use:
  Affordable Senior Citizen Apartments
  53 New Units
  Gym, Entertainment Center, Library, Doctors Office, Kitchen, Etc.
Notes: 4 classroom school in 1870
Addition in 1950s to k-8
Closed in 2008 due to high cost of hvac

## Slide 4
Jeremy Drummond│ Construction Option
The Duffy School
Addition & Renovation
April 14, 2015
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Rooftop Solar Panels
  Problem Identification
  Components
  Feasibility Analysis
  Electrical Breadth
  Implementation & Recommendation
IV. Analysis #2: Historical Requirements
V. Analysis #3: Prefab Exterior Walls
VI. Final Recommendations
VII. Acknowledgements
Analysis #1
Implementing Rooftop Solar Panels

## Slide 5
Energy Costs
Jeremy Drummond │ Construction Option
The Duffy School
Addition & Renovation
April 14, 2015
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  Problem Identification
  Components
  Feasibility Analysis
  Electrical Breadth
  Implementation & Recommendation
IV. Analysis #2: Historical Requirements
V. Analysis #3: Prefab Exterior Walls
VI. Final Recommendations
VII. Acknowledgements
Proposed Solution:
  Rooftop Solar Panels
Research Goal:
  Different types of photovoltaic systems
  Sunlight Properties
  Cost vs. Schedule
Problem Identification:
  Affordable Apartments
  Apartment Amenities
  Payment Method?
http://www.solar.excluss.com/solar-equipment/solar-panels/
Notes: 7 apts for 30% below medium income
20 for 50%
21 for 60%
5 for homeless

## Slide 6
Solar Panel Components
Jeremy Drummond │ Construction Option
The Duffy School
Addition & Renovation
April 14, 2015
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  Problem Identification
  Components
  Feasibility Analysis
  Electrical Breadth
  Implementation & Recommendation
IV. Analysis #2: Historical Requirements
V. Analysis #3: Prefab Exterior Walls
VI. Final Recommendations
VII. Acknowledgements
System:
  Grid-tied system
  4 rows of 9 panels (36 panels)
  SunPower X21- 345 Panel
  UltraLITE Model ELU14000 Centralized Inverter
  IronRidge XR1000
Placement:
  New Addition
  EPDM Roof
  Inverter Location
  AC panel and utility tie in located in RM
Created by Jeremy Drummond

## Slide 7
Jeremy Drummond │ Construction Option
The Duffy School
Addition & Renovation
April 14, 2015
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Rooftop solar Panels
  Problem Identification
  Components
  Feasibility Analysis
  Electrical Breadth
  Implementation & Recommendation
IV. Analysis #2: Historical Requirements
V. Analysis #3: Prefab Exterior Walls
VI. Final Recommendations
VII. Acknowledgements
Feasibility Analysis
Schedule:
  Installation Process
  Longest Task
  Total- 18.5 Days
Cost:
  Prices
  Installation
  Total- $69,270
Solar Panel Installation |  |  |  | 
Item | Qty. | Unit | Hours | Total
Mount | 36 | Ea. | 1.25 | 45
Rack | 4 | Per 9 Mounts | 0.75 | 3
Solar Panels | 36 | Ea. | 1 | 36
Inverter | 1 | Ea. | 4 | 4
Circuit Breaker | 1 | Ea. | 1.5 | 1.5
#12 AWG | 20 | LF | 0.5 | 10
#8 AWG | 6 | LF | 0.5 | 3
3/4" Conduit | 1153 | LF | 0.03 | 34.6
1/2" Conduit | 42 | LF | 0.25 | 10.5
 |  |  |  | 147.6
Solar Panel Cost |  |  |  | 
Item | Cost | Qty. | Unit | Total Cost
Mount | $0.11 | 12420 | Watt | $1,366.20
Rack | $322.54 | 4 | Ea. | $1,290.16
Solar Panels | $426.25 | 36 | Ea. | $15,345.00
Inverter | $5,153.88 | 1 | Ea. | $5,153.88
Circuit Breaker | $912.05 | 1 | Ea. | $912.05
#12 AWG | $47.69 | 20 | LF | $953.80
#8 AWG | $89.23 | 6 | LF | $535.38
3/4" Conduit | $3.57 | 1153 | LF | $4,116.21
1/2" Conduit | $2.44 | 42 | LF | $102.48
Solar Panel Installation | $3.18 | 12420 | Watt | $39,495.60
 |  |  |  | $69,270.76

## Slide 8
Jeremy Drummond │ Construction Option
The Duffy School
Addition & Renovation
April 14, 2015
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Rooftop solar Panels
  Problem Identification
  Components
  Feasibility Analysis
  Electrical Breadth
  Implementation & Recommendation
IV. Analysis #2: Historical Requirements
V. Analysis #3: Prefab Exterior Walls
VI. Final Recommendations
VII. Acknowledgements
Electrical Breadth
Power Usage:
  Receptacles
  Lighting
  Dryer
  Washer
  Refrigerator
  Fireplace
  Exercise Equipment
Shading:

## Slide 9
Payback Period:
  Total Cost- $69,270
  36 Panels
  kWh
  Electrical Rate
  Federal Cash Incentive
Jeremy Drummond │ Construction Option
The Duffy School
Addition & Renovation
April 14, 2015
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Rooftop solar Panels
  Problem Identification
  Components
  Feasibility Analysis
  Electrical Breadth
  Implementation & Recommendation
IV. Analysis #2: Historical Requirements
V. Analysis #3: Prefab Exterior Walls
VI. Final Recommendations
VII. Acknowledgements
Electrical Breadth
Payback Period:
  Total Cost- $69,270
  36 Panels
  60480 kWh per day Output
  Electrical Rate- $0.12
Payback Period:
  Annual Energy Value- $3,559
  Annual System Output-
  11 Years

## Slide 10
Solar Panel Implementation
Jeremy Drummond │ Construction Option
The Duffy School
Addition & Renovation
April 14, 2015
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Rooftop Solar Panels
  Problem Identification
  Components
  Feasibility Analysis
  Electrical Breadth
  Implementation & Recommendation
IV. Analysis #2: Historical Requirements
V. Analysis #3: Prefab Exterior Walls
VI. Final Recommendations
VII. Acknowledgements
Recommendation:
  Implement Rooftop Solar Panels
Potential Value Added:
  Occupant Satisfaction
  Profit after 11 years
  NJ Green Checklist
Schedule Implications:
  Design Phase: Implement Early
    Design-Review meetings between project participants & end users
    Changes can be costly to implement later in the project lifecycle
  Construction Phase: During interior finishes
Schedule Impact:
  18.5 Days
Cost Impact:
  $69,270

## Slide 11
Jeremy Drummond │ Construction Option
The Duffy School
Addition & Renovation
April 14, 2015
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: rooftop solar panels
IV. Analysis #2: Historical Requirements
  Current vs. Prefabricated Façade
  Panel Design
  Mechanical Breadth Analysis
  Panel Implementation
  Conclusion & Recommendations
V. Analysis #3: prefab exterior Walls
VI. Final Recommendations
VII. Acknowledgements
Analysis #2
Historical Requirements

## Slide 12
Jeremy Drummond │ Construction Option
The Duffy School
Addition & Renovation
April 14, 2015
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: rooftop solar panels
IV. Analysis #2: Historical Requirements
  Requirements
  Historical Consultant
  Conclusion & Recommendations
V. Analysis #3: prefab exterior Walls
VI. Final Recommendations
VII. Acknowledgements
Requirements
Requirements:
  Chalkboards
  Trim
  Tin Ceilings
  Border
  Panels
Provided by Gary Gardner Construction
Provided by Gary Gardner Construction

## Slide 13
Jeremy Drummond │ Construction Option
The Duffy School
Addition & Renovation
April 14, 2015
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: rooftop solar panels
IV. Analysis #2: Historical Requirements
  Requirements
  Historical consultant
  Conclusion & Recommendations
V. Analysis #3: prefab exterior Walls
VI. Final Recommendations
VII. Acknowledgements
Historical Consultant
Consultant:
  Keystone Preservation Group
  Location
  Previous Projects
  Cost???
Issue #1:
  Current Storage
  Item Movement
  On-Site Containers
Created by Jeremy Drummond
Taken by Jeremy Drummond

## Slide 14
Jeremy Drummond │ Construction Option
The Duffy School
Addition & Renovation
April 14, 2015
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: rooftop solar panels
IV. Analysis #2: Historical Requirements
  Requirements
  Historical consultant
  Conclusion & Recommendations
V. Analysis #3: prefab exterior Walls
VI. Final Recommendations
VII. Acknowledgements
Historical Consultant
Issue #3:
  Installation Issues
  Labeling
  Consultant
Issue #2:
  Window Procurement
  Schedule Delays
  Consultant
Provided by Keystone Preservation Group
Taken by Jeremy Drummond
Provided by Gary Gardner Construction

## Slide 15
Comparision Summary |  | 
Item | Consultant Firm | No Firm
Fee | $35,000 | x
General Conditions | x | $37,000
Schedule | Save 27 Days | x
Total | $35,000 | $37,000
 | Save $2,000 | 
Jeremy Drummond │ Construction Option
The Duffy School
Addition & Renovation
April 14, 2015
Implementation
Final Conclusions:
  On-Site Storage Container
  Material Procurement
  Labeling
Recommendation:
    Recommend hiring The Keystone Preservation Group to do historical consulting for The Duffy School.
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: rooftop solar panels
IV. Analysis #2: Historical Requirements
  Requirements
  Historical consultant
  Conclusion & Recommendations
V. Analysis #3: prefab exterior panels
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: rooftop solar panels
IV. Analysis #2: Historical Requirements
  Requirements
  Historical consultant
  Conclusion & Recommendations
V. Analysis #3: prefab exterior Walls
VI. Final Recommendations
VII. Acknowledgements
Schedule Impact:
  27 Days
Cost Impact:
  +$2,000
Comparison Summary |  | 
Item | Consultant Firm | No Firm
Fee | $35,000 | x
General Conditions | x | $37,000
Schedule | Save 27 Days | x
Total | $35,000 | $37,000
 | Save $2,000 | 
Architectural Breadth

## Slide 16
Jeremy Drummond │ Construction Option
The Duffy School
Addition & Renovation
April 14, 2015
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Analysis #3
Prefabricated Exterior Wall Panels
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Rooftop Solar Panels
IV. Analysis #2: Historical Requirements
V. Analysis #3: Prefab Exterior Walls
  Current vs. Prefabricated Façade
  Panel Design
  Panel Implementation
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements

## Slide 17
Jeremy Drummond │ Construction Option
The Duffy School
Addition & Renovation
April 14, 2015
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Opportunity Identification:
  Time & Labor Intensive
  Site Congestion
  Weather Delays
  Critical Path
Research Goals:
  Identify alternative panel
  Reduce schedule & cost
  Reduce site congestion & trade coordination on site
Original Façade:
  3.5” Brick on Wood Stud
  Cost
  Schedule
Proposed Facade:
  9” Insulated Precast Panel
  Embedded Thin Brick
  Cost = $32/SF
  Erection = 8 panels/ day
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Rooftop Solar Panels
IV. Analysis #2: Historical Requirements
V. Analysis #3: Prefab Exterior Walls
  Current vs. Prefabricated Façade
  Panel Design
  Panel Implementation
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Façade Comparison
Provided by Gary Gardner Construction
Slenderwall.com

## Slide 18
Jeremy Drummond │ Construction Option
The Duffy School
Addition & Renovation
April 14, 2015
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Panel Design
Panel Design:
  Consistency & Transportation
  Span Building Height
  Maximum width 12’
  Total 16 precast panels
    4 different panel types
Panel Installation Durations |  |  | 
Elevation | Panel QTY. | Duration | Adjusted Duration
South | 6 | .75 Days | 1 Day
North | 6 | .75 Days | 1 Day
East | 4 | .5 Days | .75 Days
Total | 16 | 2 Days | 2.75 Days
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Rooftop Solar Panels
IV. Analysis #2: Historical Requirements
V. Analysis #3: Prefab Exterior Walls
  Current vs. Prefabricated Façade
  Panel Design
  Panel Implementation
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
North
South
East
Created by Jeremy Drummond
Created by Jeremy Drummond
Created by Jeremy Drummond

## Slide 19
Jeremy Drummond │ Construction Option
The Duffy School
Addition & Renovation
April 14, 2015
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Panel Implementation
Site Layout:
Building Enclosure Construction Cost Comparison |  |  |  |  | 
Material | Total (SF) | Prefabricated Panels |  | Traditional Brick | 
 |  | Cost/SF | Total | Cost/SF | Total
Exterior Face Wall | 6,200 | $32.00 | $198,400 | $10.47 | $64,914
Interior Components | 6,200 | $18.73 | $116,126 | $18.73 | $116,126
Insulation | 6,200 | $1.65 | $10,230 | $2.89 | $17,918
Caulking | 1,190 | $2.18 | $2,594.20 | x | X
Transportation | x | Included | Included | x | X
Erection Equipment | x | Included | Included | x | $35,026
Total |  | $54.56 | $327,350 | $32.09 | $233,984
Cost Comparison Summary |  | 
Item | Prefabricated Panels Total Cost | Traditional Brick Total Cost
Cost of Assembly | $327,350 | $233,984
General Conditions Cost | $466,630 | $487,156
Total | $793,980 | $721,140
Cost Implications:
Difference
+ $72,840
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Rooftop Solar Panels
IV. Analysis #2: Historical Requirements
V. Analysis #3: Prefab Exterior Walls
  Current vs. Prefabricated Façade
  Panel Design
  Panel Implementation
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Created by Jeremy Drummond

## Slide 20
Jeremy Drummond │ Construction Option
The Duffy School
Addition & Renovation
April 14, 2015
Panel Implementation
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Rooftop Solar Panels
IV. Analysis #2: Historical Requirements
V. Analysis #3: Prefab Exterior Walls
  Current vs. Prefabricated Façade
  Panel Design
  Panel Implementation
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Cost Implications:
  Implement = Additional $6/SF
  Interior Components Same
    Vapor Barrier, Sheathing & Backup
  General Conditions Savings
    15 Days = $20,526
Final Conclusions:
  16 Architectural Precast Panels
  Schedule Reduction = 15 Days
  Implementation Cost = $72,840
Recommendation:
  Not in owner’s best interest to pursue
    Increased cost and planning for implementation outweigh savings in schedule and building performance
Created by Jeremy Drummond

## Slide 21
Conclusions
Jeremy Drummond │ Construction Option
The Duffy School
Addition & Renovation
April 14, 2015
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
IV. Analysis #2: Façade Prefabrication
V. Analysis #3: Revaluating Comp. Slab
VI. Final Recommendations
VII. Acknowledgements
Analysis 1 │ Rooftop solar Panels
  Implement Rooftop Solar Panels
    Save Cost
    Help Occupants
Analysis 3 │ Prefab Exterior Walls
  Would not recommend the prefabrication of the building’s facade
    Increased Cost & Planning
    Reduced Schedule
Analysis 2│ Historical Requirements
  Would hire an historical consultant firm
    Reduced Schedule & Planning
    Increased upfront Cost
Provided by Gary Gardner Construction

## Slide 22
Acknowledgements
Jeremy Drummond│ Construction Option
The Duffy School
Addition & Renovation
April 14, 2015
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Rooftop solar Panels
IV. Analysis #2: Historical Requirements
V. Analysis #3: Prefab Exterior Walls
VI. Final Recommendations
VII. Acknowledgements
Architectural Engineering Faculty:
Dr. Chimay Anumba (Advisor)
Special Thanks to:
My Family & Friends
Alex Medvesky- Gary F. Gardner
Dominic DeSantis- Gary F. Gardner
Janine Owens- Conifer LLC.
PACE Industry Members
Industry Acknowledgements:

## Slide 23
Thank You
Jeremy Drummond │ Construction Option
The Duffy School
Addition & Renovation
April 14, 2015
Presentation Outline:
I. Introduction
II. Project Overview
III. Analysis #1: Virtual Mockups
  In-Place vs. Virtual Mockups
  Virtual Mockup Development
  Virtual Mockup Implementation
  Conclusion & Recommendation
IV. Analysis #2: Façade Prefabrication
  Current vs. Prefabricated Façade
  Mechanical Breadth Analysis
  Schedule, Cost & Site Logistics
  Conclusion & Recommendations
V. Analysis #3: Revaluating Composite Slab
  Lightweight vs. Normal Concrete
  Structural Breadth Analysis
  Project Impacts
  Conclusion & Recommendations
VI. Final Recommendations
VII. Acknowledgements
Questions & Comments
Provided by Gary Gardner Construction
Provided by Gary Gardner Construction