## Slide 1
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Project Information
Depth Analysis 1
Depth Analysis 2
Depth Analysis 3
Conclusion & Recommendations
Acknowledgements
Title Page
Pennsylvania State University
Architectural Engineering
Senior Thesis Final Presentation
Atrium Medical Corporation
Headquarters Facility
40 Continental Boulevard
Merrimack NH, 03054
Jeffrey Martin
Advisor: Dr. Leicht
April 16th, 2014
Ref: Atrium Medical Project Documents
Ref: Atrium Medical Project Documents

## Slide 2
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Title Page
Depth Analysis 1
Depth Analysis 2
Depth Analysis 3
Conclusion & Recommendations
Acknowledgements
Project Information
Existing Conditions
Owner Information
Building Information
Project Information:
Existing Conditions
Location: 40 Continental Boulevard, Merrimack, NH 03054
Site Size: 2,367,100 SF
Existing Structure: 2 Story building
                114,000 SF
Previous Owner: Fidelity Investments
New Owner: Atrium Medical Corporation/ Maquet Getinge Group
Project Scope: Existing Renovation
                101,200 SF New Addition
Existing 100,000SF Building to be Renovated
Proposed 101,200 SF New Addition (Footprint)
Ref: www.google.com/maps

## Slide 3
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Title Page
Depth Analysis 1
Depth Analysis 2
Depth Analysis 3
Conclusion & Recommendations
Acknowledgements
Project Information
Existing Conditions
Owner Information
Building Information
Project Information:
Owner Information
Project Owner: Atrium Medical Corporation/ MAQUET/GETINGE Group
Previous Owner: Fidelity Investments
Reason for Purchase: Company Expansion
Bring all 450 + Employees Into One Facility.
Divisions of Work: Manufacturing, Storage, Business Offices, R&D, Engineering Shops
Specializes in R&D and Manufacturing
  Cardiology
  Radiology
  Chest Trauma
  Thoracic Drainage
Business unit of MAQUET Cardiovascular (Structured Alliance)
Member of GETINGE Group of companies
Ref: www.classiccapital.net
Ref: www.theiddoctor.info

## Slide 4
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Title Page
Depth Analysis 1
Depth Analysis 2
Depth Analysis 3
Conclusion & Recommendations
Acknowledgements
Project Information
Existing Conditions
Owner Information
Building Information
Project Information:
Building Information
Project Location: 40 Continental Boulevard, Merrimack, NH 03054
Building Size: 101,200 SF
Zoning: I-3 Industrial
Description: Single Story Building
Interior Mezzanine
CM Firm: Hutter Construction
Architect: Lavallee Brensinger
Structural Engineer: Foley Buhl Roberts
Civil Engineer: Hayner Swanson Inc.
Mechanical Engineer: Johnson & Jordan Inc.
Electrical Engineer: Gate City Electric
Ref: All Images found on www.google.com/images
Ref: Atrium Medical Project Documents

## Slide 5
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Title Page
Project Information
Depth Analysis 2
Depth Analysis 3
Conclusion & Recommendations
Acknowledgements
Depth Analysis 1
Problem Statement
Proposed Solution
Structural Breadth
Total Design Summary
Analysis Results
Depth Analysis 1:
Problem Statement
Structure: Steel Superstructure
Beams: Wide Flange Steel Beams
Columns: Wide Flange Steel Columns
Roof Joists: K-Series Joists
Lateral Bracing: HSS Steel Sections
Foundations: Concrete spread & strip footings and piers
Description of Structure:
Steel Structure: Atrium Medical Corporation
Problem: Owner not utilizing the opportunity to develop a more efficient structure, in regards to either cost or scheduling.
Ref: Atrium Medical Revit Structural Model

## Slide 6
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Title Page
Project Information
Depth Analysis 2
Depth Analysis 3
Conclusion & Recommendations
Acknowledgements
Depth Analysis 1
Problem Statement
Proposed Solution
Structural Breadth
Total Design Summary
Analysis Results
Sequence of Events:
Advantages of Precast Structures:
Disadvantages of Precast Structures:
Decrease in Project Schedule
Saves Space on-site
Saves Money (labor)
Availability
Timing
Small Margin of Error
High Material Cost
Depth Analysis 1:
Proposed Solution
Develop System Design (Precast Concrete)
Structural Breadth
Select Precast Components
Develop Load Cases
Size Precast Members
Perform Cost Analysis
Perform Install. Analysis
Results & System Comparison
Depth Analysis
Ref: All Images found on www.google.com/images

## Slide 7
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Title Page
Project Information
Depth Analysis 2
Depth Analysis 3
Conclusion & Recommendations
Acknowledgements
Depth Analysis 1
Problem Statement
Proposed Solution
Structural Breadth
  Developing a Design
  Determining Loads
  Sizing Members
Total Design Summary
Analysis Results
Depth Analysis 1:
Structural Breadth:
Developing a Design
Double Tee Beam
Inverted Tee Beam
Ledger Beam
Square Concrete Columns
Column Line 6
Column Line 5
Column Line 4
Column Line 3
Column Line 2
Column Line 1
Proposed System Layout
Ref: www.concretetech.com
Ref: www.cpm-group.com
Ref: www.dynaspan.com
Ref: www.timesunion.com
Ref: Atrium Medical Project Documents
Ref: www.nitterhouse.com/technical-info
Ref: www.nitterhouse.com/technical-info
Ref: www.nitterhouse.com/technical-info
Ref: www.condor-rebar.com

## Slide 8
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Title Page
Project Information
Depth Analysis 2
Depth Analysis 3
Conclusion & Recommendations
Acknowledgements
Depth Analysis 1
Problem Statement
Proposed Solution
Structural Breadth
  Developing a Design
  Determining Loads
  Sizing Members
Total Design Summary
Analysis Results
Snow Loads:
Snow loads from structural drawings
Flat Roof Snow Load = 42 PSF
Mechanical Loads
Loads due to (8) AHU’s and (4) RTU’s
Act as point load(s) throughout roof
Maximum AHU load = 9000 lbs.
Snow Drift Loads:
Two main roof levels
Lower Roof Height = 17’ 0”
Higher Roof Height = 27’ 8”
Max Surcharge = 92.31 PSF
Surcharge Length = 16.94
Member Self Weights & Superimposed Loads
Loads from:
  Double Tees
  Ledger & Inverted Tee Beams
  Superimposed Dead = 15 PSF
Snow Loads
Snow Drift Loads
Mechanical Loads
Superimposed Loads
Member Self Weights
Depth Analysis 1:
Structural Breadth:
Determining Loads
Ref: Atrium Medical Project Documents
Ref: www.nitterhouse.com/technical-info
Ref: www.trane.com

## Slide 9
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Title Page
Project Information
Depth Analysis 2
Depth Analysis 3
Conclusion & Recommendations
Acknowledgements
Depth Analysis 1
Problem Statement
Proposed Solution
Structural Breadth
  Developing a Design
  Determining Loads
  Sizing Members
Total Design Summary
Analysis Results
Depth Analysis 1:
Structural Breadth:
Sizing Members
Double Tee Beam
Inverted Tee Beam
Interior Ledger Beam
Concrete Column Loads
Exterior Ledger Beam
Column Line # | Total Axial Loads
Column Line 1 | 178.4 kips
Column Line 2 | 409.6 kips
Column Line 3 | 426.8 kips
Column Line 4 | 463.1 kips
Column Line 5 | 409.6 kips
Column Line 6 | 178.4 kips
Designs Selected For Columns by Column Line | 
Column Line 1 | 10" x 10" w/ 4 - #5 bars at 17 ft height
Column Line 2 | 10" x 10" w/ 4 - #10 bars at 17 ft height
Column Line 3 | 10" x 10" w/ 4 - #11 bars at 17 ft height
Column Line 4 | 12" x 12" w/ 4 - #8 bars at 27.5 ft height
Column Line 5 | 10" x 10" w/ 4 - #10 bars at 27.5 ft height
Column Line 6 | 10" x 10" w/ 4 - #5 bars at 27.5 ft height
Concrete Column Designs
0.57 k/ft.
9 kips
0.923k/ft.
6.083 k/ft.
4.289 k/ft.
2.875k/ft.
Beam Designs
26”x10’ D.T (No Topping), 26-6.6P
Inverted Tee Beam 40IT36-A
32LB28 (SP 13-6-0)
(TB 6 - #9)
18LB32 (SP 6-4-0) (TB 4 - #9)

## Slide 10
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Title Page
Project Information
Depth Analysis 2
Depth Analysis 3
Conclusion & Recommendations
Acknowledgements
Depth Analysis 1
Problem Statement
Proposed Solution
Structural Breadth
Total Design Summary
  Cost Summary
  Installation Summary
Analysis Results
Depth Analysis 1:
Total Design Summary:
Cost Summary
Type | Quantity | Length | Unit | Mat'l Cost/Unit | Total Mat'l Cost | Labor/Equip. Cost/Unit | Total Labor/Equip. Cost
Double Tee Beam | 188 | 50 | LF | $18.00 | $169,200.00 | $700.00 | $131,600.00
Inverted Tee Beam | 29 | 40 | LF | $275.00 | $319,000.00 | $700.00 | $20,300.00
Interior Ledger Beam | 10 | 40 | LF | $275.00 | $110,000.00 | $700.00 | $7,000.00
Exterior Ledger Beam | 28 | 40 | LF | $275.00 | $308,000.00 | $700.00 | $19,600.00
Column Line 1 | 10 | 17 | LF | $275.00 | $46,750.00 | $700.00 | $7,000.00
Column Line 2 | 11 | 17 | LF | $275.00 | $51,425.00 | $700.00 | $7,700.00
Column Line 3 | 11 | 17 | LF | $275.00 | $51,425.00 | $700.00 | $7,700.00
Column Line 4 | 11 | 27.5 | LF | $275.00 | $83,187.00 | $700.00 | $7,700.00
Column Line 5 | 10 | 27.5 | LF | $275.00 | $75,625.00 | $700.00 | $7,000.00
Column Line 6 | 10 | 27.5 | LF | $275.00 | $75,625.00 | $700.00 | $7,000.00
 |  |  |  | Total | $1,290,237.00 | Total | $222,600.00
 |  |  |  | Total Initial System Cost |  |  | $1,512,837.00
Footing Type | Original Cost | Cost Increase (35%)
Spread Footings | $69,225.81 | $24,229.03
Strip Footings | $25,675.92 | $8,986.57
Additional Concrete Cost |  | $33,216.00
Initial System Cost: $1,512,837.00
+
Additional Footing Cost: $33,216.00
=
Total System Cost: $1,546,053.00
Additional Footing Cost:
Total Precast Cost Summary:

## Slide 11
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Title Page
Project Information
Depth Analysis 2
Depth Analysis 3
Conclusion & Recommendations
Acknowledgements
Depth Analysis 1
Problem Statement
Proposed Solution
Structural Breadth
Total Design Summary
  Cost Summary
  Installation Summary
Analysis Results
Depth Analysis 1:
Total Design Summary:
Installation Summary
Type | Quantity
Double Tee Beam | 188
Inverted Tee Beam | 29
Interior Ledger Beam | 10
Exterior Ledger Beam | 28
Column Line 1 | 10
Column Line 2 | 11
Column Line 3 | 11
Column Line 4 | 11
Column Line 5 | 10
Column Line 6 | 10
Total Members | 318
# Picks per day | ~ 6 to 8
Days for completion | 40 to 53 Days
Total Precast Installation Summary:
Total System Installation Time: 40 to 53 days
Ref: www.timesunion.com
Ref: www.dynaspan.com
Ref: www.concretetech.com

## Slide 12
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Title Page
Project Information
Depth Analysis 2
Depth Analysis 3
Conclusion & Recommendations
Acknowledgements
Depth Analysis 1
Problem Statement
Proposed Solution
Structural Breadth
Total Design Summary
Analysis Results
Depth Analysis 1:
Analysis Results
 | Total Cost | Installation Time (days)
Precast Structural System (Proposed System) | $1,546,053.00 | 53 to 40
Steel Structural System (Original System) | $1,273,160.00 | 45
Difference | (+) $272,893.00 | (+) 8 to (-) 5
Overall Systems Comparison and Analysis Results:
Issues:
Cost is too high
Schedule decrease not significant
Costs | 
100 Ton Crane Rental Cost | $18,000.00
Add'l Cost of Precast System | $272,893.00
Total System Cost | $290,893.00
Installation Times | 
Total Steel Member Qty. | 318
# Picks per day (one crane) | ~6 to 8
# Picks per day (two cranes) | ~12 to 16
Total System Installation Time (days) | 20 to 26.5
Solution:
Add another crane on-site
Adjusted Costs and Installation Times:
Revised Precast System Cost: $1,564,053
Revised Precast System Installation Time: 20 to 26.5 days

## Slide 13
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Title Page
Project Information
Depth Analysis 2
Depth Analysis 3
Conclusion & Recommendations
Acknowledgements
Depth Analysis 1
Problem Statement
Proposed Solution
Structural Breadth
Total Design Summary
Analysis Results
Depth Analysis 1:
Analysis Results
Crane 1
Crane 2
Bed Trucks with Precast Members Move Along Building Perimeter for Ease of Access.
Truck
Truck
Project will utilize (2) 100 Ton Crawler Cranes
Cranes will move within building footprint
  (1) crane in Manufacturing area
  (1) crane in Warehouse Area
Movement of work flow from East to West
Gives Total Installation time = 20 to 26.5 days
Manufacturing
Warehouse
Ref: Atrium Medical Project Documents
Ref: www.bigge.com

## Slide 14
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Title Page
Project Information
Depth Analysis 1
Depth Analysis 3
Conclusion & Recommendations
Acknowledgements
Depth Analysis 2
Problem Statement
Proposed Solution
Mechanical Breadth
Total Design Summary
Analysis Results
Depth Analysis 2:
Problem Statement
Design Kingspan Micro-Rib Insulated Metal Panels
Location: Exterior Warehouse Area
Area (SF)
  Southern Face: 3,106 SF
  Eastern Face: 2,788 SF
  Northern Face: 10,401 SF
  Western Face: 4,016 SF
Description of Envelope:
Problem: Owner not utilizing the opportunity to create a more efficient building envelope surrounding the warehouse area.
Ref: www.kingspanpanels.us

## Slide 15
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Title Page
Project Information
Depth Analysis 1
Depth Analysis 3
Conclusion & Recommendations
Acknowledgements
Depth Analysis 2
Problem Statement
Proposed Solution
Mechanical Breadth
Total Design Summary
Analysis Results
Depth Analysis 2:
Proposed Solution
Develop System Design (Precast Insulated Panels)
Mech. Breadth
Thermal Analysis of Systems
Compare Thermal Efficiency‘s
Perform Cost Analysis
Perform Install. Analysis
Results & System Comparison
Depth Analysis
Sequence of Events:
Advantages of Precast Insulated Panels:
Disadvantages of Precast Insulated Panels:
Decrease Time in Project Schedule
Versatility
Energy & Thermal Efficiency
Fire Resistance
High Materials Cost
Timing
Description of Systems

## Slide 16
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Title Page
Project Information
Depth Analysis 1
Depth Analysis 3
Conclusion & Recommendations
Acknowledgements
Depth Analysis 2
Problem Statement
Proposed Solution
Mechanical Breadth
  Description of Systems
  Thermal Analysis & Results
Total Design Summary
Analysis Results
Depth Analysis 2:
Mechanical Breadth:
Description of Systems
Original System:
Insulated Metal Panels
Proposed System:
Precast Insulated Panels
Ref: Atrium Medical Project Documents
Ref: www.kingspanpanels.us
Ref: www.spancrete.com
Ref: www.spancrete.com
Ref: www.spancrete.com

## Slide 17
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Title Page
Project Information
Depth Analysis 1
Depth Analysis 3
Conclusion & Recommendations
Acknowledgements
Depth Analysis 2
Problem Statement
Proposed Solution
Mechanical Breadth
  Description of Systems
  Thermal Analysis & Results
Total Design Summary
Analysis Results
Depth Analysis 2:
Mechanical Breadth:
Thermal Analysis & Results
Insulated Metal Panels: Summer Conditions
Insulated Metal Panels: Winter Conditions

## Slide 18
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Title Page
Project Information
Depth Analysis 1
Depth Analysis 3
Conclusion & Recommendations
Acknowledgements
Depth Analysis 2
Problem Statement
Proposed Solution
Mechanical Breadth
  Description of Systems
  Thermal Analysis & Results
Total Design Summary
Analysis Results
Depth Analysis 2:
Mechanical Breadth:
Thermal Analysis & Results
Precast Insulated Panels: Summer Conditions
Precast Insulated Panels: Winter Conditions

## Slide 19
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Title Page
Project Information
Depth Analysis 1
Depth Analysis 3
Conclusion & Recommendations
Acknowledgements
Depth Analysis 2
Problem Statement
Proposed Solution
Mechanical Breadth
Total Design Summary
  Cost Summary
  Installation Summary
Analysis Results
Depth Analysis 2:
Total Design Summary:
Cost Summary
Location |  | Area (ft2) | Unit | Material $/Unit | Material $
Southern Face |  | 3106 | SF | 18 | $ 55,908.00
Eastern Face |  | 2788 | SF | 18 | $ 50,184.00
Northern Face |  | 10401 | SF | 18 | $ 187,218.00
Western Face |  | 4016 | SF | 18 | $ 72,288.00
 |  |  |  |  | $ 365,598.00
Location |  | Quantity | Unit | Labor/Equip $/Unit | Labor/Equip $
Southern Face |  | 14 | Ea. | 700 | $ 9,800.00
Eastern Face |  | 13 | Ea. | 700 | $ 9,100.00
Northern Face |  | 47 | Ea. | 700 | $ 32,900.00
Western Face |  | 18 | Ea. | 700 | $ 12,600.00
 |  |  |  |  | $ 64,400.00
 |  |  |  | Total Cost | $ 429,998.00
Footing Type | Original Cost | Cost Increase (35%)
Spread Footings | $40,631.00 | $14,221.00
Additional Concrete Cost |  | $14,221.00
Additional Footing Cost:
Precast Insulated Panel Cost:
Initial System Cost: $429,998.00
+
Additional Footing Cost: $14,221.00
=
Total System Cost: $444,219.00

## Slide 20
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Title Page
Project Information
Depth Analysis 1
Depth Analysis 3
Conclusion & Recommendations
Acknowledgements
Depth Analysis 2
Problem Statement
Proposed Solution
Mechanical Breadth
Total Design Summary
  Cost Summary
  Installation Summary
Analysis Results
Depth Analysis 2:
Total Design Summary:
Installation Summary
Location |  | Area (ft2) |  | Member Area (ft2) | Quantity (Area/Member Area)
Southern Face |  | 3106 |  | 221.36 | 14
Eastern Face |  | 2788 |  | 221.36 | 13
Northern Face |  | 10401 |  | 221.36 | 47
Western Face |  | 4016 |  | 221.36 | 18
 | Total Quantity |  |  |  | 92
 | # Picks per Day |  |  |  | ~6 to 8
 | Total Installation Time |  |  |  | 12 to 15
Total System Installation Time: 12 to 15 days
Precast Insulated Panel Install Time:
Ref: www.spancrete.com
Ref: www.spancrete.com

## Slide 21
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Title Page
Project Information
Depth Analysis 1
Depth Analysis 3
Conclusion & Recommendations
Acknowledgements
Depth Analysis 2
Problem Statement
Proposed Solution
Mechanical Breadth
Total Design Summary
Analysis Results
Depth Analysis 2:
Analysis Results
Insulated Metal Panel System Cost |  | 
Subtotal |  | $354,400.00
HSS Framing Cost (+) |  | $46,355.00
Metal Panel Cost (-) |  | $31,007.00
Total System Cost |  | $369,748.00
Total Wall Panel System Installation Time = |  |  |  | 67 Days |  | 
System Type |  | Area (ft^2) | % of Install. Time |  | Total Install. Time (days) | 
Metal Wall Panels |  | 7,112 | 26% |  | 17 | 
Insulated Metal Panels |  | 20,311 | 74% |  | 50 | 
Total = |  | 27,423 | 100% |  | 67 | 
 |  | Total Cost | Installation Time (days)
Precast Insulated Panels |  | $444,219.00 | 12 to 15
Insulated Metal Panels |  | $369,748.00 | 50
Difference |  | (+) $74,471 | (-) 38 to (-) 35
Insulated Metal Panel Costs:
Insulated Metal Panel Installation Time:
Overall Systems Comparison and Analysis Results:
Ref: www.bossteel.com
Ref: www.bossteel.com

## Slide 22
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Title Page
Project Information
Depth Analysis 1
Depth Analysis 2
Conclusion & Recommendations
Acknowledgements
Depth Analysis 3
Problem Statement
Proposed Solution
PtD Industry
System Selection
Typical Steel Connections
NISD Details
Analysis Results
Depth Analysis 3:
Problem Statement
Problem: Owner not utilizing the opportunity to plan and design for safety consideration prior to project’s construction.
Formal safety plan for field and office staff during construction
Superintendents have OSHA 30-Hour training
All other employees have OSHA 10-Hour training.
Weekly toolbox talks
Basic construction safety (i.e. PPE, Equip. Safety etc.)
“Training is an integral part of Hutter’s safety commitment. In addition to the traditional weekly toolbox talks, ongoing safety training is regularly provided by outside professionals. Among the topics continually addressed: competent persons, confined space, boom lifts, forklifts, snorkel lifts, CPR and first aid. All of our employees, including project managers have received the OSHA 10-Hour certified training and new employees receive the training within 30 days of hire. All of our superintendents have received OSHA 30-Hour training.”
Hutter Construction on Safety:
Summary of Safety Plan:
Ref: www.hutterconstruction.com

## Slide 23
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Title Page
Project Information
Depth Analysis 1
Depth Analysis 2
Conclusion & Recommendations
Acknowledgements
Depth Analysis 3
Problem Statement
Proposed Solution
PtD Industry
System Selection
Typical Steel Connections
NISD Details
Analysis Results
Depth Analysis 3:
Proposed Solution
PtD Industry
Typical Steel Connections
NISD Details
System Selection Based on Risk
Analysis Results
Sequence of Events:
Benefits of Implementing a Design Guide:
Barriers of Implementing a Design Guide:
Increase Safety Consideration
Increase in Quality Control
Reduce Delays
Increase in Productivity
Increase Collaboration between Designer & Constructors
Designer’s Liability
Additional Costs
Lack of Expertise

## Slide 24
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Title Page
Project Information
Depth Analysis 1
Depth Analysis 2
Conclusion & Recommendations
Acknowledgements
Depth Analysis 3
Problem Statement
Proposed Solution
PtD Industry
System Selection
Typical Steel Connections
NISD Details
Analysis Results
Industry developed to prevent hazards from occurring during construction
  Began in late 90’s
  Construction tasks & processes viewed during conceptual and design phase
  Ensures safety of workers during construction
Depth Analysis 3:
Prevention through Design Industry
Prevention through Design (PtD):
As the timeline of the project schedule increase, the ability to influence safety on the project decreases.
Prevention through Design Process:
Ref: www.asse.org
Ref: www.asse.org
Ref: www.lhsfna.org
Ref: www.designforconstructionsafety.org
Ref: www.elcosh.org

## Slide 25
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Title Page
Project Information
Depth Analysis 1
Depth Analysis 2
Conclusion & Recommendations
Acknowledgements
Depth Analysis 3
Problem Statement
Proposed Solution
PtD Industry
System Selection
Typical Steel Connections
NISD Details
Analysis Results
Depth Analysis 3:
System Selection
System Name | Safety Risk | Risk Percentage
Foundation |  | 4%
Structural Frame |  | 28%
Exterior Enclosure |  | 18%
Roof |  | 15%
Interiors |  | 5%
Plumbing |  | 1%
HVAC |  | 17%
Electrical |  | 13%
SliDeRulE Results
SliDeRulE Information:
Safety in Design Risk Evaluator
Program designed to interpret the level of construction safety risk for a particular project.
This program is used primarily for:
  Determining the level of safety risk for an entire building and each system within that building
  Comparing designs based on risks
  Learning about design features that could potentially increase or decrease risk
  Creating building designs that minimize the risk of injury for construction workers
Ref: www.constructionsliderule.org

## Slide 26
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Title Page
Project Information
Depth Analysis 1
Depth Analysis 2
Conclusion & Recommendations
Acknowledgements
Depth Analysis 3
Problem Statement
Proposed Solution
PtD Industry
System Selection
Typical Steel Connections
NISD Details
Analysis Results
Depth Analysis 3:
Typical Steel Connections
Ref: All Snips from Atrium Medical Project Documents
Ref: Atrium Medical Project Documents

## Slide 27
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Title Page
Project Information
Depth Analysis 1
Depth Analysis 2
Conclusion & Recommendations
Acknowledgements
Depth Analysis 3
Problem Statement
Proposed Solution
PtD Industry
System Selection
Typical Steel Connections
NISD Details
Analysis Results
Depth Analysis 3:
NISD Industry Standard Details
Ref: www.NISD.org
Ref: www.NISD.org
Ref: www.NISD.org
Ref: www.NISD.org

## Slide 28
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Title Page
Project Information
Depth Analysis 1
Depth Analysis 2
Conclusion & Recommendations
Acknowledgements
Depth Analysis 3
Problem Statement
Proposed Solution
PtD Industry
System Selection
Typical Steel Connections
NISD Details
Analysis Results
Depth Analysis 3:
NISD Industry Standard Details
Ref: www.NISD.org
Ref: www.NISD.org
Ref: www.NISD.org
Ref: www.NISD.org

## Slide 29
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Title Page
Project Information
Depth Analysis 1
Depth Analysis 2
Conclusion & Recommendations
Acknowledgements
Depth Analysis 3
Problem Statement
Proposed Solution
PtD Industry
System Selection
Typical Steel Connections
NISD Details
Analysis Results
Depth Analysis 3:
Analysis Results
Developed to ensure safety of workers during construction
If properly implemented, problems can be foreseen and therefore prevented
Encourages collaboration between designer and constructor
  Creates a better working relationship, less “lost in translation” incidents
  Ensures quality control, as issues during design can be managed and adjusted if necessary
Overall Benefits of a Design Guide
Ref: www.NISD.org

## Slide 30
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Title Page
Project Information
Depth Analysis 1
Depth Analysis 2
Depth Analysis 3
Acknowledgements
Conclusions & Recommendations
Conclusions & Recommendations
Depth Analysis 1:
Depth Analysis 2:
Depth Analysis 3:
Conclusion
Precast structural system imposed a $1,564,053.00 cost, with the use of (2) 100 ton crawler cranes and 20 to 26.5 days for installation
  Cost is $290,893.00 greater than original steel structure
  18.5 to 25 days less than structural steel installation
Recommendation
Install the precast concrete structure, to save time on the critical path of the project schedule
Conclusion
Precast insulated panels cost a total of $444,219.00, and require 12 to 15 days for installation. The panels also have a thermal efficiency (R-Value) of 23.78
  Cost is $74,471.00 greater than original envelope system
  Installation time is 35 to 38 days less than original envelope
  R-Value of this system is 1.64 greater than original envelope
Recommendation
Install the precast insulated panels to save time during installation
Conclusion
Design guide focused on basic steel installation/connection issues, as well as specific details pertaining to connections typically found within Atrium Medical
Recommendation
Pay the additional upfront fee to hire design professionals and implement a design guide

## Slide 31
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Title Page
Project Information
Depth Analysis 1
Depth Analysis 2
Depth Analysis 3
Conclusion & Recommendations
Acknowledgements
Acknowledgments
Industry Acknowledgements
Thank you:
David Lage
Les Somero
Bill Moyer
Daniel Zartman
Sean Landry
Academic Acknowledgements
Thank you:
Dr. Robert M Leicht
Dr. Ali M. Memari, P.E.
Moses D.F. Ling, P.E., RA
Special Thanks to:
Alyssa Stangl - fellow AE student/girlfriend
Garrett Schwier – fellow AE student/chair
All of my family and friends

## Slide 32
Atrium Medical Corporation
[Headquarters Facility]
Table of Contents
Title Page
Project Information
Depth Analysis 1
Depth Analysis 2
Depth Analysis 3
Conclusion & Recommendations
Acknowledgements
Questions?