## Slide 1: Mueller Laboratory Renovation
By
Mark Jackson
Construction Management
Dr. David Riley, Advisor

## Slide 2: Mueller Laboratory Renovation Presentation Outline: Introduction Breadth topic 1 – Roof Reinforcement Depth topic 1 – Recycling Opportunities Depth topic 2 – Site Logistics Breadth topic 2 – LED Downlights Conclusion
Introduction
Mueller Laboratory Renovation
On PSU University Park campus
$18 million project
Gutting, renovation of 4 of 7 floors
Replacement of outdated HVAC, electrical systems
Scheduled to be completed before 2015 school year

## Slide 3: Mueller Laboratory Renovation Presentation Outline: Introduction Breadth topic 1 – Roof Reinforcement Depth topic 1 – Recycling Opportunities Depth topic 2 – Site Logistics Breadth topic 2 – LED Downlights Conclusion
Roof Reinforcement
Reason for Reinforcement

## Slide 4: Mueller Laboratory Renovation Presentation Outline: Introduction Breadth topic 1 – Roof Reinforcement Depth topic 1 – Recycling Opportunities Depth topic 2 – Site Logistics Breadth topic 2 – LED Downlights Conclusion
Roof Reinforcement
z
1
2
3
1
2
3
Reason for Reinforcement
3 new air handling units (with room for a 4th

## Slide 5: Mueller Laboratory Renovation Presentation Outline: Introduction Breadth topic 1 – Roof Reinforcement Depth topic 1 – Recycling Opportunities Depth topic 2 – Site Logistics Breadth topic 2 – LED Downlights Conclusion
1
2
3
Roof Reinforcement
z
1
2
3
Reason for Reinforcement
3 new air handling units (with room for a 4th
4 laboratory exhaust fans

## Slide 6: Mueller Laboratory Renovation Presentation Outline: Introduction Breadth topic 1 – Roof Reinforcement Depth topic 1 – Recycling Opportunities Depth topic 2 – Site Logistics Breadth topic 2 – LED Downlights Conclusion
Roof Reinforcement
10
11
12
10
10
12
11
Under-deck Reinforcing Beams
25 steel beams
Next to existing concrete joists
Underneath existing concrete joists
Hung with bolts off of concrete beams

## Slide 7: Mueller Laboratory Renovation Presentation Outline: Introduction Breadth topic 1 – Roof Reinforcement Depth topic 1 – Recycling Opportunities Depth topic 2 – Site Logistics Breadth topic 2 – LED Downlights Conclusion
Roof Reinforcement
Problems with Under-Deck Reinforcement
Schedule depends on demolition
Difficulty of overhead work
Constraints on steel placement
Lowered ceiling height
AHU 3
AHU 1
AHU 2
Platform posts
1
2
3
4

## Slide 8: Mueller Laboratory Renovation Presentation Outline: Introduction Breadth topic 1 – Roof Reinforcement Depth topic 1 – Recycling Opportunities Depth topic 2 – Site Logistics Breadth topic 2 – LED Downlights Conclusion
Roof Reinforcement
AHU 3
AHU 1
AHU 2
Platform posts
1
2
3
4
AHU 3
AHU 1
AHU 2
1
2
3
4
5
Posts on beam
Advantages to Roof-Top Reinforcement
Does not depend on demolition
No overhead work means safer work, higher quality product
No constraints on steel placement
No lowered ceiling height

## Slide 9: Mueller Laboratory Renovation Presentation Outline: Introduction Breadth topic 1 – Roof Reinforcement Depth topic 1 – Recycling Opportunities Depth topic 2 – Site Logistics Breadth topic 2 – LED Downlights Conclusion
Roof Reinforcement
AHU 3
AHU 1
AHU 2
Platform posts
1
2
3
4
AHU 3
AHU 1
AHU 2
1
2
3
4
5
Posts on beam
Roof Waterproofing
Project scope includes membrane roof replacement
Install new roof membrane after steel is in place

## Slide 10: Mueller Laboratory Renovation Presentation Outline: Introduction Breadth topic 1 – Roof Reinforcement Depth topic 1 – Recycling Opportunities Depth topic 2 – Site Logistics Breadth topic 2 – LED Downlights Conclusion
Recycling Opportunities
Southampton, PA
Offers offsite sorting/recycling
Accepts general construction debris
198 miles away
Reinholds, PA
Recycles new, unpainted gypsum only
No demolition drywall
135 miles away
Lancaster, PA
Recycles new and used ceiling tiles
126 miles away
Altoona, PA
Recycles scrap metals
Offers free pick-up
Pays cash for scrap
42 miles away

## Slide 11: Mueller Laboratory Renovation Presentation Outline: Introduction Breadth topic 1 – Roof Reinforcement Depth topic 1 – Recycling Opportunities Depth topic 2 – Site Logistics Breadth topic 2 – LED Downlights Conclusion
Recycling Opportunities
Dumpster Rental
Trash Chute Rental
total rental cost
purchase cost
dumpster rental
Trash Chute Purchase
=78,418 lbs scraps steel
9751 lbs duct being installed on 1st floor
=29,253 lbs scrapped duct weight
18700 lbs per AHU
=56,100 lbs scrapped AHU weight
29,253 lbs duct weight
56,100 lbs AHUs
=85,353 lbs Mech scrap weight
Break Even Calculations
Results
Mech scrap will pay for dumpster, trash chute
Electrical scrap extra
Plumbing scrap extra

## Slide 12: Mueller Laboratory Renovation Presentation Outline: Introduction Breadth topic 1 – Roof Reinforcement Depth topic 1 – Recycling Opportunities Depth topic 2 – Site Logistics Breadth topic 2 – LED Downlights Conclusion
Legend:
Gate-------------------------
Site fencing----------------
Landscape protection----fencing
Contractor parking-------
Material Staging----------
Site Logistics

## Slide 13: Mueller Laboratory Renovation Presentation Outline: Introduction Breadth topic 1 – Roof Reinforcement Depth topic 1 – Recycling Opportunities Depth topic 2 – Site Logistics Breadth topic 2 – LED Downlights Conclusion
Legend:
Gate-------------------------
Site fencing----------------
Landscape protection----fencing
Contractor parking-------
Material Staging----------
Site Logistics

## Slide 14: Mueller Laboratory Renovation Presentation Outline: Introduction Breadth topic 1 – Roof Reinforcement Depth topic 1 – Recycling Opportunities Depth topic 2 – Site Logistics Breadth topic 2 – LED Downlights Conclusion
Legend:
Gate-------------------------
Site fencing----------------
Landscape protection----fencing
Contractor parking-------
Material Staging----------
Site Logistics

## Slide 15: Mueller Laboratory Renovation Presentation Outline: Introduction Breadth topic 1 – Roof Reinforcement Depth topic 1 – Recycling Opportunities Depth topic 2 – Site Logistics Breadth topic 2 – LED Downlights Conclusion
Legend:
Gate-------------------------
Site fencing----------------
Landscape protection----fencing
Contractor parking-------
Material Staging----------
Site Logistics

## Slide 16: Mueller Laboratory Renovation Presentation Outline: Introduction Breadth topic 1 – Roof Reinforcement Depth topic 1 – Recycling Opportunities Depth topic 2 – Site Logistics Breadth topic 2 – LED Downlights Conclusion
Site Logistics

## Slide 17: Mueller Laboratory Renovation Presentation Outline: Introduction Breadth topic 1 – Roof Reinforcement Depth topic 1 – Recycling Opportunities Depth topic 2 – Site Logistics Breadth topic 2 – LED Downlights Conclusion
Legend:
Gate-------------------------
Site fencing----------------
Landscape protection----fencing
Contractor parking-------
Material Staging----------
Site Logistics

## Slide 18: Mueller Laboratory Renovation Presentation Outline: Introduction Breadth topic 1 – Roof Reinforcement Depth topic 1 – Recycling Opportunities Depth topic 2 – Site Logistics Breadth topic 2 – LED Downlights Conclusion
Legend:
Gate-------------------------
Site fencing----------------
Landscape protection----fencing
Contractor parking-------
Material Staging----------
Site Logistics
Proposed Plan
New work site between Whitmore, Pond Labs
Whitmore accessible from south, east, west
Work site access from south, Pollock Road
Hydrant for truck-wash station

## Slide 19: Mueller Laboratory Renovation Presentation Outline: Introduction Breadth topic 1 – Roof Reinforcement Depth topic 1 – Recycling Opportunities Depth topic 2 – Site Logistics Breadth topic 2 – LED Downlights Conclusion
Legend:
Gate-------------------------
Site fencing----------------
Landscape protection----fencing
Contractor vehicles------
Semi trailers--------------
Material staging----------
Site Logistics
Proposed Plan
Fewer trees to work around
More contractor parking
More staging area
Flatter staging area
More delivery space
North entrance open for duration of construction

## Slide 20: Mueller Laboratory Renovation Presentation Outline: Introduction Breadth topic 1 – Roof Reinforcement Depth topic 1 – Recycling Opportunities Depth topic 2 – Site Logistics Breadth topic 2 – LED Downlights Conclusion
LED Downlights
Current LED Downlight Fixtures
In entryways, lobbies, bathrooms
Not in lab space
60 fixtures total
 | Wattage | Lumens | CRI | CRT
CREE 4” LED fixture | 13 | 665 | 90 | 4000
CREE 6” LED fixture 1 | 18 | 1250 | 90 | 4000
CREE 6” LED fixture 2 | 30 | 1664 | 90 | 4000

## Slide 21: Mueller Laboratory Renovation Presentation Outline: Introduction Breadth topic 1 – Roof Reinforcement Depth topic 1 – Recycling Opportunities Depth topic 2 – Site Logistics Breadth topic 2 – LED Downlights Conclusion
LED Downlights
 | Fixtures | Cost per fixture | CREE fixture total costs | Cost per screw-in bulb | Screw in bulb total costs | Difference in total costs
CREE 4” | 2 | $157 | $314 | $33 | $66 | $248
CREE 6” #1 | 48 | $157 | $7536 | $36 | $1728 | $5808
CREE 6” #2 | 10 | $204 | $2040 | $69 | $690 | $1350
 |  |  |  | Total amount saved: |  | $7406
 | Wattage | Lumens | CRI | CRT
CREE 4” LED fixture | 13 | 665 | 90 | 4000
CREE 6” LED fixture 1 | 18 | 1250 | 90 | 4000
CREE 6” LED fixture 2 | 30 | 1664 | 90 | 4000
LED bulb 1 | 13 | 700 | 92 | 2700
LED bulb 2 | 20.8 | 1250 | 94 | 2700
LED bulb 3 | 26 | 1650 | 82 | 4000
Proposed LED Downlight Fixtures
Use standard can fixtures
Use screw-in LED bulbs
Match bulb performance to spec’d fixture
Advantages of screw-in LED bulbs
Less expensive than hard-wired fixtures
Better performance from screw-in bulbs
Inexpensive maintenance
Can take advantage of technological advances

## Slide 22: Mueller Laboratory Renovation Presentation Outline: Introduction Breadth topic 1 – Roof Reinforcement Depth topic 1 – Recycling Opportunities Depth topic 2 – Site Logistics Breadth topic 2 – LED Downlights Conclusion
Conclusion
Recommendations
Move the roof reinforcement to the top of the roof deck.
Screw-in LED bulbs should be used instead of hard-wired LED downlights.
Scrap metal recycling is economical and easy.
The project’s worksite would benefit greatly from going south, not west.
1
2
3
AHU 3
AHU 1
AHU 2
1
2
3
4
5
Posts on beam

## Slide 23: Mueller Laboratory Renovation Presentation Outline: Introduction Breadth topic 1 – Roof Reinforcement Depth topic 1 – Recycling Opportunities Depth topic 2 – Site Logistics Breadth topic 2 – LED Downlights Conclusion
Acknowledgements:
Penn State University
Barton Malow
Dr. Riley
PSU AE Department

## Slide 24: Mueller Laboratory Renovation Presentation Outline: Introduction Breadth topic 1 – Roof Reinforcement Depth topic 1 – Recycling Opportunities Depth topic 2 – Site Logistics Breadth topic 2 – LED Downlights Conclusion
Questions?